## Config
SQA | Application | Deliverable Types | Reasons for Disapproval | A or D
Harald | ADOC | CII | Inaccurate information | A
Philip | AFIL | DD1 | Inadequate Description of Change | A-FP
| AMPS2G | DD2 | Incorrect Approvers | D
| ASC | DD3 | Incorrect Objective Evidence
| CMSN-Add-On | DPP | Incorrect scope
| Fabiola | DR | Insufficient testing
| FIIS | DV-CR | Insufficient traceability
| FSP | DV-UT | Multiple Errors
| GM | ESRA | N/A
| ImageCompare | FRS | Not compliant with procedure
| IRR | IA | Not following configuration management
| ITS | IDP | Not following document version control
| JAM | IDP/IIVP | Not using template
| LabSolutions | IIVP | Other
| LIC | ISSD | Requirement deficiency
| LSP | IVR
| MFCS | MCP
| PARIS | MCPR
| POD | MP
| Q-EDI | Other
| SFP | RA
| SPOC | RN
| Teklynx | SAD
| Turnover | SCA
| Unicorn | SCR
| viewLinc | SCS
| WWLIMS | SCS/RN
| XIAM | SDP
SDR
SE
SPP
SPR
SPVP
SVP
TM-DD to Code
TM-FRS to DD
TM-FRS to TP
TM-URS to FRS
TM-URS to TP
TM-URS/FRS to TP
TP
TPR
URS
URS/FRS
URS/TM
URS/FRS/TM

## ACR
SQA | Application | ACR # | Date of CR Approval or Disapproval | CR Approve or Disapprove? | ACR I&E # | Date of I&E Approval or Disapproval | I&E Approve or Disapprove? | Reason for Disapproval | Comments
Philip | GM | WI_C000001 | 2020-07-07 | D |  |  |  | Inaccurate information | Several fields empty
Philip | GM | WI_C000001 | 2020-07-09 | A
Philip | FSP | WI_C000002 | 2020-07-10 | A-FP
Philip | ITS | WI_C000011 | 2020-09-09 | D |  |  |  | Inaccurate information | Description contents insufficient
Philip | ITS | WI_C000011 | 2020-09-09 | A
Philip | ITS | WI_C000012 | 2020-09-24 | D |  |  |  | Inaccurate information | Description contents insufficient
Philip | ITS | WI_C000012 | 2020-09-24 | A
Philip | ITS | WI_C000012 |  |  |  | 2020-10-19 | A-FP
Philip | ITS | WI_C000013 | 2020-10-19 | A-FP
Philip | LSP | WI_L000001 | 2020-07-21 | A-FP
Philip | LSP | WI_L000001 |  |  |  | 2020-07-29 | A-FP
Philip | LSP | WI_L000002 | 2020-07-29 | D |  |  |  | Inaccurate information | GER42 serial# missing
Philip | LSP | WI_L000002 | 2020-07-31 | A
Harald | LSP | WI_L000003 | 2020-07-31 | A-FP |  | 2020-09-09 | A-FP
Harald | LSP | WI_L000004 | 2020-08-17 | A-FP |  | 2020-09-09 | A-FP
Harald | LSP | WI_L000005 | 2020-10-01 | A-FP |  | 2020-10-02 | A-FP
Harald | LSP | WI_L000006 | 2020-09-17 | A-FP
Harald | LSP | WI_L000007 | 2020-09-30 | D |  |  |  | Inaccurate information | Description contents insufficient
Harald | LSP | WI_L000007 | 2020-09-30 | A
Harald | LSP | WI_L000010 | 2020-10-13 | A-FP |  | 2020-10-14 | A-FP

## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove | Date of Approval or Disapproval | Reason for Disapproval | Comments
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-10 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-14 | Inaccurate information
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-15 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-16 | Inaccurate information
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-17 | Inaccurate information | Mismatch of documentation impact vs. reality
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | D | 2020-01-17 | Inaccurate information | Schedule summary out of date
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | D | 2020-01-17 | Multiple Errors | Revision history incomplete, tracing incorrect
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-17 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-17 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-17 | Multiple Errors
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-20 | Inaccurate information | Test execution planning incorrect
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | D | 2020-01-20 | Inaccurate information | Revision history incorrect, table name duplicate
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-20 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-20 | Multiple Errors
Philip | Release 02.21.00 | ADOC | DV-UT | 1 | Incoming | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | IDP/IIVP | 1 | N/A | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 2 | TP60 | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | CII | 1 | N/A | A-FP | 2020-01-22
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | D | 2020-01-22 | Inaccurate information | Signature entry missing for post-turnover steps
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | A | 2020-01-22
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | D | 2020-01-22 | Inaccurate information | Impact analysis insufficient
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | A | 2020-01-22
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | TP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | A | 2020-01-22
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | D | 2020-01-23 | Inaccurate information | Test execution analysis missing
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP60 | A-FP | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP53 | A-FP | 2020-01-23
Harald | Release 3.1 | MFCS | CII | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER42 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SCR | 1 | A1900137 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SPR | 1 | A2000003 | A-FP | 2020-01-27
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-27 | Inaccurate information
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-27 | Multiple Errors
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-29 | Other | Needs to include related upcoming ADOC release
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | D | 2020-01-29 | Inaccurate information | Printer exchange, several explanations missing
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | A | 2020-01-29 |  | Printer exchange
Philip | Release 02.21.01 | ADOC | SPR | 1 | A2000010 | A-FP | 2020-01-30
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-30 | Inaccurate information | Tailoring justifications missing, deliverables missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-30 | Other | Dependencies between LIC & ADOC releases missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | A | 2020-01-30
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-30 | Inaccurate information | Traceability information incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | D | 2020-01-31 | Inaccurate information | Several references incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | A | 2020-01-31
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | D | 2020-01-31 | Inaccurate information | Constraints missing
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | A | 2020-01-31
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Action missing for newly added objects
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | A | 2020-01-31
Philip | Release 01.05.00 | LIC | TP | 1 | TP07 | A-FP | 2020-01-31
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | A | 2020-01-31
Philip | Release 01.00.02 | IRR | IA | 1 | N/A | D | 2020-02-03 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | DV-UT | 1 | N/A | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000002 | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000003 | A-FP | 2020-02-03
Philip | Release 01.06.00 | ASC | DV-UT | 1 | N/A | A-FP | 2020-02-04
Philip | Release 01.06.00 | ASC | IDP/IIVP | 1 | N/A | D | 2020-02-04 | Inaccurate information | Backup plan not correctly specified
Philip | Release 01.00.02 | IRR | CII | 1 | N/A | D | 2020-02-04 | Inaccurate information | Build information incorrect
Philip | Release 01.00.02 | IRR | CII | 1 | N/A | A | 2020-02-04
Philip | Release 01.00.02 | IRR | IA | 1 | N/A | A | 2020-02-04
Philip | Release 01.00.02 | IRR | SPR | 1 | A1900123 | A-FP | 2020-02-04
Philip | Release 01.00.02 | IRR | SPVP | 1 | N/A | A | 2020-02-04
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000004 | A-FP | 2020-02-05
Harald | Release 3.1 | MFCS | MP | 1 | N/A | D | 2020-02-06 | Inaccurate information
Philip | Release 3.1 | MFCS | TP | 2 | N/A | D | 2020-02-06 | Multiple Errors | Revision history incorrect, information missing, steps incorrect
Philip | Release 3.1 | MFCS | TP | 2 | N/A | D | 2020-02-06 | Inaccurate information | Revision history incomplete
Philip | Release 3.1 | MFCS | TP | 2 | N/A | A | 2020-02-06
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | D | 2020-02-06 | Inaccurate information | Revision history incomplete
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | A | 2020-02-06
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | D | 2020-02-06 | Multiple Errors | Build information incorrect, config file missing, form changes incorrect
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | D | 2020-02-06 | Inaccurate information | Build information incorrect
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | A | 2020-02-06
Philip | Release v33.28.0 | SFP | IDP/IIVP | 1 | N/A | A-FP | 2020-02-06
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect, changes incorrect
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect, changes incorrect
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | A | 2020-02-06
Philip | Release 01.05.00 | LIC | IDP/IIVP | 1 | N/A | A-FP | 2020-02-10
Harald | Release 02.21.01 | ADOC | CII | 1 | N/A | A-FP | 2020-02-12
Harald | Release 01.05.00 | LIC | CII | 1 | N/A | A-FP | 2020-02-12
Harald | Release 01.05.00 | LIC | IVR | 1 | N/A | D | 2020-02-12 | Inaccurate information | Software Version (replaced/installed) incorrect
Harald | Release 01.05.00 | LIC | IVR | 1 | N/A | A | 2020-02-12
Harald | Release 02.21.01 | ADOC | TPR | 1 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | IA | 2 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | TPR | 1 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | IA | 2 | N/A | A-FP | 2020-02-14
Harald | Release 01.05.00 | LIC | IDP/IIVP | 2 | N/A | A-FP | 2020-02-14
Harald | Release 01.05.00 | LIC | SCS/RN | 1 | N/A | A-FP | 2020-02-14
Harald | Release 33.28.0 | SFP | IVR | 1 | N/A | A-FP | 2020-02-14
Harald | Release 33.28.0 | SFP | TPR | 3 | N/A | D | 2020-02-14 | Inaccurate information | Date typo
Harald | Release 33.28.0 | SFP | TPR | 3 | N/A | A | 2020-02-14
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | D | 2020-02-18 | Multiple Errors | Approvers incorrect, tailoring incomplete
Harald | Release 01.05.00 | LIC | IVR | 2 | N/A | A-FP | 2020-02-18
Harald | Release 3.1 | MFCS | TP | 3 | N/A | D | 2020-02-18 | Multiple Errors | Revision history incorrect, inaccurate information
Harald | Release 3.1 | MFCS | TPR | 2 | N/A | D | 2020-02-18 | Multiple Errors | missing entry
Harald | Release 3.1 | MFCS | TP | 3 | N/A | A | 2020-02-19
Harald | Release 3.1 | MFCS | TPR | 2 | N/A | A | 2020-02-19
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | D | 2020-02-20 | Multiple Errors | Documentation impact analysis incomplete, SPR reference incorrect, tailoring incorrect
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | A | 2020-02-20
Philip | Release 01.09.03 | ITS | SPVP | 1 | N/A | D | 2020-02-20 | Multiple Errors | Approvers incorrect, roles incomplete/incorrect, e-record/e-signature section incorrect
Philip | Release 01.09.03 | ITS | SPVP | 1 | N/A | A | 2020-02-20
Philip | Release 01.09.03 | ITS | URS/FRS/TM | 16 | N/A | D | 2020-02-20 | Inaccurate information | Approvers incorrect
Philip | Release 01.09.03 | ITS | URS/FRS/TM | 16 | N/A | A | 2020-02-20
Harald | Release 3.1 | MFCS | CII | 2 | N/A | A-FP | 2020-02-20
Philip | Release v33.28.0 | SFP | IVR | 1 | Prod | D | 2020-02-20 | Inaccurate information | Verifier entries incorrect
Philip | Release v33.28.0 | SFP | IVR | 1 | Prod | A | 2020-02-20
Harald | Release 3.1 | MFCS | MP | 1 | N/A | A | 2020-02-21
Philip | Release 01.09.03 | ITS | DV-UT | 1 | N/A | A-FP | 2020-02-24
Philip | Release 01.09.03 | ITS | IDP/IIVP | 1 | N/A | D | 2020-02-24 | Inaccurate information | Approver incorrect
Philip | Release 01.09.03 | ITS | IDP/IIVP | 1 | N/A | A | 2020-02-24
Philip | Release 7.1 | Unicorn | CII | 3 | N/A | D | 2020-02-24 | Inaccurate information | Revision history incomplete
Philip | Release 7.1 | Unicorn | CII | 3 | N/A | A | 2020-02-24
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-02-25
Philip | Release 01.09.03 | ITS | CII | 17 | N/A | D | 2020-02-26 | Inaccurate information | Revision history incomplete
Philip | Release 01.09.03 | ITS | CII | 17 | N/A | A | 2020-02-26
Philip | Release 01.09.03 | ITS | IA | 2 | N/A | A-FP | 2020-02-26
Philip | Release 01.09.03 | ITS | IVR | 1 | GER400 | A-FP | 2020-02-26
Philip | Release 01.09.03 | ITS | SCS/RN | 1 | N/A | D | 2020-02-26 | Inaccurate information | Approvers incorrect
Philip | Release 01.09.03 | ITS | SCS/RN | 1 | N/A | A | 2020-02-26
Philip | Release 01.09.03 | ITS | TPR | 1 | TP09 | A-FP | 2020-02-26
Harald | Release 3.1 | MFCS | SCR | 1 | M1900012 | A-FP | 2020-02-27
Harald | Release 3.1 | MFCS | SCS/RN | 1 | N/A | A-FP | 2020-02-27
Philip | Release 01.09.03 | ITS | IVR | 1 | GER42 | A-FP | 2020-02-28
Philip | Release 01.05.01 | LIC | SPVP | 1 | AQC VERA | D | 2020-02-28 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-02 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.05.01 | LIC | IDP | 1 | AQC VERA | D | 2020-03-04 | Incorrect scope | Offline review.
Philip | Release 01.05.01 | LIC | ESRA | 1 | AQC VERA | D | 2020-03-05 | Inaccurate information | Offline review. AQC090504.A Attachment C no longer exists.
Harald | Release 01.78.00 | LSP | IA | 2 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | TP | 1 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | URS/FRS/TM | 40 | ZARA | A-FP | 2020-03-10
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-11 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Harald | Release 01.78.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-03-11
Philip | Release 01.05.01 | LIC | MP | 1 | AQC VERA | D | 2020-03-12 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Philip | Release 01.05.01 | LIC | RA | 1 | AQC VERA | D | 2020-03-12 | Multiple Errors | Offline review. Failure modes and causes need to be corrected.
Harald | Release 01.78.00 | LSP | CII | 1 | N/A | A-FP | 2020-03-12
Harald | Release 01.78.00 | LSP | SCS/RN | 1 | N/A | A-FP | 2020-03-12
Harald | Release 01.78.00 | LSP | TPR | 1 | N/A | A-FP | 2020-03-12
Philip | Release 01.05.01 | LIC | RA | 1 | AQC VERA | D | 2020-03-13 | Multiple Errors | Offline review. Mitigations need to be mapped to requirements.
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-13 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Harald | Release 01.78.00 | LSP | IVR | 1 | GER42 | A-FP | 2020-03-16
Harald | Release 01.78.00 | LSP | SCR | 1 | L1900290 | A-FP | 2020-03-16
Philip | Release 01.05.01 | LIC | TM-URS to FRS | 1 | AQC VERA | D | 2020-03-17 | Multiple Errors | Offline review. Tracing needs rework.
Philip | Release 01.05.01 | LIC | TM-URS/FRS to TP | 1 | AQC VERA | D | 2020-03-17 | Multiple Errors | Offline review. Tracing needs rework.
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-03-18 | Inaccurate information | Wrong SCR
Philip | Release 01.06.00 | ASC | IDP/IIVP | 1 | N/A | A | 2020-03-19
Harald | Release 01.79.00 | LSP | DV-UT | 1 | N/A | A-FP | 2020-03-19
Harald | Release 01.79.00 | LSP | IA | 2 | N/A | D | 2020-03-19 | Inaccurate information | Wrong SCR
Harald | Release 01.79.00 | LSP | IA | 3 | N/A | D | 2020-03-19 | Inaccurate information | Wrong libraries
Harald | Release 01.79.00 | LSP | IA | 4 | N/A | D | 2020-03-19 | Inaccurate information | Missing entry
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-03-19 | Other | SPR L1900281 added
Harald | Release 01.79.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-03-19
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Base) | D | 2020-03-23 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.06.00 | ASC | CII | 11 | N/A | D | 2020-03-23 | Multiple Errors | Object list incomplete and incorrect. Requires Impact Anaylsis update.
Philip | Release 01.06.00 | ASC | IVR | 1 | GER400 | D | 2020-03-23 |  | Incorrect document used.
Philip | Release 01.06.00 | ASC | IVR | 1 | GER400 | A | 2020-03-23
Harald | Release 01.79.00 | LSP | TP | 1 | N/A | D | 2020-03-23 | Multiple Errors | Missing, wrong references to URS.
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Outgoing) | D | 2020-03-24 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Harald | Release 01.79.00 | LSP | IA | 5 | N/A | A | 2020-03-24
Harald | Release 01.79.00 | LSP | TP | 2 | N/A | A | 2020-03-24
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 14 | REA | A-FP | 2020-03-24
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 26 | GIM | D | 2020-03-24 | Multiple Errors | Missing, wrong references to TP.
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 26 | GIM | A | 2020-03-24
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (WebApp) | D | 2020-03-25 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Pricing) | D | 2020-03-25 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.06.00 | ASC | CII | 11 | N/A | A | 2020-03-25
Philip | Release 01.06.00 | ASC | IA | 2 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | CII | 1 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | IDP/IIVP | 2 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | SCS/RN | 1 | N/A | A-FP | 2020-03-26
Harald | Release 01.79.00 | LSP | TPR | 1 | N/A | A-FP | 2020-03-26
Philip | Release 01.06.00 | ASC | IVR | 1 | GER42 | A-FP | 2020-03-27
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | D | 2020-03-27 | Inaccurate information | BIA section incorrect
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | A | 2020-03-27
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | D | 2020-03-27 | Inaccurate information | Data review section incorrect, BIA section incorrect
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | A | 2020-03-27
Philip | Release 01.06.00 | ASC | TPR | 1 | TP03 | D | 2020-03-27 | Multiple Errors | Copy-paste errors in comments of unexecuted steps.
Philip | Release 01.06.00 | ASC | TPR | 1 | TP03 | A | 2020-03-27
Philip | Release 02.22.00 | ADOC | SCR | 1 | A2000031 | A-FP | 2020-03-30
Philip | Release 02.22.00 | ADOC | SPVP | 1 | N/A | D | 2020-03-30 | Inaccurate information | Approver and project roles incorrectly defined
Harald | Release 01.79.00 | LSP | IVR | 1 | GER42 | D | 2020-03-30 | Inaccurate information | Coment missing
Harald | Release 01.79.00 | LSP | IVR | 1 | GER42 | A | 2020-03-30
Harald | Release 01.79.00 | LSP | SCR | 1 | L1900194 | A-FP | 2020-03-30
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | D | 2020-03-30 | Multiple Errors | Tracing is incomplete
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | D | 2020-03-30 | Multiple Errors | Tracing is incomplete
Philip | Release 02.22.00 | ADOC | IA | 1 | N/A | D | 2020-03-31 | Multiple Errors | Deliverables tailoring justifications insufficient, documentation impact section incorrect
Philip | Release 02.22.00 | ADOC | SPVP | 1 | N/A | A | 2020-03-31
Philip | Release 02.22.00 | ADOC | TP | 1 | TP69 | D | 2020-03-31 | Inaccurate information | Test steps incomplete
Philip | Release 02.22.00 | ADOC | URS/FRS/TM | 26 | Outgoing | D | 2020-03-31 | Inaccurate information | Traceability information incomplete
Philip | Release 02.22.00 | ADOC | DV-UT | 1 | Outgoing | D | 2020-04-01 | Inaccurate information | Unit definitions missing
Philip | Release 02.22.00 | ADOC | DV-UT | 1 | Outgoing | A | 2020-04-01
Philip | Release 02.22.00 | ADOC | IDP/IIVP | 1 | N/A | A-FP | 2020-04-01
Philip | Release 02.22.00 | ADOC | TP | 1 | TP69 | A | 2020-04-01
Philip | Release 02.22.00 | ADOC | CII | 1 | N/A | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | IVR | 1 | GER400 | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | IVR | 1 | GER42 | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | SCS/RN | 1 | N/A | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | TPR | 1 | TP69 | A-FP | 2020-04-02
Philip | Release 13.2 | Fabiola | SCA | 1 | N/A | D | 2020-04-06 | Not following document version control | Not all changes described, or not based on approved version
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-04-07 | Multiple Errors | URS structure not correct for AQC VERA, contents partially incorrect or missing
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-04-08 | Multiple Errors | Roles & responsibilities incomplete, strategy inadequate
Philip | Release 13.2 | Fabiola | SCR | 1 | M2000007 | D | 2020-04-14 | Inaccurate information | Description unacceptable
Philip | Release 13.2 | Fabiola | SCR | 1 | M2000008 | D | 2020-04-14 | Inaccurate information | Replacement SCR for M2000008, description draft needs rework
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Incoming) | D | 2020-04-15 | Multiple Errors | Offline review. Structure not correct, several content errors
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Outgoing) | D | 2020-04-16 | Inaccurate information | Offline review. Corrections based on urgent COVID-19 release
Philip | Release 01.05.01 | LIC | SCA | 1 | N/A | A | 2020-04-16
Philip | Release 01.05.01 | LIC | SPVP | 1 | N/A | D | 2020-04-17 | Multiple Errors | Formatting issues, timeline correction
Philip | Release 01.05.01 | LIC | ESRA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | IA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | IDP | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | MP | 1 | N/A | D | 2020-04-20 | Multiple Errors | Formatting issues, content adaptation
Philip | Release 01.05.01 | LIC | MP | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | RA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | SPVP | 1 | N/A | A | 2020-04-20
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900186 | D | 2020-04-20 | Other | Source Code Names missing
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-04-20 | Inaccurate information | Requirements missing
Harald | Release 01.80.00 | LSP | IDP/IIVP | 1 | N/A | D | 2020-04-20 | Inaccurate information | Empty fields
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | D | 2020-04-20 | Multiple Errors | Tracing is incomplete
Harald | Release 01.80.00 | LSP | TP | 1 | L1900281 | D | 2020-04-20 | Inaccurate information | Expected result unclear
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | D | 2020-04-20 | Multiple Errors | Tracing is incomplete, requirement missing, risk description missing
Philip | Release 01.05.01 | LIC | DV-UT | 1 | N/A | A-FP | 2020-04-21
Philip | Release 01.05.01 | LIC | IIVP | 1 | N/A | A | 2020-04-21
Philip | Release 01.05.01 | LIC | TP | 1 | Legacy Tracing | A | 2020-04-21
Philip | Release 01.05.01 | LIC | TP | 1 | N/A | A | 2020-04-21
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900186 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900281 | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-04-21 | Inaccurate information | Time scedule inaccurate
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | IDP/IIVP | 1 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | SPR | 1 | L1900281 | D | 2020-04-21 | Inaccurate information | Investigation results unclear
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | TP | 1 | L1900281 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | A | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 48 | PAD | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 23 | SYM | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 16 | COR | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 3 | CDL | A-FP | 2020-04-21
Philip | Release 01.05.01 | LIC | CII | 1 | N/A | D | 2020-04-22 | Multiple Errors | Adaptations to new AS/400
Philip | Release 01.05.01 | LIC | CII | 1 | N/A | A | 2020-04-22
Philip | Release 01.05.01 | LIC | IVR | 1 | GER400 | A-FP | 2020-04-22
Harald | Release 01.80.00 | LSP | CII | 1 | N/A | A-FP | 2020-04-22
Harald | Release 01.80.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-04-22
Philip | Release 01.05.01 | LIC | SCS/RN | 1 | N/A | A | 2020-04-23
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | TM-URS/FRS to TP | 1 | N/A | A | 2020-04-23
Philip | Release 01.05.01 | LIC | TPR | 1 | Legacy Tracing | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | TPR | 1 | N/A | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | IVR | 1 | GER42 | A-FP | 2020-04-24
Harald | Release 01.80.00 | LSP | SCS/RN | 1 | N/A | D | 2020-04-24 | Inaccurate information | SPR reference is missing
Harald | Release 01.80.00 | LSP | SCS/RN | 1 | N/A | A | 2020-04-24
Harald | Release 01.80.00 | LSP | TPR | 1 | L1900186 | A-FP | 2020-04-24
Harald | Release 01.80.00 | LSP | TPR | 1 | L1900281 | A-FP | 2020-04-24
Philip | Release 01.05.01 | LIC | SCS/RN | 2 | N/A | A | 2020-04-28
Harald | Release 01.80.00 | LSP | IVR | 1 | GER42 | A-FP | 2020-04-29
Harald | Release 01.80.00 | LSP | SCR | 1 | L1900186 | A-FP | 2020-04-29
Harald | Release 01.80.00 | LSP | SPR | 1 | L1900281 | A | 2020-04-29
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-04-30
Philip | Release 13.2 | Fabiola | IA | 1 | N/A | D | 2020-05-04 | Multiple Errors | Tailoring table incomplete, system impact incorrect
Philip | Release 13.2 | Fabiola | IDP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Incorrect system name, outlined process inadequate
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Several sections are incorrect (not taking COTS nature into account)
Philip | Release 13.2 | Fabiola | SCA | 1 | N/A | D | 2020-05-04 | Multiple Errors | Changes incompletely implemented
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Incorrect systemname, references incorrect, strategy inadequate
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-04 | Multiple Errors | Tracing/references incorrect
Harald | Release 01.81.00 | LSP | IA | 1a | N/A | D | 2020-05-04 | Inaccurate information
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-05 | Multiple Errors | Tracing/references still incorrect
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-06 | Multiple Errors | Tracing/references still incorrect
Philip | Release 13.2 | Fabiola | IA | 1 | N/A | D | 2020-05-12 | Multiple Errors | Tailoring table still incomplete, system impact still incorrect
Philip | Release 13.2 | Fabiola | IDP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Outlined process still needs rework (because of COTS nature)
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Several sections are incorrect (not taking COTS nature into account)
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Formal errors, strategy discussion ongoing, DP aspects not final
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-12 | Multiple Errors | Tracing/references still incorrect, risk classifications inconsistent
Harald | Release 01.81.00 | LSP | IA | 1b | N/A | D | 2020-05-12 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-05-15 | Multiple Errors | Requirement specifications need rework
Harald | Release 01.81.00 | LSP | DV-UT | 1 | L2000059 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | DV-UT | 1 | L2000076 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | IA | 1 | N/A | A | 2020-05-15
Harald | Release 01.81.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | TP | 1 | L2000059 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | TP | 1 | L2000076 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 16 | BOML | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 44 | LAG | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 27 | GIM | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 15 | REA | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | CII | 1 | N/A | A-FP | 2020-05-18
Harald | Release 01.81.00 | LSP | IDP/IIVP | 2 | N/A | A-FP | 2020-05-18
Harald | Release 01.81.00 | LSP | SCS/RN | 1a | N/A | D | 2020-05-18 | Inaccurate information
Harald | Release 01.81.00 | LSP | SCS/RN | 1 | N/A | A | 2020-05-19
Harald | Release 01.81.00 | LSP | SPVP | 6a | Generic | D | 2020-05-19 | Inaccurate information
Harald | Release 01.81.00 | LSP | TPR | 1a | L2000059 | D | 2020-05-19 | Inaccurate information
Harald | Release 01.81.00 | LSP | TPR | 1 | L2000059 | A | 2020-05-19
Harald | Release 01.81.00 | LSP | TPR | 1 | L2000076 | A-FP | 2020-05-19
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-20 | Multiple Errors | Tracing/references still incorrect
Harald | Release 01.81.00 | LSP | SPVP | 6 | Generic | A | 2020-05-20
Harald | Release 01.81.00 | LSP | IVR | 2 | GER42 | A-FP | 2020-05-27
Harald | Release 01.81.00 | LSP | SCR | 1 | L2000059 | A-FP | 2020-05-27
Harald | Release 01.81.00 | LSP | SPR | 1 | L2000076 | A-FP | 2020-05-27
Philip | Release 13.2 | Fabiola | SE | 1 | N/A | D | 2020-05-28 | Multiple Errors | Content and result do not match, several process and logical errors
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-05-29 | Multiple Errors | Item type selections partially incorrect, contents still need some rework
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-12 | Multiple Errors | Several RS include content errors or are missing completely
Harald | Release 01.82.00 | LSP | IA | 1a | N/A | D | 2020-06-15 | Other | Release content change
Harald | Release 01.82.00 | LSP | TP | 1 | L2000073 | A-FP | 2020-06-15
Harald | Release 01.82.00 | LSP | TP | 1 | L2000112 | A-FP | 2020-06-15
Harald | Release 01.82.00 | LSP | TP | 1 | L2000066 | A-FP | 2020-06-15
Harald | Release 01.82.00 | LSP | URS/FRS/TM | 49 | PAD | A-FP | 2020-06-15
Harald | Release 01.82.00 | LSP | URS/FRS/TM | 45 | LAG | A-FP | 2020-06-15
Harald | Release 01.82.00 | LSP | URS/FRS/TM | 30 | DAC | A-FP | 2020-06-15
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-17 | Multiple Errors | Some RS have been created as Groups, risk classifications need to be changed and tracing is missing entirely
Harald | Release 01.82.00 | LSP | CII | 1 | N/A | A-FP | 2020-06-18
Harald | Release 01.82.00 | LSP | CII | 2 | N/A | A-FP | 2020-06-18
Harald | Release 01.82.00 | LSP | SCS/RN | 1a | N/A | D | 2020-06-18 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-19 | Multiple Errors | Tracing is still partially missing, one risk classification is missing
Harald | Release 01.82.00 | LSP | SCS/RN | 1 | N/A | A | 2020-06-19
Harald | Release 01.82.00 | LSP | TPR | 1 | L2000073 | A-FP | 2020-06-19 | Inaccurate information
Harald | Release 01.82.00 | LSP | TPR | 1 | L2000112 | A-FP | 2020-06-19
Harald | Release 01.82.00 | LSP | TPR | 1 | L2000117 | A-FP | 2020-06-19
Harald | Release 01.82.00 | LSP | TPR | 1a | L2000066 | D | 2020-06-19 | Inadequate Description of Change
Harald | Release 01.82.00 | LSP | TPR | 1b | L2000066 | A-FP | 2020-06-19
Harald | Release 01.82.00 | LSP | IA | 1b | N/A | A | 2020-06-20 | Other
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-23 | Multiple Errors | Additional changes required, contents incorrect, tracing is still partially missing
Harald | Release 01.82.00 | LSP | DV-UT | 1 | L2000066 | A-FP | 2020-06-23
Harald | Release 01.82.00 | LSP | DV-UT | 1 | L2000112 | A-FP | 2020-06-23
Harald | Release 01.82.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-06-23 | Other
Harald | Release 01.82.00 | LSP | IA | 2 | N/A | A-FP | 2020-06-24
Harald | Release 01.82.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-06-24
Harald | Release 01.82.00 | LSP | DV-UT | 1 | L2000117 | A-FP | 2020-06-25
Harald | Release 01.82.00 | LSP | IA | 3 | N/A | A-FP | 2020-06-25
Harald | Release 01.82.00 | LSP | IDP/IIVP | 2 | N/A | A-FP | 2020-06-25
Harald | Release 01.82.00 | LSP | IVR | 2 | GER400 | A-FP | 2020-06-25
Harald | Release 01.82.00 | LSP | SCR | 1 | L2000073 | A-FP | 2020-06-27
Harald | Release 01.82.00 | LSP | SCR | 1 | L2000066 | A-FP | 2020-06-27
Harald | Release 01.82.00 | LSP | SPR | 1 | L2000112 | A-FP | 2020-06-27
Harald | Release 01.82.00 | LSP | SPR | 1 | L2000117 | A-FP | 2020-06-27
Harald | Release 01.82.00 | LSP | IVR | 2 | GER42 | A-FP | 2020-06-29
Harald | Release 01.83.00 | LSP | DV-UT | 1a | L2000060 | D | 2020-07-03 | Insufficient testing
Harald | Release 01.83.00 | LSP | DV-UT | 1b | L2000060 | A | 2020-07-03
Harald | Release 01.83.00 | LSP | IA | 1a | N/A | D | 2020-07-03 | Other | Release content change
Harald | Release 01.83.00 | LSP | IA | 1b | N/A | D | 2020-07-03 | Inaccurate information
Harald | Release 01.83.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-07-03
Harald | Release 01.83.00 | LSP | TP | 1 | L2000060 | A-FP | 2020-07-03
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 16 | ALC | A-FP | 2020-07-03
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 17 | BOML | A-FP | 2020-07-03
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 16 | REA | A-FP | 2020-07-03
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 24 | SYM | A-FP | 2020-07-03
Philip | Release 01.11.01 | CMSN-Add-On | SPVP | 1 | N/A | D | 2020-07-09 | Multiple Errors | Several incorrect references
Philip | Release 1.1 | FIIS | CII | 6 | N/A | D | 2020-07-09 | Multiple Errors | Several version information mismatches
Philip | Release 9.7 | WWLIMS | IVR | 1 | 398 | A-FP | 2020-07-09
Philip | Release 9.7 | WWLIMS | IVR | 1 | 399 | A-FP | 2020-07-09
Philip | Release 1.1 | FIIS | MCP | 1 | N/A | D | 2020-07-13 | Incorrect Approvers | BPO & TR missing
Philip | Release 9.7 | WWLIMS | IVR | 1 | 400 | A-FP | 2020-07-16
Philip | Release 1.1 | FIIS | CII | 6 | N/A | A | 2020-07-17
Philip | Release 1.1 | FIIS | MCP | 1 | N/A | A | 2020-07-17
Philip | Release 9.7 | WWLIMS | IVR | 1 | 402 | A-FP | 2020-07-20
Philip | Release 9.7 | WWLIMS | IVR | 1 | 403 | A-FP | 2020-07-20
Philip | Release 9.7 | WWLIMS | IVR | 1 | 401 | A-FP | 2020-07-20
Philip | Release 01.11.01 | CMSN-Add-On | DV-UT | 1 | N/A | D | 2020-07-21 | Other | Req Coverage missing
Philip | Release 01.11.01 | CMSN-Add-On | MP | 1 | N/A | D | 2020-07-21 | Inaccurate information | AIR is no longer used, transition to SCR/ACR/IPDR in AQC VERA has concluded
Philip | Release 1.1 | FIIS | IVR | 1 | N/A | D | 2020-07-21 | Incorrect Objective Evidence
Philip | Release 1.1 | FIIS | MCPR | 1 | N/A | D | 2020-07-21 | Not using template | Incorrect document used.
Philip | Release 1.1 | FIIS | MCPR | 1 | N/A | A | 2020-07-21
Philip | Release 01.11.01 | CMSN-Add-On | MP | 1 | N/A | D | 2020-07-23 | Inaccurate information | Contains several references to AIR and descriptions of the workflows
Harald | Release 01.83.00 | LSP | TP | 2a | L2000060 | D | 2020-07-24 | Insufficient testing
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 17a | REA | D | 2020-07-25 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | TM-URS/FRS to TP | 1 | N/A | D | 2020-07-27 | Multiple Errors | Several trace links missing or incorrect
Harald | Release 01.83.00 | LSP | IDP/IIVP | 2a | N/A | D | 2020-07-27 | Other | Additional code
Philip | Release 01.11.01 | CMSN-Add-On | ESRA | 1 | N/A | D | 2020-07-28 | Other | Rich text filled with redundant information
Philip | Release 01.11.01 | CMSN-Add-On | IA | 1 | N/A | D | 2020-07-28 | Multiple Errors | Incorrrect SPR references, tailoring incorrect, contains reference to eRIM, replace with DLM
Philip | Release 01.11.01 | CMSN-Add-On | IIVP | 1 | N/A | D | 2020-07-28 | Other | One empty step needs to be deleted
Philip | Release 01.11.01 | CMSN-Add-On | TM-URS/FRS to TP | 1 | N/A | D | 2020-07-28 | Multiple Errors | Several trace links missing or incorrect
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-07-28 | Inaccurate information | Contains reference to eRIM, replace with DLM
Harald | Release 01.83.00 | LSP | IA | 2a | N/A | D | 2020-07-28 | Inaccurate information
Harald | Release 01.83.00 | LSP | DV-UT | 2 | L2000060 | A-FP | 2020-07-29
Harald | Release 01.83.00 | LSP | IA | 2b | N/A | A | 2020-07-29
Harald | Release 01.83.00 | LSP | IDP/IIVP | 2b | N/A | A | 2020-07-29
Harald | Release 01.83.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-07-29
Harald | Release 01.83.00 | LSP | TP | 2b | L2000060 | A | 2020-07-29
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 17b | REA | A | 2020-07-29
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 25 | SYM | A-FP | 2020-07-29
Philip | Release 01.11.01 | CMSN-Add-On | SCA | 1 | N/A | A | 2020-07-30
Harald | Release 01.83.00 | LSP | CII | 1 | N/A | A-FP | 2020-07-30
Philip | Release 01.11.01 | CMSN-Add-On | IA | 1 | N/A | A | 2020-07-31
Philip | Release 01.11.01 | CMSN-Add-On | SPVP | 1 | N/A | A | 2020-07-31
Harald | Release 01.83.00 | LSP | SCS/RN | 1 | N/A | A-FP | 2020-07-31
Harald | Release 01.83.00 | LSP | TPR | 1 | N/A | A-FP | 2020-07-31
Harald | Release 7.1 | Unicorn | TP | 1 | N/A | A-FP | 2020-08-03
Harald | Release 7.1 | Unicorn | URS | 1 | N/A | D | 2020-08-03 | Inaccurate information
Harald | Release 7.1 | Unicorn | SCA | 1 | N/A | A-FP | 2020-08-04
Philip | Release v6.50 | ImageCompare | ESRA | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | IA | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | IDP | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | IIVP | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | MCP | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | SPVP | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | TM-URS to TP | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Philip | Release v6.50 | ImageCompare | URS | 1 | N/A | D | 2020-08-05 | Multiple Errors | Incorrect templates, incorrect references (Q09.14!), nonsensical contents, tracing missing... This is not even a draft
Harald | Release 6.87 | LabSolutions | SCA | 1 | N/A | A-FP | 2020-08-11
Harald | Release 01.83.00 | LSP | IVR | 1 | GER42 | A-FP | 2020-08-12
Harald | Release 01.83.00 | LSP | SCR | 1 | L2000060 | A-FP | 2020-08-12
Harald | Release 3.1 | MFCS | SCA | 1 | N/A | A-FP | 2020-08-12
Harald | Release 7.1 | Unicorn | URS | 1 | N/A | A | 2020-08-12
Philip | Release 01.06.02 | SPOC | URS/FRS | 1 | N/A | D | 2020-08-18 | Multiple Errors | Several RS names incorrect, tracing partially missing
Harald | Release 7.1 | Unicorn | IIVP | 1 | N/A | D | 2020-08-18 | Inaccurate information
Philip | Release 01.06.02 | SPOC | IA | 1 | N/A | D | 2020-08-19 | Multiple Errors | Deliverables table/tailoring incorrect
Philip | Release 01.06.02 | SPOC | IA | 1 | N/A | D | 2020-08-19 | Inaccurate information | Tailoring incorrect/incomplete
Philip | Release 01.06.02 | SPOC | SCA | 1 | N/A | D | 2020-08-19 | Inaccurate information | Regulations incorrectly selected
Philip | Release 01.06.02 | SPOC | SPVP | 1 | N/A | D | 2020-08-19 | Inaccurate information | TP strategy incorrect
Philip | Release 01.11.01 | CMSN-Add-On | ESRA | 1 | N/A | A | 2020-08-20
Philip | Release 01.11.01 | CMSN-Add-On | IDP | 1 | N/A | A-FP | 2020-08-20
Philip | Release 01.11.01 | CMSN-Add-On | MP | 1 | N/A | A | 2020-08-20
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | A | 2020-08-20
Philip | Release 01.06.02 | SPOC | IA | 1 | N/A | A | 2020-08-20
Philip | Release 01.06.02 | SPOC | SCA | 1 | N/A | A | 2020-08-20
Harald | Release 7.1 | Unicorn | IDP | 1 | N/A | D | 2020-08-20 | Inaccurate information
Harald | Release 7.1 | Unicorn | MP | 1 | N/A | D | 2020-08-21 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | SPVP | 2 | N/A | A-FP | 2020-08-24
Harald | Release 3.1 | MFCS | IDP | 1 | N/A | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | IIVP | 1 | N/A | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | MP | 1 | N/A | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | RA | 1 | N/A | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | SPVP | 1 | N/A | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | TC1.1 | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | TC2.1 | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | TC3.1 | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | TC4.1 | D | 2020-08-24 | Inaccurate information
Harald | Release 3.1 | MFCS | URS | 1 | N/A | D | 2020-08-24 | Inaccurate information
Philip | Release 01.06.02 | SPOC | DV-UT | 1 | N/A | A-FP | 2020-08-24
Philip | Release 01.06.02 | SPOC | DV-UT | 1 | N/A | A-FP | 2020-08-24 |  | Executed
Philip | Release 01.06.02 | SPOC | IDP | 1 | N/A | A-FP | 2020-08-24
Philip | Release 01.06.02 | SPOC | MP | 1 | N/A | A-FP | 2020-08-24
Philip | Release 01.06.02 | SPOC | SPVP | 1 | N/A | A | 2020-08-24
Philip | Release 01.06.02 | SPOC | URS/FRS | 1 | N/A | A | 2020-08-24
Harald | Release 7.1 | Unicorn | IDP | 1 | N/A | A | 2020-08-24
Philip | Release 01.06.02 | SPOC | CII | 1 | N/A | A-FP | 2020-08-25
Philip | Release 01.06.02 | SPOC | ESRA | 1 | N/A | A-FP | 2020-08-25
Philip | Release 01.06.02 | SPOC | IVR | 1 | N/A | A-FP | 2020-08-25 |  | GER400
Harald | Release 3.1 | MFCS | ESRA | 1 | N/A | A-FP | 2020-08-26
Harald | Release 3.1 | MFCS | IDP | 1 | N/A | A | 2020-08-26
Harald | Release 3.1 | MFCS | MP | 1 | N/A | A | 2020-08-26
Harald | Release 3.1 | MFCS | SPVP | 1 | N/A | A | 2020-08-26
Harald | Release 3.1 | MFCS | URS | 1 | N/A | A | 2020-08-26
Philip | Release 01.06.02 | SPOC | SCS/RN | 1 | N/A | D | 2020-08-26 | Inaccurate information | Copy-Paste errors (containing content only relevant for LIC)
Philip | Release 01.06.02 | SPOC | TM-URS/FRS to TP | 1 | N/A | A-FP | 2020-08-26
Philip | Release 01.06.02 | SPOC | TPR | 1 | N/A | A-FP | 2020-08-26 |  | Legacy Tracing
Philip | Release 01.06.02 | SPOC | TPR | 1 | N/A | A-FP | 2020-08-26
Harald | Release 7.1 | Unicorn | IIVP | 1 | N/A | A | 2020-08-26
Harald | Release 7.1 | Unicorn | MP | 1 | N/A | A | 2020-08-26
Harald | Release 7.1 | Unicorn | RA | 1 | N/A | D | 2020-08-26 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | DV-UT | 1 | N/A | A-FP | 2020-08-27
Philip | Release 01.11.01 | CMSN-Add-On | TP | 1 | TP 15.7a | A-FP | 2020-08-27
Philip | Release 01.11.01 | CMSN-Add-On | TP | 1 | TP 30.9 | A-FP | 2020-08-27
Philip | Release 01.11.01 | CMSN-Add-On | TP | 1 | N/A | A-FP | 2020-08-27 |  | Legacy Tracing
Harald | Release 3.1 | MFCS | IIVP | 1 | Workstation | A | 2020-08-27
Philip | Release 01.06.02 | SPOC | SCS/RN | 1 | N/A | A | 2020-08-27
Philip | Release 01.11.01 | CMSN-Add-On | DV-UT | 1 | N/A | A-FP | 2020-08-28 |  | Executed
Philip | Release 01.11.01 | CMSN-Add-On | IIVP | 1 | N/A | A-FP | 2020-08-28
Harald | Release 3.1 | MFCS | RA | 1 | N/A | A | 2020-08-28
Harald | Release 3.1 | MFCS | SCR | 1 | N/A | A-FP | 2020-08-28
Harald | Release 3.1 | MFCS | TP | 1 | TC1.1 | A | 2020-08-28
Harald | Release 3.1 | MFCS | TP | 1 | TC4.3 | A-FP | 2020-08-28
Harald | Release 3.1 | MFCS | TP | 1 | TC5.1 | A-FP | 2020-08-28
Harald | Release 3.1 | MFCS | TP | 1 | TC5.2 | A-FP | 2020-08-28
Philip | Release 01.06.02 | SPOC | IVR | 1 | N/A | A-FP | 2020-08-28 |  | GER42
Harald | Release 7.1 | Unicorn | ESRA | 1 | N/A | A-FP | 2020-08-28
Philip | Release 01.11.01 | CMSN-Add-On | CII | 1 | N/A | A-FP | 2020-08-31
Philip | Release 01.11.01 | CMSN-Add-On | IVR | 1 | N/A | A-FP | 2020-08-31 |  | GER400
Philip | Release 01.11.01 | CMSN-Add-On | TPR | 1 | TP 15.7a | A-FP | 2020-09-01
Philip | Release 01.11.01 | CMSN-Add-On | TPR | 1 | TP 30.9 | A-FP | 2020-09-01
Philip | Release 01.11.01 | CMSN-Add-On | TPR | 1 | N/A | A-FP | 2020-09-01 |  | Legacy Tracing
Philip | Release 01.11.01 | CMSN-Add-On | SCS/RN | 1 | N/A | A-FP | 2020-09-02
Harald | Release 6.87 | LabSolutions | SCR | 1 | N/A | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | IIVP | 1 | Server | A | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC3.1 | A | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC4.2 | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC2.3 | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC2.2 | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC2.1 | A | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC1.4 | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC1.3 | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | TP | 1 | TC4.1 | A | 2020-09-02
Harald | Release 7.1 | Unicorn | RA | 1 | N/A | A-FP | 2020-09-02
Harald | Release 3.1 | MFCS | IVR | 1 | Workstation | A-FP | 2020-09-03
Harald | Release 7.1 | Unicorn | IVR | 1 | N/A | A-FP | 2020-09-08
Philip | Release v6.50 | ImageCompare | IA | 1 | N/A | D | 2020-09-10 | Multiple Errors | Tailoring incorrect/incomplete, documentation impact incorrect, application impact not included
Philip | Release v6.50 | ImageCompare | IDP | 1 | N/A | D | 2020-09-10 | Multiple Errors | Partially incorrect contents, system name incorrect, no section numbers
Philip | Release v6.50 | ImageCompare | MCP | 1 | N/A | D | 2020-09-10 | Multiple Errors | Availiability of previous version incorrectly reflected
Philip | Release v6.50 | ImageCompare | SPVP | 1 | N/A | D | 2020-09-10 | Multiple Errors | SOP change not listed, NPV/AIR references still included
Philip | Release v6.50 | ImageCompare | TP | 1 | N/A | D | 2020-09-10 | Multiple Errors | Testing missing for several requirements
Philip | Release v6.50 | ImageCompare | URS | 1 | N/A | D | 2020-09-10 | Multiple Errors | Several E-Sig requirements missing, or incorrectly "N/A-ed"
Harald | Release 3.1 | MFCS | TPR | 1 | TC5.2 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TPR | 1 | TC3.2 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TPR | 1 | TC5.1 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TPR | 1 | TC3.1 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TPR | 1 | TC1.2 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TPR | 1 | TC1.1 | A-FP | 2020-09-11
Harald | Release 3.1 | MFCS | TM-URS to TP | 1 | N/A | A-FP | 2020-09-16
Philip | Release v6.50 | ImageCompare | IA | 1 | N/A | D | 2020-09-17 | Multiple Errors | Tailoring still partially incorrect, documentation impact partially incorrect
Philip | Release v6.50 | ImageCompare | IDP | 1 | N/A | D | 2020-09-17 | Multiple Errors | Partially incorrect contents, system name incorrect
Harald | Release 3.1 | MFCS | ESRA | 1 | N/A | A-FP | 2020-09-17
Harald | Release 7.1 | Unicorn | ESRA | 2 | N/A | A-FP | 2020-09-17
Harald | Release 7.1 | Unicorn | TM-URS to TP | 1 | N/A | A-FP | 2020-09-17
Harald | Release 3.1 | MFCS | IIVP | 2 | Workstation | A | 2020-09-18
Harald | Release 3.1 | MFCS | SCS/RN | 1 | N/A | A-FP | 2020-09-18
Harald | Release 3.1 | MFCS | TP | 2 | TC1.2 | A-FP | 2020-09-18
Harald | Release 3.1 | MFCS | TP | 2 | TC3.2 | A-FP | 2020-09-18
Harald | Release 7.1 | Unicorn | IIVP | 2 | N/A | A-FP | 2020-09-18
Harald | Release 7.1 | Unicorn | SCS/RN | 1 | N/A | A-FP | 2020-09-18
Philip | Release v6.50 | ImageCompare | TP | 1 | N/A | D | 2020-09-29 | Multiple Errors | Testing still missing for several requirements; TPconfiguration needs rework
Philip | Release v6.50 | ImageCompare | URS | 1 | N/A | D | 2020-09-29 | Multiple Errors | Several E-Sig requirements missing, or incorrectly "N/A-ed"
Philip | Release 13.2 | Fabiola | CII | 1 | N/A | D | 2020-09-30 | Multiple Errors | Interface definitions don't match URS
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | D | 2020-09-30 | Multiple Errors | Several AIR references contained and AIR workflows defined
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-09-30 | Multiple Errors | Interface definitions don't match CII
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | BOM | D | 2020-10-01 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LAG | D | 2020-10-01 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | CII | 1 | N/A | D | 2020-10-02 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | SPVP | 1 | Generic | D | 2020-10-02 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | DAC | D | 2020-10-02 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | REA | D | 2020-10-02 | Inaccurate information | NPV-Vera Transfer
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-02 | D | 2020-10-06 | Multiple Errors | Incorrect tracing
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-01 | D | 2020-10-06 | Multiple Errors | Name incorrect
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-02 | D | 2020-10-06 | Multiple Errors | Name incorrect, mismatch with URS
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-03 | D | 2020-10-06 | Multiple Errors | Name incorrect
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-04 | D | 2020-10-06 | Multiple Errors | Name incorrect, URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-07 | D | 2020-10-06 | Multiple Errors | Test not covered by URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-EH-02 | D | 2020-10-06 | Multiple Errors | Mismatch with URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-EH-04 | D | 2020-10-06 | Multiple Errors | Mismatch with URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-01 | D | 2020-10-06 | Multiple Errors | Test missing
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-03 | D | 2020-10-06 | Multiple Errors | URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBV-01 | D | 2020-10-06 | Multiple Errors | URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PE-03 | D | 2020-10-06 | Multiple Errors | URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-TPI-01 | D | 2020-10-06 | Multiple Errors | Test not covered by URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-03 | D | 2020-10-06 | Multiple Errors | Mismatch with URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-07 | D | 2020-10-06 | Multiple Errors | Test missing
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-VUB-03 | D | 2020-10-06 | Multiple Errors | Formatting issues, URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-010 | D | 2020-10-06 | Multiple Errors | Test missing
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-012 | D | 2020-10-06 | Multiple Errors | Mismatch with URS
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-10-06 | Multiple Errors | Several typos and mismatches vs. TPs
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-02 | D | 2020-10-07 | Multiple Errors | Incorrect tracing
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-02 | D | 2020-10-07 | Multiple Errors | Name incorrect, mismatch with URS
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-03 | D | 2020-10-07 | Multiple Errors | Name incorrect, URS text incomplete
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-07 | D | 2020-10-07 | Multiple Errors | Test not covered by URS
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-03 | D | 2020-10-07 | Multiple Errors | URS text incomplete
Philip | Release v6.50 | ImageCompare | IA | 1 | N/A | D | 2020-10-07 | Multiple Errors | Requirements vs. TP impact incorrect
Philip | Release v6.50 | ImageCompare | IIVP | 1 | N/A | D | 2020-10-07 | Multiple Errors | Installation checks missing
Philip | Release v6.50 | ImageCompare | TP | 1 | A1 | D | 2020-10-07 | Multiple Errors | Several URS not fully tested
Philip | Release v6.50 | ImageCompare | TP | 1 | A2 | D | 2020-10-07 | Multiple Errors | Several URS not fully tested
Philip | Release v6.50 | ImageCompare | TP | 1 | B | D | 2020-10-07 | Multiple Errors | Several URS not fully tested
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | BOM | D | 2020-10-10 | Inaccurate information | NPV-Vera Transfer
Philip | Release 13.2 | Fabiola | CII | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | DPP | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | IA | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | IDP | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | Verify Fabiola Server installation | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | Verify installation for Fabiola Client 1 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | Verify installation for Fabiola Client 2 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | Verify installation for Fabiola Client 3 (Devices) | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | 1 Upgrade and data migration - Pre-Testing-Steps | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | 2 Post-Test-Steps for test result equals PASS | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | 1 Rollback or recover - Application and data | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | 2 Rollback or recover - System | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | IIVP | 1 | Verify Fabiola Server installation | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | SAD | 1 | N/A | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | SCR | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-BAS-180 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-BAS-181 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-010 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-012 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-013 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-041 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-042 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-040 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | SEC-020 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-01 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-02 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-03 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DIP-04 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DAT-050 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DAT-055 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DAT-056 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-DEV-010 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-AMD-010 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | FAB-AMD-051 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-03a | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-03b | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-04 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-05 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-06 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-ABR-07 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-01 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-03 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBI-04 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-LBV-01 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-OED-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-OED-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-OED-03 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PAB-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PR-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PE-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PE-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-PE-03 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-TPF-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-TPI-01 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-TPV-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UA-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UA-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-02 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-03 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-04 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-05 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-06 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-07 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-08 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-09 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-UD-10 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-VUB-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-VUB-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-VUB-03 | A | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-AVP-01 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-AVP-02 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | PRC-AVP-03 | A-FP | 2020-10-12
Philip | Release 13.2 | Fabiola | TP | 1 | Retention Period | A-FP | 2020-10-12
Harald | Release 01.83.00 | LSP | SCA | 3 | N/A | D | 2020-10-12 | Incorrect Approvers | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | CDL | D | 2020-10-12 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LAG | D | 2020-10-12 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | REA | D | 2020-10-12 | Inaccurate information | NPV-Vera Transfer
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | A | 2020-10-13
Harald | Release 01.83.00 | LSP | MP | 1 | N/A | D | 2020-10-13 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | SCA | 3 | N/A | A | 2020-10-13 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | GIM | D | 2020-10-13 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS/TM | 46 | LAG | A-FP | 2020-10-13
Harald | Release 6.87 | LabSolutions | URS | 1 | N/A | D | 2020-10-14 | Inaccurate information
Harald | Release 01.83.00 | LSP | CII | 1 | N/A | D | 2020-10-14 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | COR | D | 2020-10-14 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | REA | D | 2020-10-14 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | CII | 1 | N/A | A | 2020-10-15 |  | NPV-Vera Transfer
Harald | Release 01.84.00 | LSP | IA | 1 | N/A | D | 2020-10-15 | Inaccurate information
Harald | Release 01.84.00 | LSP | SCR | 1 | N/A | D | 2020-10-15 | Inaccurate information
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LAG | D | 2020-10-15 | Inaccurate information | NPV-Vera Transfer
Philip | Release 01.56.00 | PARIS | IA | 1 | N/A | D | 2020-10-15 | Multiple Errors | Several sections are not filled out, contents incorrect
Philip | Release 01.56.00 | PARIS | MP | 1 | N/A | D | 2020-10-15 | Multiple Errors | Several AIR references contained and AIR workflows defined
Philip | Release 01.56.00 | PARIS | SCR | 1 | N/A | D | 2020-10-15 | Multiple Errors | Several sections are not filled out, contents incorrect
Philip | Release 01.56.00 | PARIS | SPVP | 1 | N/A | D | 2020-10-15 | Multiple Errors | Contents inappropriate and key aspects missing
Philip | Release 01.56.00 | PARIS | TP | 1 | N/A | D | 2020-10-15 | Inaccurate information | Test definition not as discussed
Philip | Release 01.56.00 | PARIS | URS | 1 | N/A | D | 2020-10-15 | Multiple Errors | Several sections are not filled out, contents incorrect
Harald | Release 01.84.00 | LSP | DV-UT | 1 | N/A | A-FP | 2020-10-16
Harald | Release 01.83.00 | LSP | IDP | 1 | N/A | D | 2020-10-16 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | MP | 1 | N/A | D | 2020-10-16 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.84.00 | LSP | SCR | 1 | N/A | D | 2020-10-16
Harald | Release 01.84.00 | LSP | SCR | 1 | N/A | A | 2020-10-16
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | GIM | D | 2020-10-16 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | INV | D | 2020-10-16 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SYM | D | 2020-10-16 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | IDP | 1 | N/A | A | 2020-10-19 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | MP | 1 | N/A | A | 2020-10-19 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | PAD | D | 2020-10-19 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SYM | D | 2020-10-19 | Inaccurate information | NPV-Vera Transfer
Philip | Release 01.21.00 | AFIL | IA | 1 | N/A | D | 2020-10-20 | Inaccurate information | SCR ID incorrect
Philip | Release 13.2 | Fabiola | IVR | 1 | 1 Upgrade and data migration - Pre-Testing-Steps | D | 2020-10-20 | Other | Attachment is missing information
Philip | Release 13.2 | Fabiola | IVR | 1 | Verify installation for Fabiola Client 1 | A-FP | 2020-10-20
Philip | Release 13.2 | Fabiola | IVR | 1 | Verify installation for Fabiola Client 3 (Devices) | A-FP | 2020-10-20
Philip | Release v6.50 | ImageCompare | CII | 1 | N/A | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | IA | 1 | N/A | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | IIVP | 1 | N/A | D | 2020-10-20 | Other | Superfluous attachment
Philip | Release v6.50 | ImageCompare | IIVP | 1 | N/A | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | TP | 1 | A1 | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | TP | 1 | A2 | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | TP | 1 | B | A | 2020-10-20
Philip | Release v6.50 | ImageCompare | URS | 1 | N/A | A | 2020-10-20
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | REA | D | 2020-10-20 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SYM | D | 2020-10-20 | Inaccurate information | NPV-Vera Transfer
Philip | Release 01.21.00 | AFIL | IA | 1 | N/A | D | 2020-10-21 | Inaccurate information | Incorrect deliverables selection
Philip | Release 01.21.00 | AFIL | URS | 1 | N/A | D | 2020-10-21 | Inaccurate information | Still contains eRIM contents
Philip | Release 13.2 | Fabiola | IVR | 1 | 1 Upgrade and data migration - Pre-Testing-Steps | A | 2020-10-21
Philip | Release 13.2 | Fabiola | IVR | 1 | Verify Fabiola Server installation | A-FP | 2020-10-21
Harald | Release 01.83.00 | LSP | IA | 1 | N/A | D | 2020-10-21 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | MCP | 1 | N/A | D | 2020-10-21 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | RA | 1 | N/A | A | 2020-10-21 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | SPVP | 1 | Generic | D | 2020-10-21 | Inaccurate information | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | APS | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | BOM | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | CDL | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | CSL | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | DAC | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | DGR | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | GIM | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | GRL | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | INV | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LAG | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LSH | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | PAD | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | PAM | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | PAO | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | RAC | A-FP | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SYM | A | 2020-10-21 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | ZARA | A | 2020-10-21 |  | NPV-Vera Transfer
Philip | Release v6.50 | ImageCompare | IVR | 1 | N/A | A-FP | 2020-10-22
Harald | Release 01.83.00 | LSP | ESRA | 1 | N/A | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | IA | 1 | N/A | A | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | MCP | 1 | N/A | A | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | Other | 1 | Trigger Tables | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | Other | 1 | Package Structure | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | RA | 1 | N/A | D | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | SPVP | 1 | Generic | A | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | ALC | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | CFR | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | COR | A | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | LCS | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | REA | A | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SHR | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.83.00 | LSP | URS/FRS | 1 | SOS | A-FP | 2020-10-22 |  | NPV-Vera Transfer
Harald | Release 01.84.00 | LSP | IA | 1 | N/A | D | 2020-10-23 | Inaccurate information
Philip | Release 01.21.00 | AFIL | SCA | 1 | N/A | A | 2020-10-26
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-BAS-180 | D | 2020-10-26 | Incorrect Approvers
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-BAS-181 | D | 2020-10-26 | Incorrect Approvers
Harald | Release 01.84.00 | LSP | IA | 1 | N/A | A | 2020-10-26
Harald | Release 01.85.00 | LSP | SCR | 1 | N/A | A-FP | 2020-10-26
Philip | Release 01.56.00 | PARIS | SCA | 1 | N/A | A | 2020-10-26
Philip | Release 01.21.00 | AFIL | IA | 1 | N/A | A | 2020-10-27
Philip | Release 01.21.00 | AFIL | MP | 1 | N/A | A | 2020-10-27
Philip | Release 01.21.00 | AFIL | SPVP | 1 | N/A | D | 2020-10-27 | Incorrect Approvers
Philip | Release 01.21.00 | AFIL | URS | 1 | N/A | A | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-BAS-180 | A | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-BAS-181 | A | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-010 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-012 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-020 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-DAT-050 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-DAT-055 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-DAT-056 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-DEV-010 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-AMD-010 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | FAB-AMD-051 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-TPF-01 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-TPV-01 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UA-01 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-01 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-02 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-03 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-04 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-05 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-06 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-07 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-08 | D | 2020-10-27 | Other | Not all entered information visible in log/printout
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-09 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UD-10 | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | Retention Period | A-FP | 2020-10-27
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UA-02 | D | 2020-10-27 | Other | Attachment missing/actual result unclear
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-040 | D | 2020-10-27 | Other | Role does not show up in log
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-013 | D | 2020-10-27 | Other | Additional information required to explain attachments
Harald | Release 01.84.00 | LSP | DV-UT | 1 | N/A | D | 2020-10-27 | Inaccurate information | Result
Harald | Release 01.84.00 | LSP | DV-UT | 1 | N/A | A | 2020-10-27 |  | Result
Harald | Release 01.84.00 | LSP | IIVP | 1 | ZARA Verification Protocol | A-FP | 2020-10-27
Harald | Release 01.84.00 | LSP | IIVP | 1 | 1 Initial Steps | A-FP | 2020-10-27
Harald | Release 01.84.00 | LSP | IIVP | 1 | 2 Pre-Steps | A-FP | 2020-10-27
Harald | Release 01.84.00 | LSP | IIVP | 1 | 3 Installation Steps | A-FP | 2020-10-27
Harald | Release 01.84.00 | LSP | IIVP | 1 | 4 Post-Steps | A-FP | 2020-10-27
Harald | Release 01.84.00 | LSP | IIVP | 1 | 5 Verification Steps | A-FP | 2020-10-27
Philip | Release 01.21.00 | AFIL | IIVP | 1 | N/A | A-FP | 2020-10-28
Philip | Release 01.21.00 | AFIL | SCR | 1 | N/A | A | 2020-10-28
Philip | Release 01.21.00 | AFIL | SPVP | 1 | N/A | A | 2020-10-28
Philip | Release 01.21.00 | AFIL | TP | 1 | N/A | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-PE-02 | D | 2020-10-28 | Other | Attachment missing
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-042 | D | 2020-10-28 | Other | Attachment missing/actual result unclear
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-013 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | SEC-041 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-VUB-01 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-VUB-02 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-VUB-03 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-PE-01 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-PE-03 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-UA-02 | A-FP | 2020-10-28
Philip | Release 13.2 | Fabiola | TPR | 1 | PRC-AVP-03 | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | IA | 1 | N/A | A | 2020-10-28
Philip | Release 01.56.00 | PARIS | MP | 1 | N/A | A | 2020-10-28
Philip | Release 01.56.00 | PARIS | SCR | 1 | N/A | A | 2020-10-28
Philip | Release 01.56.00 | PARIS | SPVP | 1 | N/A | A | 2020-10-28
Philip | Release 01.56.00 | PARIS | TP | 1 | AH | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | TP | 1 | CD | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | TP | 1 | CMD | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | TP | 1 | FC | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | TP | 1 | SD | A-FP | 2020-10-28
Philip | Release 01.56.00 | PARIS | URS | 1 | N/A | A | 2020-10-28
Harald | Release 01.86.00 | LSP | DV-UT | 1 | SCR L1900240 UT | D | 2020-10-28 | Inaccurate information
Harald | Release 01.86.00 | LSP | DV-UT | 1 | SCR L1900240 UT | A | 2020-10-29
Harald | Release 01.86.00 | LSP | DV-UT | 1 | SPR L2000082 UT | D | 2020-10-28 | Inaccurate information
Harald | Release 01.86.00 | LSP | DV-UT | 1 | SPR L2000082 UT | A | 2020-10-29
Harald | Release 01.84.00 | LSP | TP | 1 | TP SCR - PD-005195 | A-FP | 2020-10-29
Harald | Release 01.85.00 | LSP | SCR | 1 | SCR L1900240 UT | D | 2020-10-28 | Inaccurate information