## Config
SQA | Application | Deliverable Types | Reasons for Disapproval | A or D
Harald | ADOC | CII | Inaccurate information | A
Philip | AFIL | DD1 | Inadequate Description of Change | A-FP
| AMPS2G | DD2 | Incorrect Approvers | D
| ASC | DD3 | Incorrect Objective Evidence
| CMSN-Add-On | DPP | Incorrect scope
| Fabiola | DR | Insufficient testing
| IRR | DV-CR | Insufficient traceability
| ITS | DV-UT | Multiple Errors
| JAM | ESRA | N/A
| LIC | FRS | Not compliant with procedure
| LSP | IA | Not following configuration management
| MFCS | IDP | Not following document version control
| POD | IDP/IIVP | Not using template
| Q-EDI | IIVP | Other
| SFP | ISSD | Requirement deficiency
| SPOC | IVR
| Teklynx | MCP
| Turnover | MP
| Unicorn | RA
| viewLinc | RN
| WWLIMS | SAD
| XIAM | SCA
SCR
SCS
SCS/RN
SDP
SDR
SPP
SPR
SPVP
SVP
TM-DD to Code
TM-FRS to DD
TM-FRS to TP
TM-URS to FRS
TM-URS/FRS to TP
TP
TPR
URS
URS/FRS
URS/FRS/TM

## ACR
SQA | Application | ACR # | Date of CR Approval or Disapproval | CR Approve or Disapprove? | ACR I&E # | Date of I&E Approval or Disapproval | I&E Approve or Disapprove? | Reason for Disapproval | Comments

## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-10 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-14 | Inaccurate information
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | D | 2020-01-15 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-16 | Inaccurate information
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-17 | Inaccurate information | Mismatch of documentation impact vs. reality
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | D | 2020-01-17 | Inaccurate information | Schedule summary out of date
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | D | 2020-01-17 | Multiple Errors | Revision history incomplete, tracing incorrect
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-17 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-17 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | D | 2020-01-17 | Multiple Errors
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-20 | Inaccurate information | Test execution planning incorrect
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | D | 2020-01-20 | Inaccurate information | Revision history incorrect, table name duplicate
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-20 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | D | 2020-01-20 | Multiple Errors
Philip | Release 02.21.00 | ADOC | DV-UT | 1 | Incoming | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | IDP/IIVP | 1 | N/A | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 2 | TP60 | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | CII | 1 | N/A | A-FP | 2020-01-22
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | D | 2020-01-22 | Inaccurate information | Signature entry missing for post-turnover steps
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | A | 2020-01-22
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | D | 2020-01-22 | Inaccurate information | Impact analysis insufficient
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | A | 2020-01-22
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | TP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | URS/FRS/TM | 1 | N/A | A | 2020-01-22
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | D | 2020-01-23 | Inaccurate information | Test execution analysis missing
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP60 | A-FP | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP53 | A-FP | 2020-01-23
Harald | Release 3.1 | MFCS | CII | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER42 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SCR | 1 | A1900137 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SPR | 1 | A2000003 | A-FP | 2020-01-27
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-27 | Inaccurate information
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-27 | Multiple Errors
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-29 | Other | Needs to include related upcoming ADOC release
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | D | 2020-01-29 | Inaccurate information | Printer exchange, several explanations missing
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | A | 2020-01-29 |  | Printer exchange
Philip | Release 02.21.01 | ADOC | SPR | 1 | A2000010 | A-FP | 2020-01-30
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-30 | Inaccurate information | Tailoring justifications missing, deliverables missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-30 | Other | Dependencies between LIC & ADOC releases missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | A | 2020-01-30
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-30 | Inaccurate information | Traceability information incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | D | 2020-01-31 | Inaccurate information | Several references incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | A | 2020-01-31
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | D | 2020-01-31 | Inaccurate information | Constraints missing
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | A | 2020-01-31
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Action missing for newly added objects
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | A | 2020-01-31
Philip | Release 01.05.00 | LIC | TP | 1 | TP07 | A-FP | 2020-01-31
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | A | 2020-01-31
Philip | Release 01.00.02 | IRR | IA | 1 | N/A | D | 2020-02-03 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | DV-UT | 1 | N/A | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000002 | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000003 | A-FP | 2020-02-03