## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Wayne | LC-S 01073.000 | Groninger | Traceability | 1 | Protrace-01 | A-FP | 2018-01-16
Wayne | LC-S 01104.000 | Assay File Database | Software Change Request | 1 | SCR-01 | D | 2018-01-17 | Not compliant with procedure
Wayne | LC-S 01104.000 | Assay File Database | Software Change Request | 1 | SCR-01 | A | 2018-01-17
Wayne | LC-S 00986.005 | PCN/SCN | Software Compliance Assessment |  | SCA-01 | D | 2018-01-18 | Incorrect scope | Project name includes SMF, but Assessment links only PCN SCN
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TC_IPDR_ ADDWWLIMS08562_SLIGO | A | 2018-01-15 |  | Resubmittal
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TC_IPDR_ ADDWWLIMS08562_LONGFORD | A | 2018-01-15 |  | Resubmittal
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPIT_E_05 | D | 2018-01-11 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPIT_E_05 | A | 2018-01-15
Beilah | 01033.011 | Pulse | IIVP results | 1 | install for QA | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Traceability | 4 |  | A-FP | 2018-01-15
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | D | 2018-01-16 | Not following document version control | missing revision history/TCTCPIT_R_11
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-16
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 |  | A-FP | 2018-01-16
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPLR_R_11 | A-FP | 2018-01-18
Beilah | 01090.000 | WWLIMS | CII | 1 | Workstation v9.3a | A-FP | 2018-01-16
Beilah | 01090.000 | WWLIMS | CII | 1 | Supplemental Items v9.3a | A-FP | 2018-01-16
Beilah | 00303.099 | DFCS | Test Protocol Results | 1 | Test Protocol_01_DFCS_PostponementOrders | A-FP | 2018-01-16
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 1 | UAT 01_Postponement Picklist Changes | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 1 | UAT 02_ Regression | A-FP | 2018-01-17
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3: ADDULCD771510T | A-FP | 2018-01-17
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3: ADDULCD772728l | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | Software Change Request | 2 |  | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | Project Plan | 2 |  | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Test Protocol | 1 | HCE_Protocol | A-FP | 2018-01-03
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | HCE_Protocol | D | 2018-01-18 | Not compliant with procedure | missing signature
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | HCE_Protocol | A | 2018-01-18
Beilah | 01000.006 | DPW | Test Protocol | 1 | Search_Protocol | A-FP | 2018-01-09 |  | Previous link/approval
Beilah | 00100.006 | DPW | Test Protocol Results | 1 | Search_Protocol | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Test Protocol | 5 | Diagnostics Library_v5_Protocol | A-FP | 2018-01-03
Beilah | 01033.011 | Pulse | Test Protocol Results | 5 | Diagnostics Library_v5_Protocol | A-FP | 2018-01-18
Beilah | 01000.006 | DPW | System Certification Summary | 1 |  | D | 2018-01-18 | Inaccurate information
Beilah | 00303.099 | DFCS | Traceability | 13 |  | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | Design Verification | 1 | Unit Testing Document for QIMS v2.50 | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | Design Verification | 1 | Unit Testing Document for QIMS Report Manager v1.80 | A-FP | 2018-01-18
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_02 | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | D | 2018-01-18 | Inaccurate information
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | D | 2018-01-18 | Inaccurate information
Beilah | 01114.000 | Abbott Transfusion Medicine | Software Compliance Assessment | 1 | Abbott Transfusion Medicine | A-FP | 2018-01-18 |  | Automatic Exclusion
Nick | 928.007 | Apollo/PHM | IIVP results | 2 | 2 | A-FP | 2018-01-15
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 4 | D | 2018-01-15 | Inaccurate information
Nick | 750.011 | AFMS | Software Change Request | 3 | 1 | A | 2018-01-15
Nick | 750.011 | AFMS | URS | 6 | 1 | D | 2018-01-15 | Not compliant with procedure | incorrect deletion of requirements
Nick | 750.011 | AFMS | FRS | 6 | 1 | D | 2018-01-15 | Not compliant with procedure | incorrect deletion of requirements
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 3 | A-FP | 2018-01-15
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 4 | A | 2018-01-15
Nick | 928.007 | Apollo/PHM | Test Protocol | 3 | 2 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 6 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 1 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 12 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 11 | A-FP | 2018-01-16
Nick | 750.011 | AFMS | URS | 6 | 1 | A | 2018-01-16
Nick | 750.011 | AFMS | FRS | 15 | 1 | D | 2018-01-16 | Not compliant with procedure
Nick | 750.011 | AFMS | CII | 9 | 1 | A | 2018-01-16
Nick | 354.004 | SAS | Test Protocol | 3 | 1 | A-FP | 2018-01-16
Nick | 750.011 | AFMS | FRS | 15 | 1 | A | 2018-01-16
Nick | 750.011 | AFMS | Validation Plan | 2 | 1 | A | 2018-01-17
Nick | epas 18-1658 | Metrics Library | Project Plan | 2 |  | A-FP | 2018-01-18
Nick | 750.011 | AFMS | Test Protocol | 2 | 3 | A-FP | 2018-01-18
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-18 | Inaccurate information
Nick | 1075.001 | DaVinci | Software Change Request | 1 | 1 | A | 2018-01-19
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-19 | Inaccurate information
Nick | 1075.001 | DaVinci | FRS | 2 | 1 | D | 2018-01-19 | Requirement deficiency
Wayne | LC-S 00986.005 | PCN/SCN | Software Compliance Assessment | 1 | SCA-01 | A | 2018-01-22
Wayne | LC-S 01104.000 | Assay File Database | Project Plan | 1 | 1 | D | 2018-01-23 | Other | PreReview before NPV submittal
Wayne | LC-S 00986.005 | PCN/SCN | Software Change Request | 1 | 1 | D | 2018-01-24 | Inaccurate information
Wayne | LC-S 00986.005 | PCN/SCN | Software Change Request | 1 | 1 | A | 2018-01-24
Wayne | LC-S 00986.005 | PCN/SCN | FRS | 16 |  | A-FP | 2018-01-25
Wayne | LC-S 00986.005 | PCN/SCN | Design Verification | 1 |  | A-FP | 2018-01-26
Nick | 589.05 | CMSNext | Software Compliance Assessment | 1 | 1 | D | 2018-01-22 | Inaccurate information | Bad Link
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 1 | A-FP | 2018-01-22
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-22 | Inaccurate information
Nick | ePAS 16-33266 v12 | GS Reports | Project Plan | 1 |  | A | 2018-01-22
Nick | 345.004 | SAS | Test Protocol Results | 3 | 1 | A-FP | 2018-01-22 |  | Sas Micro Biasplot
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-22 | Inaccurate information
NIck | 589.05 | CMSNext | Software Compliance Assessment | 1 | 1 | A | 2018-01-23
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-23 | Inaccurate information
Nick | 1075.001 | DaVinci | URS | 2 | 1 | D | 2018-01-23 | Not compliant with procedure | Approver List
Nick | 1075.001 | DaVinci | Validation Plan | 1 | 1 | D | 2018-01-23 | Not compliant with procedure | Approver List
Nick | 354.004 | SAS | System Certification Summary | 1 | 1 | A-FP | 2018-01-23
Nick | ePAS 15-15617 V8 | GS Reports | Project Plan | 1 |  | A-FP | 2018-01-24
Nick | ePAS 18-1699 | Metrics Library | Design Documentation | 1 |  | A-FP | 2018-01-24 |  | source to target
Nick | ePAS 18-1700 | Metrics Library | Design Documentation | 1 |  | A-FP | 2018-01-24 |  | source to target
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | D | 2018-01-24 | Inaccurate information
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | URS | 2 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | CII | 1 | 1 | D | 2018-01-24 | Not following document version control | not to release but to software.
Nick | ePAS 16-38941 V3 | GS Reports | Move to Production | 1 | 1 | A-FP | 2018-01-24
Nick | 1075.001 | DaVinci | Validation Plan | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | CII | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | FRS | 2 | 1 | A | 2018-01-25
nick | 1075.001 | DaVinci | CII | 1 | 1 | A | 2018-01-25
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 1 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 2 | D | 2018-01-25 | Inaccurate information
Nick | 750.11 | AFMS | Test Protocol | 4 | 8 | D | 2018-01-25 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 2 | D | 2018-01-25 | Inaccurate information
Nick | 750.11 | AFMS | Test Protocol | 4 | 8 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 3 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 2 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 1 | A | 2018-01-25
Nick | 589.05 | CMSNext | Software Change Request | 1 | 1 | D | 2018-01-26 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | A | 2018-01-26
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 3 | A | 2018-01-26
Wayne | LC-S 00986.005 | PCN/SCN | IIVP | 1 |  | D | 2018-01-26 | Inaccurate information | No instruction to generate Objective Evidence
Wayne | LC-S 00986.005 | PCN/SCN | IIVP | 1 |  | A | 2018-01-26
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | D | 2018-01-19 | Inaccurate information | Disapproved 2nd time
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | A | 2018-01-19
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | D | 2018-01-19 | Inaccurate information | Disapproved 2nd time
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | FRS | 9 | WWLIMS Bookshelf: Assay File Management | A | 2018-01-19 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-19 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-24 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | D | 2018-01-19 | Not following document version control
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPLC_E_15 | A-FP | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_1 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_1 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_2 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_2 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_3 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_3 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | DT_ArchitectAssayDetail | A-FP | 2018-01-19
Beilah | 01090.000 | DPW | Test Protocol Results | 1 | Translation Workflow_Diagnostics.abbott_v2_Protocol | A-FP | 2018-01-19
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | D | 2018-01-22 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | A | 2018-01-24
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | A | 2018-01-25 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A | 2018-01-24 |  | Resubmitted for minor correction.
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A | 2018-01-25 |  | Resubmitted for minor correction.
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Test Protocol TCTCPIT_E_05: ADDULCD771510T | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLC_R_05 : ADDULCD772728L | A-FP | 2018-01-22
Beilah | 01094.001 | IRIS | IIVP results | 1 | Prod | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Test Protocol TCTCPLC_E_15: ADDULCD772728L | A-FP | 2018-01-22
Beilah | 01101.000 | QIMS | IIVP | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | A-FP | 2018-01-22
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | D | 2018-01-22 | Not compliant with procedure
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | A | 2018-01-22
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employee Valuation Testing: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employee Valuation Testing: v2.50 | A | 2018-01-25
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-24 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-25 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | D | 2018-01-24 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | A | 2018-01-25
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employees Maintenance Regression Testing: v2.50 | D | 2018-01-22 |  | No req trace to review against.
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employees Maintenance Regression Testing: v2.50 | D | 2018-01-25 | Inaccurate information
Beilah | 00303.099 | DFCS | Design Verification | 3 | Design Verification: Pick list | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | IIVP | 1 | IIVP- Instrument Server-v9.3 | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | CII | 4 | CII | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | IIVP | 4 | Install | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | User Acceptance Protocol results | 1 | UAT 01_Postponement Picklist Changes_Results - FAIL | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 2 | UAT 01_Postponement Picklist Changes | D | 2018-01-23 | Not using template | template is okay just missing header.
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 2 | UAT 01_Postponement Picklist Changes | A | 2018-01-23
Beilah | 00303.099 | DFCS | Test Protocol | 3 | Test Protocol_01_DFCS_PostponementOrders | A-FP | 2018-01-23
Beilah | 00303.099 | DFCS | Test Protocol Results | 3 | Test Protocol_01_DFCS_PostponementOrders_Results | D | 2018-01-24 | Inaccurate information
Beilah | 00303.099 | DFCS | Test Protocol Results | 3 | Test Protocol_01_DFCS_PostponementOrders_Results | A | 2018-01-24 |  | Failed test
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPIT_R_12 Result: ADDULCD771510T | A-FP | 2018-01-23
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit test - Instrument Server v9.3a | A-FP | 2018-01-23
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPINDT_14 Result: ADDULCD771510T | D | 2018-01-24 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPINDT_14 Result: ADDULCD771510T | A | 2018-01-25
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Test Protocol TCTCPINDT_14 | A | 2018-01-25 |  | only for update purposes.
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Test Protocol TCTCPINDT_14 | A | 2018-01-25 |  | only for update purposes.
Beilah | 01090.000 | WWLIMS | Traceability | 16 | Traceability Matrix - TPTCPPRT | D | 2018-01-24 | Inaccurate information | This was approved once resubmitted and upon resubmittle has wrong header invofrrmation
Beilah | 01090.000 | WWLIMS | Traceability | 16 | Traceability Matrix - TPTCPPRT | A | 2018-01-24
Beilah | 01101.000 | QIMS | Traceability | 7 | FRS Section 2 Traceability Matrix (for QIMS 2.50) | D | 2018-01-24 | Inaccurate information
Beilah | 01101.000 | QIMS | Traceability | 7 | FRS Section 2 Traceability Matrix (for QIMS 2.50) | A | 2018-01-25
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3a | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_01 | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Traceability | 1 | Traceability Matrix - TPIDARCC | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Traceability | 11 | Traceability Matrix - TPTCPINDT | A-FP | 2018-01-25
Beilah | 01090.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | D | 2018-01-25 | Inaccurate information
Liz | 01117.000 | ideaPoint | Software Compliance Assessment | 1 |  | A-FP | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Development Test Protocol | D | 2018-01-26 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol | 3 | Development Test Protocol | A | 2018-01-29
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCISVR_01 | A-FP | 2018-01-26
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCISVR_01 | A-FP | 2018-01-30 |  | resubmitted
Beilah | 01090.000 | WWLIMS | Traceability | 8 | Traceability Matrix - TPISVR | D | 2018-01-26 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Traceability | 8 | Traceability Matrix - TPISVR | A | 2018-01-29
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit Test - WorkStation v9.3b | A-FP | 2018-01-26
Beilah | 01101.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | D | 2018-01-26 | Other | Blank page
Beilah | 01101.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | A | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | A | 2018-01-26
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | D | 2018-01-26 | Other | wrong document attached to NVP
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory-Workstation v9.3b | A-FP | 2018-01-26
Beilah | 01033.011 | Pulse | System Certification Summary | 1 | Certification Summary | A-FP | 2018-01-26
Beilah | 01090.000 | WWLIMS | Validation Plan | 3 | Val Plan | A-FP | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | D | 2018-01-26
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | A | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 02 - IPDR ADDQIMS08557: failed | A-FP | 2018-02-01 |  | Failed step will be rerun
Beilah | 01101.000 | QIMS | Test Protocol | 2 | DT_ArchitectAssayDetail | A-FP | 2018-01-29
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation: ADDULCD771510T 9.3b | A-FP | 2018-01-29
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation: ADDULCD772728L 9.3b | A-FP | 2018-01-29
Beilah | 01033.011 | Pulse | IIVP results | 1 | Installation Instructions and Verification Protocol_Prod | A-FP | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | D | 2018-01-30 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | A | 2018-01-31
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | D | 2018-01-30 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | A | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol | 3 | DT_ArchitectAssayDetail | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass - Test Protocol DT_ArchitectAssayDetail Result: ADDULCD772728L | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol TCAFMARAD_2 Result: ADDULCD771510T | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | CII | 2 | Configuration Item Inventory - Instrument Server v9.3a | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | A | 2018-01-30 |  | Resubmitted
Beilah | 01033.013 | Pulse | Software Compliance Assessment | 6 | Release v15.0 | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 ADDULCL771783 9.3 | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol TCAFMARAD_3 Result: ADDULCD772728L | A-FP | 2018-01-31
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 03 - IPDR ADDQIMS08558 | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 03 - IPDR ADDQIMS08558 | A | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol - TCAFMARAD_1 Result: ADDULCD772728L | A-FP | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | TCIDARCC_01 | A | 2018-01-31 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | A | 2018-02-01
Beilah | 01090.000 | WWLIMS | URS | 33 | WWLIMS User Requirements Specification |  | 2018-02-01
Beilah | 01090.000 | WWLIMS | URS | 24 | WWLIMS Traceability Matrix |  | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_02 | A | 2018-02-01 |  | Resubmitted
Beilah | 01101.000 | QIMS | Design Verification | 2 | Unit Testing Document for QIMS v2.50 | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | D | 2018-02-01 | Insufficient testing | missing screen prints
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | A | 2018-02-01
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit test - Instrument Server v9.3b | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3b | A-FP | 2018-02-01
Beilah | 01101.000 | QIMS | CII | 2 | Configuration Item Inventory for QIMS 2.50 | A-FP | 2018-02-01
Beilah | 01006.002 | Alinity Source Verifier | Software Compliance Assessment | 1 |  | A-FP | 2018-02-01 |  | Link to original SCA
Beilah | 01101.000 | QIMS | IIVP results | 2 | Quality Information Management System (QIMS) Version 2.50 – Manual Installation Instructions for 32 bit or 64 bit pc | A-FP | 2018-02-01
Beilah | 01006.002 | Alinity Source Verifier | Software Change Request | 1 |  | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TC_IPDR_ ADDWWLIMS08562_SLIGO Result: ADDULCD773047T | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol - TC_IPDR_ ADDWWLIMS08562_LONGFORD Result: ADDULCD773047T | A-FP | 2018-02-01
Nick | 345.004 | SAS | Test Protocol | 1 | 1 | A-FP | 2018-01-25 |  | regplot micro
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 | A-FP | 2018-01-27
Nick | 589.05 | CMSNext | Software Change Request | 1 | 1 | D | 2018-01-29 | Not compliant with procedure
Nick | 1075.001 | DaVinci | ISSD | 1 | 1 | A-FP | 2018-01-29
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | A | 2018-01-29
Nick | 750.011 | AFMS | Test Protocol | 2 | 2 | A-FP | 2018-01-29
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 3 | D | 2018-01-29 | Other
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 3 | A | 2018-01-29
Nick | 581.024 | TODS | Software Change Request | 1 | 1 | D | 2018-01-29
Nick | 928.008 | Apollo/PHM | Software Compliance Assessment | 1 | 1 | D | 2018-01-30 | Other
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 1 | A-FP | 2018-01-30
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | D | 2018-01-30 | Inaccurate information
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | D | 2018-01-30 | Other
Nick | ePAS 18-1902 | Metrics Library | Validation Plan | 1 |  | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Traceability | 2 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 2 | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 4 | D | 2018-01-31 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | D | 2018-01-31 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 4 | A | 2018-01-31
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | D | 2018-01-31 | Other
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | D | 2018-01-31 | Inaccurate information
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | D | 2018-01-31 | Inaccurate information
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | A | 2018-01-31
Nick | ePAS 17-4771 V11.0 | GS Reports | Move to Production | 1 | 1 | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 prod | D | 2018-02-01 | Inaccurate information
Nick | ePAS 18-1699 | Metrics Library | Design Documentation | 1 |  | A | 2018-02-01
Nick | ePAS 18-1700 | Metrics Library | Design Documentation | 1 |  | A | 2018-02-01
Nick | ePAS 18-2537 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-01
Nick | ePAS 18-2538 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-01
Nick | 345.004 | SAS | System Certification Summary | 1 | 1 | A-FP | 2018-02-01 |  | regplot micro
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 3 | D | 2018-02-01 | Not compliant with procedure
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 prod | A | 2018-02-02
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 3 | A | 2018-02-02

## SQA
Beilah
Liz
Nick
Wayne

## Application
Application
123 Compliance
Abbott Transfusion Medicine
ADD Shop Floor Paper (SFP) Report System
AFMS
Alinity Source Verifier
ALMS
Apollo/PHM
Artifactory
ASAP
Assay File Database
BitBucket
Clinical Trials DB (CTD)
ClinPlus CTMS
CMSNext
Commercial Affiliate eSMF
DaVinci
DFCS
DPW
EDMS
E-labeling Web Package Insert Retrieval
EP Evaluator
GDSN/GS1
Groninger
GS Reports
ICQ Filler Data Collection
ideaPoint
IRIS
JAMA
Knowledge Management
Metrics Library
MSS
PCN/SCN
PEAR
PRISM Metrics
PSA
Pulse
QIMS
Reliasoft Xfmea
RSLMS
SAS
TODS
WWLIMS

## Deliverable Types
CII
Data Migration Plan
Data Privacy Plan
Design Documentation
Design Verification
FRS
IDP
IIVP
IIVP results
ISSD
Maintenance Plan
Move to Production
Project Plan
Release Notes
Software Change Request
Software Compliance Assessment
System Certification Summary
Test Protocol
Test Protocol Results
Traceability
URS
URS/FRS
User Acceptance Protocol
User Acceptance Protocol results
Validation Plan

## Reasons for Disapproval
Inaccurate information
Incorrect scope
Insufficient testing
Insufficient traceability
N/A
Not compliant with procedure
Not following configuration management
Not following document version control
Not using template
Other
Requirement deficiency

## A or D
A
D
A-FP