## ACR
SQA | Application | ACR # | Date of CR Approval or Disapproval | CR Approve or Disapprove? | ACR I&E # | Date of I&E Approval or Disapproval | I&E Approve or Disapprove? | Reason for Disapproval | Comments
Lan | Global Product Part Master (GPPM) | CSIT09631 | 2019-07-11 | A-FP
Lan | Global Product Part Master (GPPM) | CSIT09639 | 2019-08-05 | A-FP
Lan | Global Product Part Master (GPPM) | CSIT09694 | 2019-07-31 | A-FP

## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Software Change Request | 8 | SCR-08 | D | 2019-07-10 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | URS | 3 | URS-03 | D | 2019-07-16 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Software Change Request | 8 | SCR-08 | A | 2019-07-30 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | URS | 3 | URS-03 | A | 2019-07-31 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | FRS | 5 | FRS-05 | D | 2019-08-01 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | FRS | 5 | FRS-05 | A | 2019-08-08 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 7 | Install -01 | A | 2019-08-19 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 2 | Protocol -08 | D | 2019-08-21 | Mutlible Errors | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 1 | Protocol -09 | D | 2019-08-22 | Mutlible Errors | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Traceability | 4 | Tmatrix-01 | D | 2019-08-22 | Insufficient traceability | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 2 | Protocol -08 | A | 2019-08-26 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 1 | Protocol -09 | A | 2019-08-27 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Traceability | 4 | Tmatrix-01 | A | 2019-08-29 |  | NPV
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-03 | D | 2019-07-19 | Inaccurate information | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-02 | D | 2019-07-19 | Mutlible Errors | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-03 | A | 2019-07-22 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-02 | A | 2019-07-22 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP | 1 | Install-01 | A-FP | 2019-07-22 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP | 1 | Install-01 | A-FP | 2019-07-22 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP | 1 | Install-03 | A-FP | 2019-07-22 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP results | 1 | Install-02 | A | 2019-07-29 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Test Protocol | 1 | Protocol-26 | A-FP | 2019-07-29 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol | 1 | Protocol-10 | A-FP | 2019-07-29 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-01 | D | 2019-08-01 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-02 | D | 2019-08-01 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-01 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-02 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-03 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-05 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-06 | Mutlible Errors | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 2 | Install-03 | A | 2019-08-07 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol | 1 | Protocol-24 | A-FP | 2019-08-08 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 2 | Install-03 Results | A | 2019-08-09 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol | 1 | Protocol-23 | A | 2019-08-10 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP results | 1 | Install-01 | A-FP | 2019-08-10 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-01 | A-FP | 2019-08-10 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-03 | A-FP | 2019-08-10 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-10 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Traceability | 2 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-15 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | A | 2019-08-16 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol Results | 1 | Protocol-23 | D | 2019-08-20 | Mutlible Errors | Email
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-22 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | IIVP results | 2 | Install-01 | D | 2019-08-22 | Mutlible Errors
Carole | DA-S01509.000 | ESD | IIVP results | 2 | Install-01 | A | 2019-08-22 | N/A
Carole | DA-S01509.000 | ESD | Other | 3 | Deployment Plan (Post IQ)-01 | D | 2019-08-22 | Inaccurate information | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 3 | Install-03 | D | 2019-08-23 | Inaccurate information | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol Results | 1 | Protocol-23 | A | 2019-08-23 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol Results | 1 | Protocol-10 | A-FP | 2019-08-23 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-24 | A-FP | 2019-08-23 | N/A
Carole | DA-S00931.001 | ADMS Order Management | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | Other | 3 | Deployment Plan (Post IQ)-01 | A | 2019-08-23 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 3 | Install-03 Results | A-FP | 2019-08-24 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Test Protocol Results | 1 | Protocol-26 | A | 2019-08-24 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-24 | Mutlible Errors | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-03 Results | D | 2019-08-26 | Incorrect Approvers | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-03 Results | A | 2019-08-26 | N/A | Approve Failed Results in NPV
Carole | DA-S00921.001 | ADMS R12 - Inventory | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26
Carole | DA-S00931.001 | ADMS Order Management | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-04 | A | 2019-08-29 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP results | 1 | Install-01 | A-FP | 2019-08-29
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-01 | A-FP | 2019-08-29 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-03 | A-FP | 2019-08-29 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-04 Results | A | 2019-08-30 | N/A
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-02 | Not using template | Email
Ken | DA-S01449.000 | PRISM OMT Test Fixture | CII | 2 |  | D | 2019-08-13 | Inaccurate information | CII change without IPDR
Ken | DA-S01449.000 | PRISM OMT Test Fixture | IIVP results | 1 | Install-01 Results | D | 2019-08-13 | Inaccurate information | Does not match CII
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-22 | Other | Email
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 1 | SQA-09 | D | 2019-08-28 | N/A | Email
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 2 | SQA-08 | D | 2019-08-29 | Incorrect scope | AWC 3.3 upgrade to AWC 4.2, use new extension
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-30 | Other | Email
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | URS | 5 | SRS-01ver5 FRS for QIST v3.2 | D | 2019-07-21 | Inaccurate information | Email
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | URS | 5 | SRS-01ver5 FRS for QIST v3.2 | A | 2019-07-24
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | Project Plan | 1 | SPP-02ver01 SPP for QIST v3.2 | A | 2019-07-29
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | FRS | 5 | SRS-01ver5 FRS for QIST v3.2 | D | 2019-08-01 | Inaccurate information | Email
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | Project Plan | 5 | SPP-02ver01 SPP for QIST v3.2 | D | 2019-08-01 | Inaccurate information | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | SCR-02v01 Software Change Request | D | 2019-08-01 | Mutlible Errors | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | URS | 1 | URS-01v02 User Requirements Specification] | D | 2019-08-02 | Mutlible Errors | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol | 2 | Protocol-01v02 Protocol | D | 2019-08-05 | Mutlible Errors | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 2 | SCR-02v01 Software Change Request | A | 2019-08-08
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | URS | 1 | URS-01v02 User Requirements Specification] | A | 2019-08-08
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | CII | 1 | VDD-02v01 CII / Spreadsheet Template v1.10 | D | 2019-08-08 | Mutlible Errors | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | CII | 1 | VDD-02v01 CII / Spreadsheet Template v1.10 | A | 2019-08-08
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol | 3 | Protocol-01v02 Protocol | A | 2019-08-09
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol Results | 1 | Protocol-01v02 Protocol Result | A | 2019-08-09
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-09 | Mutlible Errors | Email
Lan | 1457 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-09
Lan | 1069.003 | QIST : Quality Impact Score Tool 3.2 | FRS | 5 | SRS-01ver5 FRS for QIST v3.2 | A | 2019-08-12

## SQA
Arun
Carole
Ken
Lan
Liz

## Application
Application | Application Owner or BRM
Abbott Collaborative Environment (ACE)
Abbott Product Lifecycle Management (APLM)
AbbottLink Q Simulator
ADMS Account payable
ADMS Advance Supply Chain
ADMS Bills of Material
ADMS Cost/GL management
ADMS Demantra
ADMS Engineering
ADMS Global Module
ADMS Inventory
ADMS iSupplier
ADMS MPS/MRP
ADMS Order Management
ADMS Purchasing
ADMS Quality
ADMS ShipConsole
ADMS Warehouse Management
ADMS Work in Progress
Alinity S Result QC
ALISS (Alinity LIS Simulator)
Amplifier Research (AR) emcware - Radiated Immunity (Susceptibility) Test Software
APLM - Design Planning (DP) Workflow
APLM - QSR Workflow
Architect Instrument Test Station Configuration Software
Assay Checker Update for Architect Software version 8.1
Automated Refrigeration Monitoring System (ARMS)
Bamboo for Unit Test Result Reporting
BSQ Device Simulator - EP
Calibrator PDF to XML Converter
Camstar
Compliance Test System (CTS) - Harmonics & Flicker Test Software
Desco / Edge ESD Tester
ESD
File Verification Suite
Global Product Part Master (GPPM)
Gravimetric Vol. Cal Spreadsheet v1.10
GSS Reliability Database
HL7 Simulator for BSQ (HL7SIM-BSQ)
HP Quality Center Version 11.0 Validation
IBM Rational ClearCase
ICQ Device Simulator 1.3
IDA (Instrument Data Analytics)
IDA Data Mart (Maintenance)
IDA Data Mart 2.0 Assay Early Warning
IDA Data Mart 3.0 - Westgard Automation
IDA ETL A3600
IDA-Q
Induction Heating Serial/USB GUI
Ixiasoft DITA Content Management System
LIS Simulator
Load Runner
Loftware Software Suite
LOG-ICAL
Mashup - Design Plan
Mashup - Product Defect Tracking
MobileONe
Proactive Operations Monitoring 2.10
Q ASTM Simulator
QIA Server Interface Simulator
QIST : Quality Impact Score Tool 3.2
Reference Standard Inspection Spreadsheet Template
SBM - Affiliate CAPA
SBM - Distributor Control
SBM - Meetings Application
SBM - Pre-Market Issue Tracking
SBM DCR
SBM Machine Shop (SBM MS)
Serena Business Manager (SBM) - Base (Core) Application Upgrade
Software Tool Access Request System (STARS)
SolidWorks Enterprise Product Data Management (SWEPDM)
Stats CC Data Process
SyncMyGSS - APLM to GSS Web Publish
Team Track - Non-Product Software Problem Reporting
Ticket Code Tool Database and ASP Interface

## Deliverable Types
Cancellation
CII
Data Migration Plan
Data Privacy Plan
Decommissioning Plan
Decommissioning Report
Design Documentation
Design Verification
ERES
FRS
IDP
IIVP
IIVP results
ISSD
Maintenance Plan
Move to Production
Other
Project Plan
Release Notes
Risk Assessment
Software Change Request
Software Compliance Assessment
System Certification Summary
Test Protocol
Test Protocol Results
Traceability
URS
URS/FRS
User Acceptance Protocol
User Acceptance Protocol results
Validation Plan

## Reasons for Disapproval
Inaccurate information
Inadequate Description of Change
Incorrect Approvers
Incorrect Objective Evidence
Incorrect scope
Insufficient testing
Insufficient traceability
Mutlible Errors
N/A
Not compliant with procedure
Not following configuration management
Not following document version control
Not using template
Other
Requirement deficiency

## A or D
A
D
A-FP