## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Wayne | LC-S 01073.000 | Groninger | Traceability | 1 | Protrace-01 | A-FP | 2018-01-16
Wayne | LC-S 01104.000 | Assay File Database | Software Change Request | 1 | SCR-01 | D | 2018-01-17 | Not compliant with procedure
Wayne | LC-S 01104.000 | Assay File Database | Software Change Request | 1 | SCR-01 | A | 2018-01-17
Wayne | LC-S 00986.005 | PCN/SCN | Software Compliance Assessment | 1 | SCA-01 | D | 2018-01-18 | Incorrect scope | Project name includes SMF, but Assessment links only PCN SCN
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TC_IPDR_ ADDWWLIMS08562_SLIGO | A | 2018-01-15 |  | Resubmittal
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TC_IPDR_ ADDWWLIMS08562_LONGFORD | A | 2018-01-15 |  | Resubmittal
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPIT_E_05 | D | 2018-01-11 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPIT_E_05 | A | 2018-01-15
Beilah | 01033.011 | Pulse | IIVP results | 1 | install for QA | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-15
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | DP_Product Lines_Protocol | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Traceability | 4 |  | A-FP | 2018-01-15
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | D | 2018-01-16 | Not following document version control | missing revision history/TCTCPIT_R_11
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-16
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 |  | A-FP | 2018-01-16
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPLR_R_11 | A-FP | 2018-01-18
Beilah | 01090.000 | WWLIMS | CII | 1 | Workstation v9.3a | A-FP | 2018-01-16
Beilah | 01090.000 | WWLIMS | CII | 1 | Supplemental Items v9.3a | A-FP | 2018-01-16
Beilah | 00303.099 | DFCS | Test Protocol Results | 1 | Test Protocol_01_DFCS_PostponementOrders | A-FP | 2018-01-16
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 1 | UAT 01_Postponement Picklist Changes | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 1 | UAT 02_ Regression | A-FP | 2018-01-17
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3: ADDULCD771510T | A-FP | 2018-01-17
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3: ADDULCD772728l | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | Software Change Request | 2 |  | A-FP | 2018-01-17
Beilah | 00303.099 | DFCS | Project Plan | 2 |  | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Test Protocol | 1 | HCE_Protocol | A-FP | 2018-01-03
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | HCE_Protocol | D | 2018-01-18 | Not compliant with procedure | missing signature
Beilah | 01033.011 | Pulse | Test Protocol Results | 1 | HCE_Protocol | A | 2018-01-18
Beilah | 01000.006 | DPW | Test Protocol | 1 | Search_Protocol | A-FP | 2018-01-09 |  | Previous link/approval
Beilah | 00100.006 | DPW | Test Protocol Results | 1 | Search_Protocol | A-FP | 2018-01-17
Beilah | 01033.011 | Pulse | Test Protocol | 5 | Diagnostics Library_v5_Protocol | A-FP | 2018-01-03
Beilah | 01033.011 | Pulse | Test Protocol Results | 5 | Diagnostics Library_v5_Protocol | A-FP | 2018-01-18
Beilah | 01000.006 | DPW | System Certification Summary | 1 |  | D | 2018-01-18 | Inaccurate information
Beilah | 00303.099 | DFCS | Traceability | 13 |  | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | Design Verification | 1 | Unit Testing Document for QIMS v2.50 | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | Design Verification | 1 | Unit Testing Document for QIMS Report Manager v1.80 | A-FP | 2018-01-18
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_02 | A-FP | 2018-01-18
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | D | 2018-01-18 | Inaccurate information
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | D | 2018-01-18 | Inaccurate information
Beilah | 01114.000 | Abbott Transfusion Medicine | Software Compliance Assessment | 1 | Abbott Transfusion Medicine | A-FP | 2018-01-18 |  | Automatic Exclusion
Nick | 928.007 | Apollo/PHM | IIVP results | 2 | 2 | A-FP | 2018-01-15
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 4 | D | 2018-01-15 | Inaccurate information
Nick | 750.011 | AFMS | Software Change Request | 3 | 1 | A | 2018-01-15
Nick | 750.011 | AFMS | URS | 6 | 1 | D | 2018-01-15 | Not compliant with procedure | incorrect deletion of requirements
Nick | 750.011 | AFMS | FRS | 6 | 1 | D | 2018-01-15 | Not compliant with procedure | incorrect deletion of requirements
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 3 | A-FP | 2018-01-15
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 4 | A | 2018-01-15
Nick | 928.007 | Apollo/PHM | Test Protocol | 3 | 2 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 6 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 1 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 12 | A-FP | 2018-01-16
Nick | 928.007 | Apollo/PHM | Test Protocol | 2 | 11 | A-FP | 2018-01-16
Nick | 750.011 | AFMS | URS | 6 | 1 | A | 2018-01-16
Nick | 750.011 | AFMS | FRS | 15 | 1 | D | 2018-01-16 | Not compliant with procedure
Nick | 750.011 | AFMS | CII | 9 | 1 | A | 2018-01-16
Nick | 354.004 | SAS | Test Protocol | 3 | 1 | A-FP | 2018-01-16
Nick | 750.011 | AFMS | FRS | 15 | 1 | A | 2018-01-16
Nick | 750.011 | AFMS | Validation Plan | 2 | 1 | A | 2018-01-17
Nick | epas 18-1658 | Metrics Library | Project Plan | 2 |  | A-FP | 2018-01-18
Nick | 750.011 | AFMS | Test Protocol | 2 | 3 | A-FP | 2018-01-18
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-18 | Inaccurate information
Nick | 1075.001 | DaVinci | Software Change Request | 1 | 1 | A | 2018-01-19
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-19 | Inaccurate information
Nick | 1075.001 | DaVinci | FRS | 2 | 1 | D | 2018-01-19 | Requirement deficiency
Wayne | LC-S 00986.005 | PCN/SCN | Software Compliance Assessment | 1 | SCA-01 | A | 2018-01-22
Wayne | LC-S 01104.000 | Assay File Database | Project Plan | 1 | 1 | D | 2018-01-23 | Other | PreReview before NPV submittal
Wayne | LC-S 00986.005 | PCN/SCN | Software Change Request | 1 | 1 | D | 2018-01-24 | Inaccurate information
Wayne | LC-S 00986.005 | PCN/SCN | Software Change Request | 1 | 1 | A | 2018-01-24
Wayne | LC-S 00986.005 | PCN/SCN | FRS | 16 | 1 | A-FP | 2018-01-25
Wayne | LC-S 00986.005 | PCN/SCN | Design Verification | 1 | 1 | A-FP | 2018-01-26
Nick | 589.05 | CMSNext | Software Compliance Assessment | 1 | 1 | D | 2018-01-22 | Inaccurate information | Bad Link
Nick | 928.007 | Apollo/PHM | IIVP results | 1 | 1 | A-FP | 2018-01-22
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-22 | Inaccurate information
Nick | ePAS 16-33266 v12 | GS Reports | Project Plan | 1 |  | A | 2018-01-22
Nick | 345.004 | SAS | Test Protocol Results | 3 | 1 | A-FP | 2018-01-22 |  | Sas Micro Biasplot
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-22 | Inaccurate information
Nick | 589.05 | CMSNext | Software Compliance Assessment | 1 | 1 | A | 2018-01-23
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | D | 2018-01-23 | Inaccurate information
Nick | 1075.001 | DaVinci | URS | 2 | 1 | D | 2018-01-23 | Not compliant with procedure | Approver List
Nick | 1075.001 | DaVinci | Validation Plan | 1 | 1 | D | 2018-01-23 | Not compliant with procedure | Approver List
Nick | 354.004 | SAS | System Certification Summary | 1 | 1 | A-FP | 2018-01-23
Nick | ePAS 15-15617 V8 | GS Reports | Project Plan | 1 |  | A-FP | 2018-01-24
Nick | ePAS 18-1699 | Metrics Library | Design Documentation | 1 |  | A-FP | 2018-01-24 |  | source to target
Nick | ePAS 18-1700 | Metrics Library | Design Documentation | 1 |  | A-FP | 2018-01-24 |  | source to target
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | D | 2018-01-24 | Inaccurate information
Nick | 1075.001 | DaVinci | Project Plan | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | URS | 2 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | CII | 1 | 1 | D | 2018-01-24 | Not following document version control | not to release but to software.
Nick | ePAS 16-38941 V3 | GS Reports | Move to Production | 1 | 1 | A-FP | 2018-01-24
Nick | 1075.001 | DaVinci | Validation Plan | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | CII | 1 | 1 | A | 2018-01-24
Nick | 1075.001 | DaVinci | FRS | 2 | 1 | A | 2018-01-25
Nick | 1075.001 | DaVinci | CII | 1 | 1 | A | 2018-01-25
Nick | 1075.001 | DaVinci | IIVP | 1 | 1 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 1 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 2 | D | 2018-01-25 | Inaccurate information
Nick | 750.011 | AFMS | Test Protocol | 4 | 8 | D | 2018-01-25 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 2 | D | 2018-01-25 | Inaccurate information
Nick | 750.011 | AFMS | Test Protocol | 4 | 8 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 3 | D | 2018-01-25 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 2 | A | 2018-01-25
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 1 | A | 2018-01-25
Nick | 589.05 | CMSNext | Software Change Request | 1 | 1 | D | 2018-01-26 | Inaccurate information
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | A | 2018-01-26
Nick | 1075.001 | DaVinci | Test Protocol | 2 | 3 | A | 2018-01-26
Wayne | LC-S 00986.005 | PCN/SCN | IIVP | 1 | 1 | D | 2018-01-26 | Inaccurate information | No instruction to generate Objective Evidence
Wayne | LC-S 00986.005 | PCN/SCN | IIVP | 1 | 1 | A | 2018-01-26
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | D | 2018-01-19 | Inaccurate information | Disapproved 2nd time
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS 2.50 | A | 2018-01-19
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | D | 2018-01-19 | Inaccurate information | Disapproved 2nd time
Beilah | 01101.000 | QIMS | CII | 1 | Configuration Item Inventory for QIMS Report Manager 1.80 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | FRS | 9 | WWLIMS Bookshelf: Assay File Management | A | 2018-01-19 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-19 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPIT_R_11 | A | 2018-01-24 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | D | 2018-01-19 | Not following document version control
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | TCTCPLC_E_15 | A-FP | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_1 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_1 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_2 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_2 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_3 | D | 2018-01-19 |  | Formatting issues. Not content.
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCAFMARAD_3 | A | 2018-01-19
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | DT_ArchitectAssayDetail | A-FP | 2018-01-19
Beilah | 01090.000 | DPW | Test Protocol Results | 1 | Translation Workflow_Diagnostics.abbott_v2_Protocol | A-FP | 2018-01-19
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | D | 2018-01-22 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | A | 2018-01-24
Beilah | 01090.000 | WWLIMS | Traceability | 5 | For: DT_AFMARAD | A | 2018-01-25 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A | 2018-01-24 |  | Resubmitted for minor correction.
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLR_E_04: ADDULCD771510T | A | 2018-01-25 |  | Resubmitted for minor correction.
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Test Protocol TCTCPIT_E_05: ADDULCD771510T | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPLC_R_05 : ADDULCD772728L | A-FP | 2018-01-22
Beilah | 01094.001 | IRIS | IIVP results | 1 | Prod | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Test Protocol TCTCPLC_E_15: ADDULCD772728L | A-FP | 2018-01-22
Beilah | 01101.000 | QIMS | IIVP | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | A-FP | 2018-01-22
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | D | 2018-01-22 | Not compliant with procedure
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: v2.50 | A | 2018-01-22
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employee Valuation Testing: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employee Valuation Testing: v2.50 | A | 2018-01-25
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-24 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08557: v2.50 | D | 2018-01-25 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | D | 2018-01-22 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | D | 2018-01-24 | Insufficient testing
Beilah | 01101.000 | QIMS | Test Protocol | 1 | IPDR ADDQIMS08558: v2.50 | A | 2018-01-25
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employees Maintenance Regression Testing: v2.50 | D | 2018-01-22 |  | No req trace to review against.
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Employees Maintenance Regression Testing: v2.50 | D | 2018-01-25 | Inaccurate information
Beilah | 00303.099 | DFCS | Design Verification | 3 | Design Verification: Pick list | A-FP | 2018-01-22
Beilah | 01090.000 | WWLIMS | IIVP | 1 | IIVP- Instrument Server-v9.3 | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | CII | 4 | CII | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | IIVP | 4 | Install | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | User Acceptance Protocol results | 1 | UAT 01_Postponement Picklist Changes_Results - FAIL | A-FP | 2018-01-22
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 2 | UAT 01_Postponement Picklist Changes | D | 2018-01-23 | Not using template | template is okay just missing header.
Beilah | 00303.099 | DFCS | User Acceptance Protocol | 2 | UAT 01_Postponement Picklist Changes | A | 2018-01-23
Beilah | 00303.099 | DFCS | Test Protocol | 3 | Test Protocol_01_DFCS_PostponementOrders | A-FP | 2018-01-23
Beilah | 00303.099 | DFCS | Test Protocol Results | 3 | Test Protocol_01_DFCS_PostponementOrders_Results | D | 2018-01-24 | Inaccurate information
Beilah | 00303.099 | DFCS | Test Protocol Results | 3 | Test Protocol_01_DFCS_PostponementOrders_Results | A | 2018-01-24 |  | Failed test
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPIT_R_12 Result: ADDULCD771510T | A-FP | 2018-01-23
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit test - Instrument Server v9.3a | A-FP | 2018-01-23
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPINDT_14 Result: ADDULCD771510T | D | 2018-01-24 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol TCTCPINDT_14 Result: ADDULCD771510T | A | 2018-01-25
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Test Protocol TCTCPINDT_14 | A | 2018-01-25 |  | only for update purposes.
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Test Protocol TCTCPINDT_14 | A | 2018-01-25 |  | only for update purposes.
Beilah | 01090.000 | WWLIMS | Traceability | 16 | Traceability Matrix - TPTCPPRT | D | 2018-01-24 | Inaccurate information | This was approved once resubmitted and upon resubmittle has wrong header invofrrmation
Beilah | 01090.000 | WWLIMS | Traceability | 16 | Traceability Matrix - TPTCPPRT | A | 2018-01-24
Beilah | 01101.000 | QIMS | Traceability | 7 | FRS Section 2 Traceability Matrix (for QIMS 2.50) | D | 2018-01-24 | Inaccurate information
Beilah | 01101.000 | QIMS | Traceability | 7 | FRS Section 2 Traceability Matrix (for QIMS 2.50) | A | 2018-01-25
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3a | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_01 | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Traceability | 1 | Traceability Matrix - TPIDARCC | A-FP | 2018-01-25
Beilah | 01090.000 | WWLIMS | Traceability | 11 | Traceability Matrix - TPTCPINDT | A-FP | 2018-01-25
Beilah | 01090.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | D | 2018-01-25 | Inaccurate information
Liz | 01117.000 | ideaPoint | Software Compliance Assessment | 1 | 1 | A-FP | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol | 2 | Development Test Protocol | D | 2018-01-26 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol | 3 | Development Test Protocol | A | 2018-01-29
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCISVR_01 | A-FP | 2018-01-26
Beilah | 01090.000 | WWLIMS | Test Protocol | 4 | TCISVR_01 | A-FP | 2018-01-30 |  | resubmitted
Beilah | 01090.000 | WWLIMS | Traceability | 8 | Traceability Matrix - TPISVR | D | 2018-01-26 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Traceability | 8 | Traceability Matrix - TPISVR | A | 2018-01-29
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit Test - WorkStation v9.3b | A-FP | 2018-01-26
Beilah | 01101.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | D | 2018-01-26 | Other | Blank page
Beilah | 01101.000 | QIMS | Traceability | 5 | FRS Section 11 Traceability Matrix (for QIMS 2.50) | A | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | A | 2018-01-26
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | D | 2018-01-26 | Other | wrong document attached to NVP
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory-Workstation v9.3b | A-FP | 2018-01-26
Beilah | 01033.011 | Pulse | System Certification Summary | 1 | Certification Summary | A-FP | 2018-01-26
Beilah | 01090.000 | WWLIMS | Validation Plan | 3 | Val Plan | A-FP | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | D | 2018-01-26
Beilah | 01101.000 | QIMS | Test Protocol | 1 | Test Protocol 02 - IPDR ADDQIMS08557 | A | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 02 - IPDR ADDQIMS08557: failed | A-FP | 2018-02-01 |  | Failed step will be rerun
Beilah | 01101.000 | QIMS | Test Protocol | 2 | DT_ArchitectAssayDetail | A-FP | 2018-01-29
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation: ADDULCD771510T 9.3b | A-FP | 2018-01-29
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation: ADDULCD772728L 9.3b | A-FP | 2018-01-29
Beilah | 01033.011 | Pulse | IIVP results | 1 | Installation Instructions and Verification Protocol_Prod | A-FP | 2018-01-29
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | D | 2018-01-30 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 01 - Employee Valuation Testing | A | 2018-01-31
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | D | 2018-01-30 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 04 - Employees Maintenance Regression Testing | A | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol | 3 | DT_ArchitectAssayDetail | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass - Test Protocol DT_ArchitectAssayDetail Result: ADDULCD772728L | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol TCAFMARAD_2 Result: ADDULCD771510T | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | CII | 2 | Configuration Item Inventory - Instrument Server v9.3a | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCTCPPRT_19 | A | 2018-01-30 |  | Resubmitted
Beilah | 01033.013 | Pulse | Software Compliance Assessment | 6 | Release v15.0 | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 ADDULCL771783 9.3 | A-FP | 2018-01-30
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol TCAFMARAD_3 Result: ADDULCD772728L | A-FP | 2018-01-31
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 03 - IPDR ADDQIMS08558 | D | 2018-01-31 | Not compliant with procedure
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 03 - IPDR ADDQIMS08558 | A | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | Pass Test Protocol - TCAFMARAD_1 Result: ADDULCD772728L | A-FP | 2018-01-31
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | TCIDARCC_01 | A | 2018-01-31 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3 - Validation: ADDULCD878490T | A | 2018-02-01
Beilah | 01090.000 | WWLIMS | URS | 33 | WWLIMS User Requirements Specification | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | Traceability | 24 | WWLIMS Traceability Matrix | D | 2018-02-12 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol | 1 | TCIDARCC_02 | A | 2018-02-01 |  | Resubmitted
Beilah | 01101.000 | QIMS | Design Verification | 2 | Unit Testing Document for QIMS v2.50 | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | D | 2018-02-01 | Insufficient testing | missing screen prints
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | D | 2018-02-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPLR_R_11 Result: ADDULCD771510T | A | 2018-02-01
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Unit test - Instrument Server v9.3b | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3b | A-FP | 2018-02-01
Beilah | 01101.000 | QIMS | CII | 2 | Configuration Item Inventory for QIMS 2.50 | A-FP | 2018-02-01
Beilah | 01006.002 | Alinity Source Verifier | Software Compliance Assessment | 1 |  | A-FP | 2018-02-01 |  | Link to original SCA
Beilah | 01101.000 | QIMS | IIVP results | 2 | Quality Information Management System (QIMS) Version 2.50 – Manual Installation Instructions for 32 bit or 64 bit pc | A-FP | 2018-02-01
Beilah | 01006.002 | Alinity Source Verifier | Software Change Request | 1 |  | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TC_IPDR_ ADDWWLIMS08562_SLIGO Result: ADDULCD773047T | A-FP | 2018-02-01
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol - TC_IPDR_ ADDWWLIMS08562_LONGFORD Result: ADDULCD773047T | A-FP | 2018-02-01
Nick | 345.004 | SAS | Test Protocol | 1 | 1 | A-FP | 2018-01-25 |  | regplot micro
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 QA | A-FP | 2018-01-27
Nick | 589.05 | CMSNext | Software Change Request | 1 | 1 | D | 2018-01-29 | Not compliant with procedure
Nick | 1075.001 | DaVinci | ISSD | 1 | 1 | A-FP | 2018-01-29
Nick | 1075.001 | DaVinci | Test Protocol | 1 | 4 | A | 2018-01-29
Nick | 750.011 | AFMS | Test Protocol | 2 | 2 | A-FP | 2018-01-29
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 3 | D | 2018-01-29 | Other
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 3 | A | 2018-01-29
Nick | 581.024 | TODS | Software Change Request | 1 | 1 | D | 2018-01-29
Nick | 928.008 | Apollo/PHM | Software Compliance Assessment | 1 | 1 | D | 2018-01-30 | Other
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 1 | A-FP | 2018-01-30
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | D | 2018-01-30 | Inaccurate information
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | D | 2018-01-30 | Other
Nick | ePAS 18-1902 | Metrics Library | Validation Plan | 1 |  | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Traceability | 2 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | Test Protocol Results | 2 | 2 | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 4 | D | 2018-01-31 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | D | 2018-01-31 | Not compliant with procedure
Nick | 1075.001 | DaVinci | Test Protocol Results | 1 | 4 | A | 2018-01-31
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | D | 2018-01-31 | Other
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | D | 2018-01-31 | Inaccurate information
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | D | 2018-01-31 | Inaccurate information
Nick | 1075.001 | DaVinci | IDP | 1 | 1 | A | 2018-01-31
Nick | ePAS 17-4771 V11.0 | GS Reports | Move to Production | 1 | 1 | A-FP | 2018-01-31
Nick | 1075.001 | DaVinci | Release Notes | 1 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | System Certification Summary | 1 | 1 | A | 2018-01-31
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 prod | D | 2018-02-01 | Inaccurate information
Nick | ePAS 18-1699 | Metrics Library | Design Documentation | 1 |  | A | 2018-02-01
Nick | ePAS 18-1700 | Metrics Library | Design Documentation | 1 |  | A | 2018-02-01
Nick | ePAS 18-2537 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-01
Nick | ePAS 18-2538 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-01
Nick | 345.004 | SAS | System Certification Summary | 1 | 1 | A-FP | 2018-02-01 |  | regplot micro
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 3 | D | 2018-02-01 | Not compliant with procedure
Nick | 1075.001 | DaVinci | IIVP results | 1 | 1 prod | A | 2018-02-02
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 3 | A | 2018-02-02
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - validation | A-FP | 2018-02-02
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3 - validation: ADDULCD773047T | A-FP | 2018-02-02
Beilah | 01090.000 | WWLIMS | Test Protocol | 11 | Pass Test Protocol TCINT_05 Result: ADDULCD772827L | A-FP | 2018-02-02
Beilah | 01101.000 | QIMS | Test Protocol Results | 1 | Test Protocol 02 - IPDR ADDQIMS08557: GISULCV102537 | A-FP | 2018-02-02 |  | resubmitted
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3: ADDULCD706358T | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TC_IPDR_ ADDWWLIMS08562_SLIGO Result: ADDULCD773047T | A-FP | 2018-02-05 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol - TC_IPDR_ ADDWWLIMS08562_LONGFORD Result: ADDULCD773047T | A-FP | 2018-02-05 |  | Resubmitted
Beilah | 01006.002 | Alinity Source Verifier | Software Change Request | 1 |  | A-FP | 2018-02-05 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 7 | Pass - Test Protocol - TCARCH_05 - Result | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3b_Longford : ADDIE8D003096 | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3b_Longford : ADDIE8D003096 | A-FP | 2018-02-05 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3b_Longford: ADDIE8D003288 | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3b_Longford: ADDIE8D003288 | A-FP | 2018-02-05 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | URS | 33 | WWLIMS User Requirements Specification | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | Traceability | 24 | WWLIMS Traceability Matrix" Project Level | A | 2018-02-21
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - validation: ADDULCD771107L | A-FP | 2018-02-05
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Pass Test Protocol TCTCPIT_R_11 Result: ADDULCD773047T | D | 2018-02-05 | Other | The link in the folder is to the wrong protocol.
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 2 | Pass Test Protocol TCTCPIT_R_11 Result: ADDULCD773047T | A | 2018-02-05
Beilah | 01033.014 | Pulse | Software Compliance Assessment | 6 |  | A-FP | 2018-02-05 |  | Link approval to parent
Beilah | 01033.014 | Pulse | Test Protocol | 1 | DP_Filters_Protocol | D | 2018-02-06 | Insufficient testing | through email.
Beilah | 01033.015 | Pulse | Software Change Request | 1 |  | D | 2018-02-06 | Inaccurate information | through email.
Beilah | 01033.015 | Pulse | Software Change Request | 1 |  | A | 2018-02-08
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass Test Protocol TCTCPPRT_19 Result: ADDULCD772728L | A-FP | 2018-02-06
Beilah | 01033.014 | Pulse | Software Change Request | 1 |  | A-FP | 2018-02-06
Beilah | 01033.014 | Pulse | Software Change Request | 2 |  | A-FP | 2018-02-07
Beilah | 01033.014 | Pulse | Test Protocol Results | 1 | DP_Filters_Protocol | A | 2018-02-06
Beilah | 01033.014 | Pulse | Test Protocol Results | 1 | DP_Filters_Protocol | A-FP | 2018-02-08
Beilah | 01033.014 | Pulse | Traceability | 5 | URS/FRS to Test Protocol Trace_v5 | A-FP | 2018-02-07
Beilah | 01033.014 | Pulse | IIVP | 3 |  | A-FP | 2018-02-06 |  | approval of Link to parent
Beilah | 01033.014 | Pulse | IIVP results | 3 | install QA: a3161c8 | A-FP | 2018-02-08
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: ADDULCD771083 | A-FP | 2018-02-06
Beilah | 01101.000 | QIMS | IIVP results | 1 | Manual Installation Instructions for 32 bit or 64 bit pc: ADDULCD772995L, ADDULCL772586 | A-FP | 2018-02-06
Beilah | 00303.099 | DFCS | Design Verification | 4 | Picklist changes | A-FP | 2018-02-07
Beilah | 00303.099 | DFCS | CII | 5 | Picklist changes | D | 2018-02-07 | Inaccurate information
Beilah | 00303.099 | DFCS | CII | 5 | Picklist changes | A | 2018-02-07
Beilah | 00303.099 | DFCS | IIVP | 5 | Picklist changes | D | 2018-02-07 | Inaccurate information
Beilah | 00303.099 | DFCS | IIVP | 5 | Picklist changes | A | 2018-02-07
Beilah | 00849.009 | PEAR | Software Compliance Assessment | 5.0.1 |  | A-FP | 2018-02-07
Beilah | 0032.019 | EDMS | Software Compliance Assessment | 5.2.1 |  | A-FP | 2018-02-07
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Code Review - Instrument Server v9.3c | A-FP | 2018-02-07
Beilah | 01090.000 | WWLIMS | Design Verification | 1 | Design Verification - Unit Test - Instrument Server v9.3c | A-FP | 2018-02-07
Beilah | 01033.014 | Pulse | Design Verification | 1 | Unit test | A-FP | 2018-02-07
Beilah | 01033.014 | Pulse | CII | 1 |  | A-FP | 2018-02-07
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3c | A-FP | 2018-02-07
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3 - Validation: ADDULCD706358T | A-FP | 2018-02-07
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 8 | Pass - Test Protocol - TCIDPR_02 - Result | A-FP | 2018-02-12
Beilah | 01101.000 | QIMS | User Acceptance Protocol | 1 | User Acceptance Testing – Doc Authoring | A-FP | 2018-02-08
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3c -Validation: ADDULCD773047T | A-FP | 2018-02-08
Beilah | 01101.000 | QIMS | User Acceptance Protocol | 1 | User Acceptance Testing – Biochem | A-FP | 2018-02-08
Beilah | 01101.000 | QIMS | User Acceptance Protocol | 1 | User Acceptance Testing – Chem | A-FP | 2018-02-08
Beilah | 01101.000 | QIMS | User Acceptance Protocol | 1 | User Acceptance Testing – Micro | A-FP | 2018-02-08
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3c - Longford: ADDIE8D003288 | A-FP | 2018-02-08
Beilah | 01101.000 | QIMS | IIVP results | 1 | (QIMS) Version 2.50 – Manual Installation Instructions for 32 bit or 64 bit pc: ADDULCL772586 | A-FP | 2018-02-08
Beilah | 01033.013 | Pulse | IIVP | 3 |  | A | 2018-02-08 |  | link to parent
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 3 | Pass Test Protocol DT Instrument Server Result: ADDULCD771510T ADDULCD773047T | A-FP | 2018-02-08
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 7 | D | 2018-02-06 | Not compliant with procedure
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 7 | A | 2018-02-06
Nick | ePAS 18-2539 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-07
Nick | ePAS 18-3255 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-07
Nick | ePAS 18-2540 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-07
Nick | ePAS 18-2770 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-07
Nick | ePAS 18-2771 | Metrics Library | Test Protocol | 1 |  | A-FP | 2018-02-07
Nick | 581.024 | TODS | Software Change Request | 1 | 1 | A | 2018-02-08
Nick | 581.024 | TODS | Test Protocol | 1 | 1 | D | 2018-02-09 | Not compliant with procedure
Nick | 581.024 | TODS | Test Protocol | 1 | 2 | D | 2018-02-09 | Not compliant with procedure
Nick | 581.024 | TODS | Test Protocol | 1 | 1 | A | 2018-02-09
Nick | 581.024 | TODS | Test Protocol | 1 | 2 | A | 2018-02-09
Beilah | 01033.014 | Pulse | System Certification Summary | 1 |  | A-FP | 2018-02-09
Beilah | 01101.000 | QIMS | User Acceptance Protocol results | 1 | User Acceptance Testing – IQA | A-FP | 2018-02-09
Beilah | 01101.000 | QIMS | User Acceptance Protocol results | 1 | User Acceptance Testing – EM | A-FP | 2018-02-09
Beilah | 01006.002 | Alinity Source Verifier | Software Change Request | 1 |  | A | 2018-02-09 |  | resubmitted
Beilah | 01101.000 | QIMS | System Certification Summary | 1 |  | D | 2018-02-09
Beilah | 01101.000 | QIMS | System Certification Summary | 1 |  | A | 2018-02-09 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 8 | Pass - Test Protocol - TCIDPR_02 - Result | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | FRS | 3 | Functional Requirements Specification | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | Design Verification | 1 | Design Verification-Unit Testing | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | CII | 1 |  | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | IIVP | 1 |  | A-FP | 2018-02-12
Beilah | 00303.099 | DFCS | Test Protocol Results | 3 | DFCS_PostponementOrders_Results | A | 2018-02-12
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol - TCIDARCC_02 - Result: ADDIE8D003288 | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | Traceability | 3 | URS to FRS Trace | D | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | Traceability | 3 | URS to FRS Trace | A | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | Traceability | 3 | URS to FRS Trace | A | 2018-02-14 |  | Resubmitted
Beilah | 01006.002 | Alinity Source Verifier | Traceability | 3 | URS/FRS to Test Protocol Trace | A-FP | 2018-02-12
Beilah | 01006.002 | Alinity Source Verifier | Traceability | 3 | URS/FRS to Test Protocol Trace | A | 2018-02-13 |  | Resubmitted
Beilah | 00332.019 | EDMS | Software Compliance Assessment | 5.2.1 |  | A | 2018-02-12 |  | Resubmitted
Beilah | 00332.019 | EDMS | Software Change Request | 1 |  | A-FP | 2018-02-12
Beilah | 00332.019 | EDMS | Software Change Request | 1 |  | A | 2018-02-14 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | Traceability | 24 | WWLIMS Traceability Matrix | D | 2018-02-12 | Inaccurate information
Beilah | 01033.015 | Pulse | Test Protocol | 3 | My Instruments_v3_Protocol | A-FP | 2018-02-12 |  | Link approval to parent
Beilah | 01006.002 | Alinity Source Verifier | Test Protocol | 1 |  | D | 2018-02-12 | Inaccurate information
Beilah | 01006.002 | Alinity Source Verifier | Test Protocol | 1 |  | A | 2018-02-12
Beilah | 00849.009 | PEAR | Software Change Request | 1 |  | D | 2018-02-12 | Inaccurate information
Beilah | 00849.009 | PEAR | Software Change Request | 1 |  | A | 2018-02-13
Beilah | 00849.009 | PEAR | Software Change Request | 1 |  | A | 2018-02-14 |  | Resubmitted
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Workstation v9.3 | A-FP | 2018-02-14
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Instrument Server v9.3 | A-FP | 2018-02-14
Beilah | 01090.000 | WWLIMS | CII | 1 | Configuration Item Inventory - Supplemental Items v9.3 | A-FP | 2018-02-14
Beilah | 00303.099 | DFCS | IIVP results | 5 | Installation Instructions and Verification Protocol: LT063086 | A-FP | 2018-02-14
Beilah | 01033.014 | Pulse | IIVP results | 1 | Installation Instructions and Verification Protocol - Prod: 0d60429 | A-FP | 2018-02-14
Beilah | 01033.013 | Pulse | FRS | 11 | Customer Portal_v11 | A | 2018-02-15 |  | Resubmitted
Beilah | 01033.013 | Pulse | FRS | 4 | Distributor Portal_v4 | A-FP | 2018-02-15
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 4 | TCISVR_01 - Result: ADDULCD773047T | A-FP | 2018-02-15
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation ADDULCD772728l | A-FP | 2018-02-15
Beilah | 01101.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3 - Validation ADDULCD773047T | A-FP | 2018-02-15
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3)Validation ADDULCD771510T | A-FP | 2018-02-15
Beilah | 01033.013 | Pulse | Traceability | 41 | URS to FRS Trace - v41 | A-FP | 2018-02-15
Beilah | 01006.002 | Alinity Source Verifier | IIVP results | 1 | QA | A-FP | 2018-02-15
Wayne | 1073.000 | Groninger | IIVP | 1 |  | D | 2018-01-03 | Inaccurate information
Wayne | 01073.000 | Groninger | IIVP | 1 |  | A | 2018-01-03
Wayne | 01073.000 | Groninger | IIVP | 2 |  | A | 2018-01-04
Wayne | 00055.041 | eNovator | Traceability | 1 |  | A | 2018-01-12 |  | eNovator
Wayne | 00419.016 | Reliasoft Xfmea | Other | 1 |  | A-FP | 2018-01-13 |  | Other
Wayne | 01073.000 | Groninger | Test Protocol | 1 |  | D | 2018-01-03 | Inaccurate information
Wayne | 01073.000 | Groninger | Test Protocol | 1 |  | D | 2018-01-04 | Inaccurate information
Wayne | 01073.000 | Groninger | Test Protocol | 1 |  | A | 2018-01-09
Wayne | 01073.000 | Groninger | Traceability | 1 |  | A-FP | 2018-01-16
Wayne | 01073.000 | Groninger | Design Verification | 1 |  | A-FP | 2018-01-17
Wayne | 01104.000 | Assay File Database | Software Change Request | 1 |  | D | 2018-01-17 | Not compliant with procedure
Wayne | 01104.000 | Assay File Database | Software Change Request | 1 |  | A | 2018-01-17
Wayne | 00986.005 | PCN/SCN | Software Compliance Assessment | 1 |  | D | 2018-01-18 | Inaccurate information
Wayne | 00986.005 | PCN/SCN | Software Compliance Assessment | 1 |  | A | 2018-01-22
Wayne | 00986.005 | PCN/SCN | Software Change Request | 1 |  | D | 2018-01-23 | Incorrect scope
Wayne | 00986.005 | PCN/SCN | Software Change Request | 1 |  | A | 2018-01-24
Wayne | 01073.000 | Groninger | CII | 1 |  | D | 2018-01-17 | Not compliant with procedure
Wayne | 01073.000 | Groninger | CII | 1 |  | D | 2018-01-18 | Not compliant with procedure
Wayne | 01073.000 | Groninger | CII | 1 |  | A | 2018-01-19
Wayne | 00986.005 | PCN/SCN | CII | 1 |  | A-FP | 2018-02-05
Wayne | 00986.005 | PCN/SCN | Design Verification | 1 |  | A-FP | 2018-01-26
Wayne | 01073.000 | Groninger | CII | 1 |  | A-FP | 2018-02-05
Wayne | 01073.000 | Groninger | Design Verification | 1 |  | A-FP | 2018-02-05
Wayne | 00986.005 | PCN/SCN | FRS | 1 |  | A-FP | 2018-01-25
Wayne | 00986.005 | PCN/SCN | IIVP | 1 |  | D | 2018-01-26 | Not compliant with procedure
Wayne | 00986.005 | PCN/SCN | IIVP | 1 |  | A | 2018-01-26
Wayne | 01073.000 | Groninger | IDP | 1 |  | A-FP | 2018-02-06 |  | Deployment Plan
Wayne | 00986.005 | PCN/SCN | Test Protocol | 1 |  | A-FP | 2018-02-05
Wayne | 01115.000 | DARA Filler DHM and RU | Software Compliance Assessment | 1 |  | A-FP | 2018-02-08 |  | DARA Filler DHM and RU
Wayne | 01115.000 | DARA Filler DHM and RU | ERES | 1 |  | A-FP | 2018-02-09 |  | DARA Filler DHM and RU and eSig eRec
Wayne | 00986.005 | PCN/SCN | Test Protocol Results | 1 |  | D | 2018-02-09 | Not using template
Wayne | 01115.000 | DARA Filler DHM and RU | Software Change Request | 1 |  | A-FP | 2018-02-08 |  | DARA Filler DHM and RU
Wayne | 00986.005 | PCN/SCN | Traceability | 1 |  | D | 2018-02-09 | Not compliant with procedure
Wayne | 00986.000 | PCN/SCN | Traceability | 1 |  | A | 2018-02-13
Wayne | 00986.005 | PCN/SCN | IIVP results | 1 |  | D | 2018-02-07 | Not compliant with procedure
Wayne | 00953.000 | BioCommand Batch Control Plus | IIVP results | 1 |  | A | 2018-02-15 |  | BioCommand Batch Control Plus
Wayne | 01115.000 | DARA Filler DHM and RU | Validation Plan | 1 |  | A-FP | 2018-02-15 |  | DARA Filler DHM and RU
Wayne | 01115.000 | DARA Filler DHM and RU | Project Plan | 1 |  | A-FP | 2018-02-15 |  | DARA Filler DHM and RU
Wayne | 00986.005 | PCN/SCN | System Certification Summary | 1 |  | D | 2018-02-14 | Inaccurate information
Wayne | 00986.005 | PCN/SCN | System Certification Summary | 1 |  | A | 2018-02-15
Wayne | 00986.005 | PCN/SCN | IIVP results | 1 | Prod | A-FP | 2018-02-19
Nick | 589.05 | CMSNext | Test Protocol | 1 | 1 | A-FP | 2018-02-12
Nick | 589.05 | CMSNext | Test Protocol | 1 | 2 | A-FP | 2018-02-12
Nick | 589.05 | CMSNext | Test Protocol | 1 | 3 | A-FP | 2018-02-12
Nick | 750.011 | AFMS | Test Protocol Results | 4 | 8 | D | 2018-02-12
Nick | 750.011 | AFMS | Test Protocol Results | 1 | 6 | A-FP | 2018-02-12
Nick | 589.05 | CMSNext | Test Protocol | 1 | 4 | A-FP | 2018-02-12
Nick | 750.011 | AFMS | IIVP results | 1 | 1 QA - 3rd build | D | 2018-02-12 | Not compliant with procedure
Nick | 589.05 | CMSNext | Test Protocol | 1 | 5 | A-FP | 2018-02-12
Nick | 589.05 | CMSNext | Test Protocol | 1 | 6 | A-FP | 2018-02-12
Nick | ePAS 18-4461 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-13
Nick | ePAS 18-4462 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-13
Nick | ePAS 18-4818 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-13
Nick | ePAS 18-4820 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-13
Nick | 750.011 | AFMS | Traceability | 9 | 1 | D | 2018-02-14 | Insufficient traceability
Nick | 750.011 | AFMS | CII | 10 | 1 | A-FP | 2018-02-14
Nick | 750.011 | AFMS | Test Protocol | 2 | 1 | A-FP | 2018-02-14
Nick | 928.008 | Apollo/PHM | Software Change Request | 1 | 1 | A | 2018-02-14
Nick | 928.008 | Apollo/PHM | Test Protocol | 1 | 1 | A-FP | 2018-02-14
Nick | 750.011 | AFMS | Test Protocol | 3 | 3 | A-FP | 2018-02-15
Nick | 750.011 | AFMS | Test Protocol | 2 | 6 | A-FP | 2018-02-15
Nick | 750.011 | AFMS | Test Protocol | 3 | 7 | A-FP | 2018-02-15
Nick | ePAS 18-4976 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-16
Nick | ePAS 18-4977 | Metrics Library | Test Protocol Results | 1 |  | A-FP | 2018-02-16
NIck | 750.011 | AFMS | IIVP results | 1 | 1 QA - 3rd build | A | 2018-02-16
Nick | 750.011 | AFMS | Test Protocol | 5 | 8 | A-FP | 2018-02-19
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3: ADDULCD773400 | A-FP | 2018-02-19
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass - Test Protocol - TCIDARCC_01 - Result: ADDULCD773400 | D | 2018-02-19 | Inaccurate information
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 1 | Pass - Test Protocol - TCIDARCC_01 - Result: ADDULCD773400 | A | 2018-02-20
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 10 | Pass Test Protocol TCREG_04 Result: ADDULCD772728L | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Software Change Request | 1 |  | A | 2018-02-19 |  | resubmitted
Beilah | 01033.013 | Pulse | Software Change Request | 1 |  | A | 2018-02-21 |  | Resubmitted
Beilah | 01033.013 | Pulse | Software Change Request | 1 |  | A | 2018-02-22
Beilah | 01033.013 | Pulse | Test Protocol | 1 | DP_Download_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 3 | Distributor Portal Instructions for Use_v3 Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 1 | DP_Multiple Download_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 1 | DP_Multiple Download_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Distributor Portal Assay Files OUS_v2_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Distributor Portal Assay Files OUS_v2_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 1 | DP_Download_Protocol: 01037 | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 1 | DP_Download_Protocol: 01037 | A-FP | 2018-02-19 |  | link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 2 | DP_Download_Protocol v2: 01037 | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 2 | DP_Download_Protocol v2: 01037 | A | 2018-02-19 |  | resubmitted
Beilah | 01033.013 | Pulse | Test Protocol | 2 | DP_Download_Protocol v2: 01037 | A-FP | 2018-02-19 |  | link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 3 | Distributor Portal Instructions for Use_v3 Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 3 | Distributor Portal Instructions for Use_v3 Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 1 | CP_Multiple Download_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 1 | CP_Multiple Download_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 3 | OUS Emp TL_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 3 | OUS Emp TL_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Q Tech_Assay File_OUS_v2_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Q Tech_Assay File_OUS_v2_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 4 | Instructions for Use_Protocol_v4 | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 4 | Instructions for Use_Protocol_v4 | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 3 | Product Requirements_Protocol | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 3 | Product Requirements_Protocol | A-FP | 2018-02-19 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 3 | DL_Download_Protocol 01036 | A-FP | 2018-02-19
Beilah | 01033.013 | Pulse | Test Protocol | 3 | DL_Download_Protocol | A-FP | 2018-02-19 |  | link to parent
Beilah | 01033.013 | Pulse | Traceability | 3 | URS/FRS to Test Protocol Trace_v3 | A-FP | 2018-02-19
Beilah | 01006.002 | Alinity Source Verifier | Test Protocol | 2 |  | A-FP | 2018-02-19
Beilah | 01006.002 | Alinity Source Verifier | Test Protocol Results | 2 |  | D | 2018-02-19 | Inaccurate information
Beilah | 01006.002 | Alinity Source Verifier | Test Protocol Results | 2 |  | A | 2018-02-19
Beilah | 00303.099 | DFCS | User Acceptance Protocol results | 2 | UAT 01_Postponement Picklist Changes_Results - PASS | D | 2018-02-19 | Inaccurate information
Beilah | 00303.099 | DFCS | User Acceptance Protocol results | 2 | UAT 01_Postponement Picklist Changes_Results - PASS | A | 2018-02-20
Beilah | 01090.000 | WWLIMS | Test Protocol Results | 11 | Pass Test Protocol TCINT_05 Result: 9.3 | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 1: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 2: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 3: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 4: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 5: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 6: Longford | A-FP | 2018-02-20
Beilah | 01090.000 | WWLIMS | User Acceptance Protocol results | 1 | Pass - Test Protocol - User Acceptance Testing - Protocol 7: Longford | A-FP | 2018-02-20
Beilah | 00303.099 | DFCS | User Acceptance Protocol results | 1 | UAT 02_ Regression_Results - PASS | A-FP | 2018-02-20 |  | Resubmitted
Beilah | 01006.002 | Alinity Source Verifier | Release Notes | 1 |  | A-FP | 2018-02-20
Beilah | 01006.002 | Alinity Source Verifier | System Certification Summary | 1 |  | A-FP | 2018-02-20
Beilah | 00303.099 | DFCS | Release Notes | 1 |  | A-FP | 2018-02-21
Beilah | 01090.000 | WWLIMS | Traceability | 24 | WWLIMS Traceability Matrix | A | 2018-02-21
Beilah | 01107.000 | WWLIMS | Software Change Request | 4 |  | D | 2018-02-21 | Inaccurate information
Beilah | 01107.000 | WWLIMS | Software Change Request | 4 |  | A | 2018-02-21
Beilah | 01033.013 | Pulse | Traceability | 11 | 01038.000 parent | A-FP | 2018-02-21
Beilah | 01033.013 | Pulse | Traceability | 6 | 01037.000 parent | A-FP | 2018-02-21
Beilah | 01033.013 | Pulse | Traceability | 7 | 01036 parent | A-FP | 2018-02-21
Beilah | 00303.099 | DFCS | System Certification Summary | 1 |  | D | 2018-02-21 | Inaccurate information
Beilah | 00303.099 | DFCS | System Certification Summary | 1 |  | A | 2018-02-21
Beilah | 01006.002 | Alinity Source Verifier | IIVP results | 1 | Prod | A-FP | 2018-02-22
Beilah | 01090.000 | WWLIMS | System Certification Summary | 1 |  | D | 2018-02-22 | Inaccurate information
Beilah | 01090.000 | WWLIMS | System Certification Summary | 1 |  | A | 2018-02-22
Nick | 750.011 | AFMS | User Acceptance Protocol | 5 | 8 | A-FP | 2018-02-19
Nick | ePAS 18-5565 | GS Reports | Project Plan | 1 |  | A-FP | 2018-02-20
Nick | 928.008 | Apollo/PHM | Test Protocol Results | 1 | 1 | D | 2018-02-20 | Not compliant with procedure | Missing signature
Nick | 589.05 | CMSNext | Test Protocol | 1 | 7 | A-FP | 2018-02-20
Nick | 589.05 | CMSNext | Test Protocol | 1 | 6 | A | 2018-02-20
Nick | ePAS 18-5706 | GS Reports | Project Plan | 1 |  | A-FP | 2018-02-20
Nick | 581.024 | TODS | Software Change Request | 2 | 1 | A-FP | 2018-02-20
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 1 | A-FP | 2018-02-21
Nick | 750.011 | AFMS | User Acceptance Protocol results | 5 | 8 | A-FP | 2018-02-21
Nick | 928.008 | Apollo/PHM | Test Protocol Results | 1 | 1 | A | 2018-02-21
Nick | 750.011 | AFMS | Traceability | 9 | 1 | A | 2018-02-21
Nick | ePAS 18-5882 | Metrics Library | System Certification Summary | 1 |  | A-FP | 2018-02-22
Nick | 750.011 | AFMS | Test Protocol | 3 | 1 | A-FP | 2018-02-22
Nick | 928.008 | Apollo/PHM | System Certification Summary | 1 | 1 | D | 2018-02-22 | Inaccurate information
Nick | 928.008 | Apollo/PHM | System Certification Summary | 1 | 1 | A | 2018-02-22
Nick | 750.011 | AFMS | Test Protocol Results | 2 | 2 | A-FP | 2018-02-22
Nick | 581.024 | TODS | Test Protocol Results | 1 | 1 | A-FP | 2018-02-22
Nick | 581.024 | TODS | Test Protocol Results | 1 | 2 | D | 2018-02-22 | Not compliant with procedure
Nick | 581.024 | TODS | Test Protocol Results | 1 | 2 | A | 2018-02-23
Nick | 750.011 | AFMS | Test Protocol | 3 | 2 | A-FP | 2018-02-23
Nick | 750.011 | AFMS | ISSD | 1 | 1 | D | 2018-02-23 | Inaccurate information
Nick | 750.011 | AFMS | IDP | 1 | 1 | A | 2018-02-23
Nick | 496.019 | Navigator | Cancellation | 1 | 1 | A-FP | 2018-02-23
Nick | 750.011 | AFMS | ISSD | 1 | 1 | D | 2018-02-23 | Inaccurate information
Nick | 686.024 | Navigator | Cancellation | 1 | 1 | A-FP | 2018-02-23
Nick | 750.011 | AFMS | System Certification Summary | 1 | 1 | D | 2018-02-23 | Inaccurate information
Nick | 750.011 | AFMS | ISSD | 1 | 1 | A | 2018-02-23
Nick | 750.011 | AFMS | System Certification Summary | 1 | 1 | A | 2018-02-23
Wayne | 1104.000 | Assay File Database | Project Plan | 1 |  | D | 2018-02-24 | Not compliant with procedure
Wayne | 055.041 | eNovator | ISSD | 1 |  | D | 2018-02-20 | Not compliant with procedure
Wayne | 936.000 | TrendReader | IIVP | 2 |  | A-FP | 2018-02-19
Wayne | 936.000 | TrendReader | IIVP results | 1 |  | A-FP | 2018-02-23
Beilah | 01033.013 | Pulse | Test Protocol | 4 | Operations Manuals_OUS_Protocol - v4 | A-FP | 2018-02-23 |  | Link to parent
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Q Tech Distributor Portal Operations Manuals OUS_v2 | A-FP | 2018-02-23 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - SligoDB Migration testing | D | 2018-02-23 | Insufficient testing
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - SligoDB Migration validation testing: ADDIE6D006303L | A | 2018-02-26
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - SligoDB Migration validation testing: ADDULCD772728L | A-FP | 2018-02-26
Beilah | 01033.013 | Pulse | Software Change Request | 2 | Software Change Request_v2 | A-FP | 2018-02-26
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Installation Instructions and Verification Protocol- Instrument Server-v9.3: ADDULCD706358T | A-FP | 2018-02-26
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Installation Instructions and Verification Protocol - WWLIMS Supplemental Items v9.3: ADDULCD878490T | A-FP | 2018-02-26
Beilah | 01033.013 | Pulse | Design Verification | 1 |  | A-FP | 2018-02-26
Beilah | 01033.013 | Pulse | CII | 1 |  | A-FP | 2018-02-26
Beilah | 01107.000 | WWLIMS | IIVP results | 1 | Installation Instructions and Verification Protocol - Instrument Manager Service- v9.21 - Sligo DB Migration: Addulcd772228 | A-FP | 2018-02-26
Beilah | 01107.000 | WWLIMS | IIVP results | 1 | Installation Instructions and Verification Protocol - Task Items: ABTAPA3290 (sligo) | A-FP | 2018-02-26
Beilah | 01107.000 | WWLIMS | User Acceptance Protocol results | 1 | Test Protocol - Task Items Test Protocol - SLG Validation ABTAPA3290 | A-FP | 2018-02-26
Beilah | 01107.000 | WWLIMS | Test Protocol Results | 1 | Test Protocol - Instrument Server Test Protocol ADDULCD706358T (sligo) | A-FP | 2018-02-26
Beilah | 01107.000 | WWLIMS | Test Protocol Results | 11 | Test Protocol - TCINT_05 ADDIE6D006303L )Sligo) | A-FP | 2018-02-26
Beilah | 01033.013 | Pulse | Test Protocol | 2 | Q Tech Distributor Portal Operations Manuals OUS_v2 | A-FP | 2018-02-26 |  | link to parent
Beilah | 01033.013 | Pulse | Traceability | 12 | URS/FRS to Test Protocol Trace - v12 01038 | A-FP | 2018-02-26
Beilah | 01033.013 | Pulse | Traceability | 7 | URS/FRS to Test Protocol Trace - v12 01037 | A-FP | 2018-02-26
Beilah | 00303.099 | DFCS | IIVP results | 5 | Installation Instructions and verification Protocol – Prod | A-FP | 2018-02-27
Beilah | 01107.000 | WWLIMS | Test Protocol Results | 1.1 | Test Protocol - IMS Test Protocol_Sligo DB Migration | A-FP | 2018-02-27
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS Supplemental Items v9.3: Prod ADDULCD896266 | A-FP | 2018-02-28
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - LC Prod Multi computers | A-FP | 2018-02-28
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | Instrument Server-v9.3 prod multi computers | A-FP | 2018-02-28
Beilah | 00332.019 | EDMS | Design Verification | 1 | EDMS-Satish Unit Testing | A-FP | 2018-02-28
Beilah | 00849.009 | PEAR | Design Verification | 1 | Design Verification Sravani Unit Testing | A-FP | 2018-02-28
Beilah | 01033.013 | Pulse | IIVP results | 1 | Installation Instructions and Verification Protocol_Val: e4b6d81 | A-FP | 2018-02-28
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - LC Prod | D | 2018-03-01 | Inaccurate information
Beilah | 01090.000 | WWLIMS | IIVP results | 1 | WWLIMS WorkStation v9.3 - LC Prod | A | 2018-03-01
Beilah | 01033.013 | Pulse | Test Protocol Results | 4 | Hospital Dashboard_Protocol_v4 | A-FP | 2018-03-01
Beilah | 01033.013 | Pulse | Test Protocol Results | 1 | OUS Emp TL_Protocol | A-FP | 2018-03-01
Nick | ePAS 18-4636 | Metrics Library | Project Plan | 1 |  | A-FP | 2018-02-26
Nick | ePAS 14-8099 V8.0 | GS Reports | Project Plan | 1 |  | A-FP | 2018-02-27
Nick | 589.05 | CMSNext | Test Protocol | 1 | 8 | D | 2018-03-01 | Insufficient traceability
Nick | 589.05 | CMSNext | Test Protocol | 1 | 8 | A | 2018-03-01
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 8 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 6 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 5 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 4 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 3 | A-FP | 2018-03-02
Nick | ePAS 17-39843 v2 | GS Reports | Move to Production | 1 |  | A-FP | 2018-03-02
Nick | ePAS 18-6950 V1 | GS Reports | Move to Production | 1 |  | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 1 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 2 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Test Protocol Results | 1 | 7 | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | Release Notes | 1 | 1 | D | 2018-03-02 | Inaccurate information
Nick | 589.05 | CMSNext | Release Notes | 1 | 1 | D | 2018-03-02 | Inaccurate information
Nick | 589.05 | CMSNext | System Certification Summary | 1 | 1 | D | 2018-03-02 | Inaccurate information
Nick | 589.05 | CMSNext | Release Notes | 1 | 1 | A | 2018-03-02
Nick | ePAS 18-5711 V1 | GS Reports | Move to Production | 1 |  | A-FP | 2018-03-02
Nick | 589.05 | CMSNext | System Certification Summary | 1 | 1 | A | 2018-03-02

## SQA
Beilah
Liz
Nick
Wayne

## Application
Application
123 Compliance
Abbott Transfusion Medicine
ADD Shop Floor Paper (SFP) Report System
AFMS
Alinity Source Verifier
ALMS
Apollo/PHM
Artifactory
ASAP
Assay File Database
BioCommand Batch Control Plus
BitBucket
Clinical Trials DB (CTD)
ClinPlus CTMS
CMSNext
Commercial Affiliate eSMF
DARA Filler DHM and RU
DARA Filler DHM and RU
DaVinci
DFCS
DPW
EDMS
E-labeling Web Package Insert Retrieval
eNovator
EP Evaluator
GDSN/GS1
Groninger
GS Reports
ICQ Filler Data Collection
ideaPoint
IRIS
JAMA
Knowledge Management
Metrics Library
MSS
Navigator
PCN/SCN
PEAR
PRISM Metrics
PSA
Pulse
QIMS
Reliasoft Xfmea
RSLMS
SAS
TODS
TrendReader
WWLIMS

## Deliverable Types
Cancellation
CII
Data Migration Plan
Data Privacy Plan
Design Documentation
Design Verification
ERES
FRS
IDP
IIVP
IIVP results
ISSD
Maintenance Plan
Move to Production
Other
Project Plan
Release Notes
Software Change Request
Software Compliance Assessment
System Certification Summary
Test Protocol
Test Protocol Results
Traceability
URS
URS/FRS
User Acceptance Protocol
User Acceptance Protocol results
Validation Plan

## Reasons for Disapproval
Inaccurate information
Incorrect scope
Insufficient testing
Insufficient traceability
N/A
Not compliant with procedure
Not following configuration management
Not following document version control
Not using template
Other
Requirement deficiency

## A or D
A
D
A-FP