## Config
SQA | Application | Deliverable Types | Reasons for Disapproval | A or D
Harald | ADOC | CII | Inaccurate information | A
Philip | AFIL | DD1 | Inadequate Description of Change | A-FP
| AMPS2G | DD2 | Incorrect Approvers | D
| ASC | DD3 | Incorrect Objective Evidence
| CMSN-Add-On | DPP | Incorrect scope
| Fabiola | DR | Insufficient testing
| IRR | DV-CR | Insufficient traceability
| ITS | DV-UT | Multiple Errors
| JAM | ESRA | N/A
| LIC | FRS | Not compliant with procedure
| LSP | IA | Not following configuration management
| MFCS | IDP | Not following document version control
| POD | IDP/IIVP | Not using template
| Q-EDI | IIVP | Other
| SFP | ISSD | Requirement deficiency
| SPOC | IVR
| Teklynx | MCP
| Turnover | MP
| Unicorn | RA
| viewLinc | RN
| WWLIMS | SAD
| XIAM | SCA
SCR
SCS
SCS/RN
SDP
SDR
SE
SPP
SPR
SPVP
SVP
TM-DD to Code
TM-FRS to DD
TM-FRS to TP
TM-URS to FRS
TM-URS/FRS to TP
TP
TPR
URS
URS/FRS
URS/TM
URS/FRS/TM

## ACR
SQA | Application | ACR # | Date of CR Approval or Disapproval | CR Approve or Disapprove? | ACR I&E # | Date of I&E Approval or Disapproval | I&E Approve or Disapprove? | Reason for Disapproval | Comments

## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-06 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-10 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-10 | Multiple Errors
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-14 | Inaccurate information
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-15 | Multiple Errors
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | D | 2020-01-16 | Inaccurate information
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-17 | Inaccurate information | Mismatch of documentation impact vs. reality
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | D | 2020-01-17 | Inaccurate information | Schedule summary out of date
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | D | 2020-01-17 | Multiple Errors | Revision history incomplete, tracing incorrect
Harald | Release 3.1 | MFCS | CII | 1 | N/A | D | 2020-01-17 | Inaccurate information
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-17 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-17 | Multiple Errors
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | D | 2020-01-20 | Inaccurate information | Test execution planning incorrect
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | D | 2020-01-20 | Inaccurate information | Revision history incorrect, table name duplicate
Harald | Release 3.1 | MFCS | TP | 1 | N/A | D | 2020-01-20 | Multiple Errors
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | D | 2020-01-20 | Multiple Errors
Philip | Release 02.21.00 | ADOC | DV-UT | 1 | Incoming | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | IA | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | IDP/IIVP | 1 | N/A | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | SPVP | 1 | N/A | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 2 | TP60 | A-FP | 2020-01-21
Philip | Release 02.21.00 | ADOC | TP | 10 | TP53 | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | URS/FRS/TM | 15 | Incoming | A | 2020-01-21
Philip | Release 02.21.00 | ADOC | CII | 1 | N/A | A-FP | 2020-01-22
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | D | 2020-01-22 | Inaccurate information | Signature entry missing for post-turnover steps
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER400 | A | 2020-01-22
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | D | 2020-01-22 | Inaccurate information | Impact analysis insufficient
Philip | Release 01.05.00 | LIC | SPR | 1 | A2000006 | A | 2020-01-22
Harald | Release 3.1 | MFCS | IDP/IIVP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | TP | 1 | N/A | A | 2020-01-22
Harald | Release 3.1 | MFCS | URS/TM | 1 | N/A | A | 2020-01-22
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | D | 2020-01-23 | Inaccurate information | Test execution analysis missing
Philip | Release 02.21.00 | ADOC | SCS/RN | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP60 | A-FP | 2020-01-23
Philip | Release 02.21.00 | ADOC | TPR | 1 | TP53 | A-FP | 2020-01-23
Harald | Release 3.1 | MFCS | CII | 1 | N/A | A | 2020-01-23
Philip | Release 02.21.00 | ADOC | IVR | 1 | GER42 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SCR | 1 | A1900137 | A-FP | 2020-01-27
Philip | Release 02.21.00 | ADOC | SPR | 1 | A2000003 | A-FP | 2020-01-27
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-27 | Inaccurate information
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-27 | Multiple Errors
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-29 | Other | Needs to include related upcoming ADOC release
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | D | 2020-01-29 | Inaccurate information | Printer exchange, several explanations missing
Philip | Release 4.0.0 | POD | IVR | 1 | N/A | A | 2020-01-29 |  | Printer exchange
Philip | Release 02.21.01 | ADOC | SPR | 1 | A2000010 | A-FP | 2020-01-30
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-30 | Inaccurate information | Tailoring justifications missing, deliverables missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | D | 2020-01-30 | Other | Dependencies between LIC & ADOC releases missing
Philip | Release 01.05.00 | LIC | SPVP | 1 | N/A | A | 2020-01-30
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | D | 2020-01-30 | Inaccurate information | Traceability information incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | D | 2020-01-31 | Inaccurate information | Several references incorrect
Philip | Release 02.21.01 | ADOC | TP | 2 | TP68 | A | 2020-01-31
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | D | 2020-01-31 | Inaccurate information | Constraints missing
Philip | Release 02.21.01 | ADOC | URS/FRS/TM | 16 | Incoming | A | 2020-01-31
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | D | 2020-01-31 | Inaccurate information | Action missing for newly added objects
Philip | Release 01.05.00 | LIC | IA | 1 | N/A | A | 2020-01-31
Philip | Release 01.05.00 | LIC | TP | 1 | TP07 | A-FP | 2020-01-31
Philip | Release 01.05.00 | LIC | URS/FRS/TM | 8 | N/A | A | 2020-01-31
Philip | Release 01.00.02 | IRR | IA | 1 | N/A | D | 2020-02-03 | Inaccurate information | Documentation impact analysis incomplete
Philip | Release 01.05.00 | LIC | DV-UT | 1 | N/A | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000002 | A-FP | 2020-02-03
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000003 | A-FP | 2020-02-03
Philip | Release 01.06.00 | ASC | DV-UT | 1 | N/A | A-FP | 2020-02-04
Philip | Release 01.06.00 | ASC | IDP/IIVP | 1 | N/A | D | 2020-02-04 | Inaccurate information | Backup plan not correctly specified
Philip | Release 01.00.02 | IRR | CII | 1 | N/A | D | 2020-02-04 | Inaccurate information | Build information incorrect
Philip | Release 01.00.02 | IRR | CII | 1 | N/A | A | 2020-02-04
Philip | Release 01.00.02 | IRR | IA | 1 | N/A | A | 2020-02-04
Philip | Release 01.00.02 | IRR | SPR | 1 | A1900123 | A-FP | 2020-02-04
Philip | Release 01.00.02 | IRR | SPVP | 1 | N/A | A | 2020-02-04
Philip | Release v33.28.0 | SFP | SCR | 1 | M2000004 | A-FP | 2020-02-05
Harald | Release 3.1 | MFCS | MP | 1 | N/A | D | 2020-02-06 | Inaccurate information
Philip | Release 3.1 | MFCS | TP | 2 | N/A | D | 2020-02-06 | Multiple Errors | Revision history incorrect, information missing, steps incorrect
Philip | Release 3.1 | MFCS | TP | 2 | N/A | D | 2020-02-06 | Inaccurate information | Revision history incomplete
Philip | Release 3.1 | MFCS | TP | 2 | N/A | A | 2020-02-06
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | D | 2020-02-06 | Inaccurate information | Revision history incomplete
Philip | Release 3.1 | MFCS | URS/TM | 2 | N/A | A | 2020-02-06
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | D | 2020-02-06 | Multiple Errors | Build information incorrect, config file missing, form changes incorrect
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | D | 2020-02-06 | Inaccurate information | Build information incorrect
Philip | Release v33.28.0 | SFP | CII | 32 | N/A | A | 2020-02-06
Philip | Release v33.28.0 | SFP | IDP/IIVP | 1 | N/A | A-FP | 2020-02-06
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect, changes incorrect
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | D | 2020-02-06 | Multiple Errors | Traceability information incorrect, revision history incorrect, changes incorrect
Philip | Release v33.28.0 | SFP | URS/FRS/TM | 45 | N/A | A | 2020-02-06
Philip | Release 01.05.00 | LIC | IDP/IIVP | 1 | N/A | A-FP | 2020-02-10
Harald | Release 02.21.01 | ADOC | CII | 1 | N/A | A-FP | 2020-02-12
Harald | Release 01.05.00 | LIC | CII | 1 | N/A | A-FP | 2020-02-12
Harald | Release 01.05.00 | LIC | IVR | 1 | N/A | D | 2020-02-12 | Inaccurate information | Software Version (replaced/installed) incorrect
Harald | Release 01.05.00 | LIC | IVR | 1 | N/A | A | 2020-02-12
Harald | Release 02.21.01 | ADOC | TPR | 1 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | IA | 2 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | TPR | 1 | N/A | A-FP | 2020-02-13
Harald | Release 01.05.00 | LIC | IA | 2 | N/A | A-FP | 2020-02-14
Harald | Release 01.05.00 | LIC | IDP/IIVP | 2 | N/A | A-FP | 2020-02-14
Harald | Release 01.05.00 | LIC | SCS/RN | 1 | N/A | A-FP | 2020-02-14
Harald | Release 33.28.0 | SFP | IVR | 1 | N/A | A-FP | 2020-02-14
Harald | Release 33.28.0 | SFP | TPR | 3 | N/A | D | 2020-02-14 | Inaccurate information | Date typo
Harald | Release 33.28.0 | SFP | TPR | 3 | N/A | A | 2020-02-14
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | D | 2020-02-18 | Multiple Errors | Approvers incorrect, tailoring incomplete
Harald | Release 01.05.00 | LIC | IVR | 2 | N/A | A-FP | 2020-02-18
Harald | Release 3.1 | MFCS | TP | 3 | N/A | D | 2020-02-18 | Multiple Errors | Revision history incorrect, inaccurate information
Harald | Release 3.1 | MFCS | TPR | 2 | N/A | D | 2020-02-18 | Multiple Errors | missing entry
Harald | Release 3.1 | MFCS | TP | 3 | N/A | A | 2020-02-19
Harald | Release 3.1 | MFCS | TPR | 2 | N/A | A | 2020-02-19
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | D | 2020-02-20 | Multiple Errors | Documentation impact analysis incomplete, SPR reference incorrect, tailoring incorrect
Philip | Release 01.09.03 | ITS | IA | 1 | N/A | A | 2020-02-20
Philip | Release 01.09.03 | ITS | SPVP | 1 | N/A | D | 2020-02-20 | Multiple Errors | Approvers incorrect, roles incomplete/incorrect, e-record/e-signature section incorrect
Philip | Release 01.09.03 | ITS | SPVP | 1 | N/A | A | 2020-02-20
Philip | Release 01.09.03 | ITS | URS/FRS/TM | 16 | N/A | D | 2020-02-20 | Inaccurate information | Approvers incorrect
Philip | Release 01.09.03 | ITS | URS/FRS/TM | 16 | N/A | A | 2020-02-20
Harald | Release 3.1 | MFCS | CII | 2 | N/A | A-FP | 2020-02-20
Philip | Release v33.28.0 | SFP | IVR | 1 | Prod | D | 2020-02-20 | Inaccurate information | Verifier entries incorrect
Philip | Release v33.28.0 | SFP | IVR | 1 | Prod | A | 2020-02-20
Harald | Release 3.1 | MFCS | MP | 1 | N/A | A | 2020-02-21
Philip | Release 01.09.03 | ITS | DV-UT | 1 | N/A | A-FP | 2020-02-24
Philip | Release 01.09.03 | ITS | IDP/IIVP | 1 | N/A | D | 2020-02-24 | Inaccurate information | Approver incorrect
Philip | Release 01.09.03 | ITS | IDP/IIVP | 1 | N/A | A | 2020-02-24
Philip | Release 7.1 | Unicorn | CII | 3 | N/A | D | 2020-02-24 | Inaccurate information | Revision history incomplete
Philip | Release 7.1 | Unicorn | CII | 3 | N/A | A | 2020-02-24
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-02-25
Philip | Release 01.09.03 | ITS | CII | 17 | N/A | D | 2020-02-26 | Inaccurate information | Revision history incomplete
Philip | Release 01.09.03 | ITS | CII | 17 | N/A | A | 2020-02-26
Philip | Release 01.09.03 | ITS | IA | 2 | N/A | A-FP | 2020-02-26
Philip | Release 01.09.03 | ITS | IVR | 1 | GER400 | A-FP | 2020-02-26
Philip | Release 01.09.03 | ITS | SCS/RN | 1 | N/A | D | 2020-02-26 | Inaccurate information | Approvers incorrect
Philip | Release 01.09.03 | ITS | SCS/RN | 1 | N/A | A | 2020-02-26
Philip | Release 01.09.03 | ITS | TPR | 1 | TP09 | A-FP | 2020-02-26
Harald | Release 3.1 | MFCS | SCR | 1 | M1900012 | A-FP | 2020-02-27
Harald | Release 3.1 | MFCS | SCS/RN | 1 | N/A | A-FP | 2020-02-27
Philip | Release 01.09.03 | ITS | IVR | 1 | GER42 | A-FP | 2020-02-28
Philip | Release 01.05.01 | LIC | SPVP | 1 | AQC VERA | D | 2020-02-28 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-02 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.05.01 | LIC | IDP | 1 | AQC VERA | D | 2020-03-04 | Incorrect scope | Offline review.
Philip | Release 01.05.01 | LIC | ESRA | 1 | AQC VERA | D | 2020-03-05 | Inaccurate information | Offline review. AQC090504.A Attachment C no longer exists.
Harald | Release 01.78.00 | LSP | IA | 2 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | TP | 1 | N/A | A-FP | 2020-03-10
Harald | Release 01.78.00 | LSP | URS/FRS/TM | 40 | ZARA | A-FP | 2020-03-10
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-11 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Harald | Release 01.78.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-03-11
Philip | Release 01.05.01 | LIC | MP | 1 | AQC VERA | D | 2020-03-12 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Philip | Release 01.05.01 | LIC | RA | 1 | AQC VERA | D | 2020-03-12 | Multiple Errors | Offline review. Failure modes and causes need to be corrected.
Harald | Release 01.78.00 | LSP | CII | 1 | N/A | A-FP | 2020-03-12
Harald | Release 01.78.00 | LSP | SCS/RN | 1 | N/A | A-FP | 2020-03-12
Harald | Release 01.78.00 | LSP | TPR | 1 | N/A | A-FP | 2020-03-12
Philip | Release 01.05.01 | LIC | RA | 1 | AQC VERA | D | 2020-03-13 | Multiple Errors | Offline review. Mitigations need to be mapped to requirements.
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | AQC VERA | D | 2020-03-13 | Multiple Errors | Offline review. Contents need to be adapted to reflect usage of AQC VERA.
Harald | Release 01.78.00 | LSP | IVR | 1 | GER42 | A-FP | 2020-03-16
Harald | Release 01.78.00 | LSP | SCR | 1 | L1900290 | A-FP | 2020-03-16
Philip | Release 01.05.01 | LIC | TM-URS to FRS | 1 | AQC VERA | D | 2020-03-17 | Multiple Errors | Offline review. Tracing needs rework.
Philip | Release 01.05.01 | LIC | TM-URS/FRS to TP | 1 | AQC VERA | D | 2020-03-17 | Multiple Errors | Offline review. Tracing needs rework.
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-03-18 | Inaccurate information | Wrong SCR
Philip | Release 01.06.00 | ASC | IDP/IIVP | 1 | N/A | A | 2020-03-19
Harald | Release 01.79.00 | LSP | DV-UT | 1 | N/A | A-FP | 2020-03-19
Harald | Release 01.79.00 | LSP | IA | 2 | N/A | D | 2020-03-19 | Inaccurate information | Wrong SCR
Harald | Release 01.79.00 | LSP | IA | 3 | N/A | D | 2020-03-19 | Inaccurate information | Wrong libraries
Harald | Release 01.79.00 | LSP | IA | 4 | N/A | D | 2020-03-19 | Inaccurate information | Missing entry
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-03-19 | Other | SPR L1900281 added
Harald | Release 01.79.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-03-19
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Base) | D | 2020-03-23 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.06.00 | ASC | CII | 11 | N/A | D | 2020-03-23 | Multiple Errors | Object list incomplete and incorrect. Requires Impact Anaylsis update.
Philip | Release 01.06.00 | ASC | IVR | 1 | GER400 | D | 2020-03-23 |  | Incorrect document used.
Philip | Release 01.06.00 | ASC | IVR | 1 | GER400 | A | 2020-03-23
Harald | Release 01.79.00 | LSP | TP | 1 | N/A | D | 2020-03-23 | Multiple Errors | Missing, wrong references to URS.
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Outgoing) | D | 2020-03-24 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Harald | Release 01.79.00 | LSP | IA | 5 | N/A | A | 2020-03-24
Harald | Release 01.79.00 | LSP | TP | 2 | N/A | A | 2020-03-24
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 14 | REA | A-FP | 2020-03-24
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 26 | GIM | D | 2020-03-24 | Multiple Errors | Missing, wrong references to TP.
Harald | Release 01.79.00 | LSP | URS/FRS/TM | 26 | GIM | A | 2020-03-24
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (WebApp) | D | 2020-03-25 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Pricing) | D | 2020-03-25 | Multiple Errors | Offline review. Structure and paths incorrect, requirements contents not matching original
Philip | Release 01.06.00 | ASC | CII | 11 | N/A | A | 2020-03-25
Philip | Release 01.06.00 | ASC | IA | 2 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | CII | 1 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | IDP/IIVP | 2 | N/A | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-03-25
Harald | Release 01.79.00 | LSP | SCS/RN | 1 | N/A | A-FP | 2020-03-26
Harald | Release 01.79.00 | LSP | TPR | 1 | N/A | A-FP | 2020-03-26
Philip | Release 01.06.00 | ASC | IVR | 1 | GER42 | A-FP | 2020-03-27
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | D | 2020-03-27 | Inaccurate information | BIA section incorrect
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | A | 2020-03-27
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | D | 2020-03-27 | Inaccurate information | Data review section incorrect, BIA section incorrect
Philip | Release 01.06.00 | ASC | SCS/RN | 1 | N/A | A | 2020-03-27
Philip | Release 01.06.00 | ASC | TPR | 1 | TP03 | D | 2020-03-27 | Multiple Errors | Copy-paste errors in comments of unexecuted steps.
Philip | Release 01.06.00 | ASC | TPR | 1 | TP03 | A | 2020-03-27
Philip | Release 02.22.00 | ADOC | SCR | 1 | A2000031 | A-FP | 2020-03-30
Philip | Release 02.22.00 | ADOC | SPVP | 1 | N/A | D | 2020-03-30 | Inaccurate information | Approver and project roles incorrectly defined
Harald | Release 01.79.00 | LSP | IVR | 1 | GER42 | D | 2020-03-30 | Inaccurate information | Coment missing
Harald | Release 01.79.00 | LSP | IVR | 1 | GER42 | A | 2020-03-30
Harald | Release 01.79.00 | LSP | SCR | 1 | L1900194 | A-FP | 2020-03-30
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | D | 2020-03-30 | Multiple Errors | Tracing is incomplete
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | D | 2020-03-30 | Multiple Errors | Tracing is incomplete
Philip | Release 02.22.00 | ADOC | IA | 1 | N/A | D | 2020-03-31 | Multiple Errors | Deliverables tailoring justifications insufficient, documentation impact section incorrect
Philip | Release 02.22.00 | ADOC | SPVP | 1 | N/A | A | 2020-03-31
Philip | Release 02.22.00 | ADOC | TP | 1 | TP69 | D | 2020-03-31 | Inaccurate information | Test steps incomplete
Philip | Release 02.22.00 | ADOC | URS/FRS/TM | 26 | Outgoing | D | 2020-03-31 | Inaccurate information | Traceability information incomplete
Philip | Release 02.22.00 | ADOC | DV-UT | 1 | Outgoing | D | 2020-04-01 | Inaccurate information | Unit definitions missing
Philip | Release 02.22.00 | ADOC | DV-UT | 1 | Outgoing | A | 2020-04-01
Philip | Release 02.22.00 | ADOC | IDP/IIVP | 1 | N/A | A-FP | 2020-04-01
Philip | Release 02.22.00 | ADOC | TP | 1 | TP69 | A | 2020-04-01
Philip | Release 02.22.00 | ADOC | CII | 1 | N/A | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | IVR | 1 | GER400 | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | IVR | 1 | GER42 | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | SCS/RN | 1 | N/A | A-FP | 2020-04-02
Philip | Release 02.22.00 | ADOC | TPR | 1 | TP69 | A-FP | 2020-04-02
Philip | Release 13.2 | Fabiola | SCA | 1 | N/A | D | 2020-04-06 | Not following document version control | Not all changes described, or not based on approved version
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-04-07 | Multiple Errors | URS structure not correct for AQC VERA, contents partially incorrect or missing
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-04-08 | Multiple Errors | Roles & responsibilities incomplete, strategy inadequate
Philip | Release 13.2 | Fabiola | SCR | 1 | M2000007 | D | 2020-04-14 | Inaccurate information | Description unacceptable
Philip | Release 13.2 | Fabiola | SCR | 1 | M2000008 | D | 2020-04-14 | Inaccurate information | Replacement SCR for M2000008, description draft needs rework
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Incoming) | D | 2020-04-15 | Multiple Errors | Offline review. Structure not correct, several content errors
Philip | Release 02.2x.xx | ADOC | URS/FRS | 1 | AQC VERA (Outgoing) | D | 2020-04-16 | Inaccurate information | Offline review. Corrections based on urgent COVID-19 release
Philip | Release 01.05.01 | LIC | SCA | 1 | N/A | A | 2020-04-16
Philip | Release 01.05.01 | LIC | SPVP | 1 | N/A | D | 2020-04-17 | Multiple Errors | Formatting issues, timeline correction
Philip | Release 01.05.01 | LIC | ESRA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | IA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | IDP | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | MP | 1 | N/A | D | 2020-04-20 | Multiple Errors | Formatting issues, content adaptation
Philip | Release 01.05.01 | LIC | MP | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | RA | 1 | N/A | A | 2020-04-20
Philip | Release 01.05.01 | LIC | SPVP | 1 | N/A | A | 2020-04-20
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900186 | D | 2020-04-20 | Other | Source Code Names missing
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-04-20 | Inaccurate information | Requirements missing
Harald | Release 01.80.00 | LSP | IDP/IIVP | 1 | N/A | D | 2020-04-20 | Inaccurate information | Empty fields
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | D | 2020-04-20 | Multiple Errors | Tracing is incomplete
Harald | Release 01.80.00 | LSP | TP | 1 | L1900281 | D | 2020-04-20 | Inaccurate information | Expected result unclear
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | D | 2020-04-20 | Multiple Errors | Tracing is incomplete, requirement missing, risk description missing
Philip | Release 01.05.01 | LIC | DV-UT | 1 | N/A | A-FP | 2020-04-21
Philip | Release 01.05.01 | LIC | IIVP | 1 | N/A | A | 2020-04-21
Philip | Release 01.05.01 | LIC | TP | 1 | Legacy Tracing | A | 2020-04-21
Philip | Release 01.05.01 | LIC | TP | 1 | N/A | A | 2020-04-21
Philip | Release 01.05.01 | LIC | URS/FRS | 1 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900186 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | DV-UT | 1 | L1900281 | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | D | 2020-04-21 | Inaccurate information | Time scedule inaccurate
Harald | Release 01.80.00 | LSP | IA | 2 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | IDP/IIVP | 1 | N/A | A | 2020-04-21
Harald | Release 01.80.00 | LSP | SPR | 1 | L1900281 | D | 2020-04-21 | Inaccurate information | Investigation results unclear
Harald | Release 01.80.00 | LSP | TP | 1 | L1900186 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | TP | 1 | L1900281 | A | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 43 | LAG | A | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 48 | PAD | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 23 | SYM | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 16 | COR | A-FP | 2020-04-21
Harald | Release 01.80.00 | LSP | URS/FRS/TM | 3 | CDL | A-FP | 2020-04-21
Philip | Release 01.05.01 | LIC | CII | 1 | N/A | D | 2020-04-22 | Multiple Errors | Adaptations to new AS/400
Philip | Release 01.05.01 | LIC | CII | 1 | N/A | A | 2020-04-22
Philip | Release 01.05.01 | LIC | IVR | 1 | GER400 | A-FP | 2020-04-22
Harald | Release 01.80.00 | LSP | CII | 1 | N/A | A-FP | 2020-04-22
Harald | Release 01.80.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-04-22
Philip | Release 01.05.01 | LIC | SCS/RN | 1 | N/A | A | 2020-04-23
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | TM-URS/FRS to TP | 1 | N/A | A | 2020-04-23
Philip | Release 01.05.01 | LIC | TPR | 1 | Legacy Tracing | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | TPR | 1 | N/A | A-FP | 2020-04-23
Philip | Release 01.05.01 | LIC | IVR | 1 | GER42 | A-FP | 2020-04-24
Harald | Release 01.80.00 | LSP | SCS/RN | 1 | N/A | D | 2020-04-24 | Inaccurate information | SPR reference is missing
Harald | Release 01.80.00 | LSP | SCS/RN | 1 | N/A | A | 2020-04-24
Harald | Release 01.80.00 | LSP | TPR | 1 | L1900186 | A-FP | 2020-04-24
Harald | Release 01.80.00 | LSP | TPR | 1 | L1900281 | A-FP | 2020-04-24
Philip | Release 01.05.01 | LIC | SCS/RN | 2 | N/A | A | 2020-04-28
Harald | Release 01.80.00 | LSP | IVR | 1 | GER42 | A-FP | 2020-04-29
Harald | Release 01.80.00 | LSP | SCR | 1 | L1900186 | A-FP | 2020-04-29
Harald | Release 01.80.00 | LSP | SPR | 1 | L1900281 | A | 2020-04-29
Philip | Release 01.05.01 | LIC | SPR | 1 | A2000019 | A-FP | 2020-04-30
Philip | Release 13.2 | Fabiola | IA | 1 | N/A | D | 2020-05-04 | Multiple Errors | Tailoring table incomplete, system impact incorrect
Philip | Release 13.2 | Fabiola | IDP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Incorrect system name, outlined process inadequate
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Several sections are incorrect (not taking COTS nature into account)
Philip | Release 13.2 | Fabiola | SCA | 1 | N/A | D | 2020-05-04 | Multiple Errors | Changes incompletely implemented
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-05-04 | Multiple Errors | Incorrect systemname, references incorrect, strategy inadequate
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-04 | Multiple Errors | Tracing/references incorrect
Harald | Release 01.81.00 | LSP | IA | 1a | N/A | D | 2020-05-04 | Inaccurate information
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-05 | Multiple Errors | Tracing/references still incorrect
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-06 | Multiple Errors | Tracing/references still incorrect
Philip | Release 13.2 | Fabiola | IA | 1 | N/A | D | 2020-05-12 | Multiple Errors | Tailoring table still incomplete, system impact still incorrect
Philip | Release 13.2 | Fabiola | IDP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Outlined process still needs rework (because of COTS nature)
Philip | Release 13.2 | Fabiola | MP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Several sections are incorrect (not taking COTS nature into account)
Philip | Release 13.2 | Fabiola | SPVP | 1 | N/A | D | 2020-05-12 | Multiple Errors | Formal errors, strategy discussion ongoing, DP aspects not final
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-12 | Multiple Errors | Tracing/references still incorrect, risk classifications inconsistent
Harald | Release 01.81.00 | LSP | IA | 1b | N/A | D | 2020-05-12 | Inaccurate information
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-05-15 | Multiple Errors | Requirement specifications need rework
Harald | Release 01.81.00 | LSP | DV-UT | 1 | L2000059 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | DV-UT | 1 | L2000076 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | IA | 1 | N/A | A | 2020-05-15
Harald | Release 01.81.00 | LSP | IDP/IIVP | 1 | N/A | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | IVR | 1 | GER400 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | TP | 1 | L2000059 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | TP | 1 | L2000076 | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 16 | BOML | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 44 | LAG | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 27 | GIM | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | URS/FRS/TM | 15 | REA | A-FP | 2020-05-15
Harald | Release 01.81.00 | LSP | CII | 1 | N/A | A-FP | 2020-05-18
Harald | Release 01.81.00 | LSP | IDP/IIVP | 2 | N/A | A-FP | 2020-05-18
Harald | Release 01.81.00 | LSP | SCS/RN | 1a | N/A | D | 2020-05-18 | Inaccurate information
Harald | Release 01.81.00 | LSP | SCS/RN | 1 | N/A | A | 2020-05-19
Harald | Release 01.81.00 | LSP | SPVP | 6a | Generic | D | 2020-05-19 | Inaccurate information
Harald | Release 01.81.00 | LSP | TPR | 1a | L2000059 | D | 2020-05-19 | Inaccurate information
Harald | Release 01.81.00 | LSP | TPR | 1 | L2000059 | A | 2020-05-19
Harald | Release 01.81.00 | LSP | TPR | 1 | L2000076 | A-FP | 2020-05-19
Philip | Release 13.2 | Fabiola | URS | 1 | N/A | D | 2020-05-20 | Multiple Errors | Tracing/references still incorrect
Harald | Release 01.81.00 | LSP | SPVP | 6 | Generic | A | 2020-05-20
Harald | Release 01.81.00 | LSP | IVR | 2 | GER42 | A-FP | 2020-05-27
Harald | Release 01.81.00 | LSP | SCR | 1 | L2000059 | A-FP | 2020-05-27
Harald | Release 01.81.00 | LSP | SPR | 1 | L2000076 | A-FP | 2020-05-27
Philip | Release 13.2 | Fabiola | SE | 1 | N/A | D | 2020-05-28 | Multiple Errors | Content and result do not match, several process and logical errors
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-05-29 | Multiple Errors | Item type selections partially incorrect, contents still need some rework
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-12 | Multiple Errors | Several RS include content errors or are missing completely
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-17 | Multiple Errors | Some RS have been created as Groups, risk classifications need to be changed and tracing is missing entirely
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-19 | Multiple Errors | Tracing is still partially missing, one risk classification is missing
Philip | Release 01.11.01 | CMSN-Add-On | URS/FRS | 1 | N/A | D | 2020-06-23 | Multiple Errors | Additional changes required, contents incorrect, tracing is still partially missing