## ACR
SQA | Application | ACR # | Date of CR Approval or Disapproval | CR Approve or Disapprove? | ACR I&E # | Date of I&E Approval or Disapproval | I&E Approve or Disapprove? | Reason for Disapproval | Comments
Lan | Global Product Part Master (GPPM) | CSIT09631 | 2019-07-11 | A-FP
Lan | Global Product Part Master (GPPM) | CSIT09639 | 2019-08-05 | A-FP
Lan | Global Product Part Master (GPPM) | CSIT09694 | 2019-07-31 | A-FP

## FPA
SQA | Project ID | Application | Deliverable | Doc Version | Doc ID, if needed | Approve or Disapprove? | Date of Approval or Disapproval | Reason for Disapproval | Comments
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | URS | 5 | SRS-01ver5 FRS for QIST v3.2 | D | 2019-07-21 | Inaccurate information | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | URS | 5 | SRS-01ver5 FRS for QIST v3.2 | A | 2019-07-24
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | FRS | 5 | SRS-01ver5 FRS for QIST v3.2 | D | 2019-08-01 | Inaccurate information | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | FRS | 5 | SRS-01ver5 FRS for QIST v3.2 | A | 2019-08-12
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Project Plan | 5 | SPP-02ver01 SPP for QIST v3.2 | D | 2019-08-01 | Inaccurate information | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Project Plan | 1 | SPP-02ver01 SPP for QIST v3.2 | A | 2019-07-29
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Validation Plan | 1 | SPP-02ver01 SPP for QIST v3.2 | D | 2019-08-27 | Mutlible Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Validation Plan | 1 | SPP-02ver01 SPP for QIST v3.2 | D | 2019-08-29 | Inaccurate information | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Validation Plan | 1 | SPP-02ver01 SPP for QIST v3.2 | A | 2019-09-03
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | SCR-02v01 Software Change Request | D | 2019-09-03 | Mutlible Errors | Email
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 2 | SCR-02v01 Software Change Request | A | 2019-08-08
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | URS | 1 | URS-01v02 User Requirements Specification] | D | 2019-08-02 | Mutlible Errors | Email
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | URS | 1 | URS-01v02 User Requirements Specification] | A | 2019-08-08
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol | 2 | Protocol-01v02 Protocol | D | 2019-08-05 | Mutlible Errors | Email
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol | 3 | Protocol-01v02 Protocol | A | 2019-08-09
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Test Protocol Results | 1 | Protocol-01v02 Protocol Result | A | 2019-08-09
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | CII | 1 | VDD-02v01 CII / Spreadsheet Template v1.10 | D | 2019-08-08 | Mutlible Errors | Email
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | CII | 1 | VDD-02v01 CII / Spreadsheet Template v1.10 | A | 2019-08-08
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-09 | Mutlible Errors | Email
Lan | DA-S 01457.000 | Gravimetric Vol. Cal Spreadsheet v1.10 | Software Change Request | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-09
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP results | 1 | Install-02v01 Result | D | 2019-08-04 | Not compliant with procedure | Email
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP results | 1 | Install-02v01 Result | A | 2019-08-08
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP | 2 | Install-02v02 | D | 2019-08-09 | Not compliant with procedure
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP | 2 | Install-02v02 | A | 2019-08-09
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP results | 2 | Install-02v02 Result | A-FP | 2019-08-21
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP results | 2 | Protocol 59 Result | D | 2019-09-03 | Not compliant with procedure | Email
Lan | DA-S 00536.004 | GSS Reliability Database | IIVP results | 2 | Protocol 60 Result | D | 2019-09-03 | Not compliant with procedure | Email
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 2 | SQA-08 | D | 2019-08-29 | Not compliant with procedure | AWC 3.3 upgrade to AWC 4.2, use new extension
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 1 | SQA-09 | D | 2019-08-28 | N/A | Email
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-02 | Not using template | Email
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-22 | Other | Email
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-08-30 | Other | Email
Ken | DA-S01449.000 | PRISM OMT Test Fixture | CII | 2 |  | D | 2019-08-13 | Inaccurate information | CII change without IPDR
Ken | DA-S01449.000 | PRISM OMT Test Fixture | IIVP results | 1 | Install-01 Results | D | 2019-08-13 | Inaccurate information | Does not match CII
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Software Change Request | 8 | SCR-08 | D | 2019-07-10 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Software Change Request | 8 | SCR-08 | A | 2019-07-30 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | URS | 3 | URS-03 | D | 2019-07-16 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | URS | 3 | URS-03 | A | 2019-07-31 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | FRS | 5 | FRS-05 | D | 2019-08-01 | Inaccurate information | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | FRS | 5 | FRS-05 | A | 2019-08-08 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 2 | Protocol -08 | D | 2019-08-21 | Mutlible Errors | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 2 | Protocol -08 | A | 2019-08-26 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 1 | Protocol -09 | D | 2019-08-22 | Mutlible Errors | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 1 | Protocol -09 | A | 2019-08-27 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Test Protocol | 7 | Install -01 | A | 2019-08-19 |  | NPV
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Traceability | 4 | Tmatrix-01 | D | 2019-08-22 | Insufficient traceability | Email
Arun | DA-S 01112.000 | Calibrator PDF to XML Converter | Traceability | 4 | Tmatrix-01 | A | 2019-08-29 |  | NPV
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-03 | D | 2019-07-19 | Inaccurate information | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-03 | A | 2019-07-22 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-03 Results | D | 2019-08-26 | Incorrect Approvers | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-03 Results | A | 2019-08-26 | N/A | Approve Failed Results in NPV
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 2 | Install-03 | A | 2019-08-07 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 2 | Install-03 Results | A | 2019-08-09 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 3 | Install-03 | D | 2019-08-23 | Inaccurate information | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 3 | Install-03 Results | A-FP | 2019-08-24 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-04 | A | 2019-08-29 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-04 Results | A | 2019-08-30 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-02 | D | 2019-07-19 | Mutlible Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-02 | A | 2019-07-22 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP results | 1 | Install-02 | A | 2019-07-29 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol | 1 | Protocol-23 | A | 2019-08-10 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol Results | 1 | Protocol-23 | D | 2019-08-20 | Mutlible Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol Results | 1 | Protocol-23 | A | 2019-08-23 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP | 1 | Install-01 | A-FP | 2019-07-22 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP results | 1 | Install-01 | A-FP | 2019-08-10 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | IIVP results | 1 | Install-01 | A-FP | 2019-08-29
Carole | DA-S00922.001 | ADMS Purchasing | Test Protocol | 1 | Protocol-26 | A-FP | 2019-07-29 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Test Protocol Results | 1 | Protocol-26 | A | 2019-08-24 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-22 | Mutlible Errors | Email
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-24 | Mutlible Errors | Email
Carole | DA-S00922.001 | ADMS Purchasing | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP | 1 | Install-01 | A-FP | 2019-07-22 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-01 | A-FP | 2019-08-10 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-01 | A-FP | 2019-08-29 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol | 1 | Protocol-10 | A-FP | 2019-07-29 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol Results | 1 | Protocol-10 | A-FP | 2019-08-23 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Traceability | 2 | TMatrixUSPro-01 | A | 2019-08-12 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00923.001 | ADMS Work in Progress | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26
Carole | DA-S00931.001 | ADMS Order Management | IIVP | 1 | Install-03 | A-FP | 2019-07-22 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-03 | A-FP | 2019-08-10 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-03 | A-FP | 2019-08-29 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol | 1 | Protocol-24 | A-FP | 2019-08-08 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-24 | A-FP | 2019-08-23 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Traceability | 5 | TMatrixUSPro-01 | A | 2019-08-10 | N/A
Carole | DA-S00931.001 | ADMS Order Management | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | D | 2019-08-23 | Mutlible Errors | Email
Carole | DA-S00931.001 | ADMS Order Management | System Certification Summary | 1 | VVSR-02v01 System Certification Summary Report | A | 2019-08-26
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-01 | D | 2019-08-01 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-02 | D | 2019-08-01 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-01 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-02 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-03 | A | 2019-08-02 | N/A
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-05 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-06 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | D | 2019-08-15 | Mutlible Errors | Email
Carole | DA-S01509.000 | ESD | System Certification Summary | 1 | Validation Summary Report-01 | A | 2019-08-16 | N/A
Carole | DA-S01509.000 | ESD | IIVP results | 2 | Install-01 | D | 2019-08-22 | Mutlible Errors
Carole | DA-S01509.000 | ESD | IIVP results | 2 | Install-01 | A | 2019-08-22 | N/A
Carole | DA-S01509.000 | ESD | Other | 3 | Deployment Plan (Post IQ)-01 | D | 2019-08-22 | Inaccurate information | Email
Carole | DA-S01509.000 | ESD | Other | 3 | Deployment Plan (Post IQ)-01 | A | 2019-08-23 | N/A
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-09-03 | Other | Not complete
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Software Change Request | 2 | SCR-09 | D | 2019-09-09 | Inaccurate information
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Software Change Request | 2 | SCR-09 | A | 2019-09-09
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 2 | SQA-08 | A | 2019-09-16
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | URS/FRS | 13 | SRS-01 | D | 2019-09-16 | Requirement deficiency
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | URS/FRS | 13 | SRS-01 | A | 2019-09-16
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Design Documentation | 12 | SDD-01 (SCR-09) | A-FP | 2019-09-12
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | IIVP | 1 | Install-10 (SCR-09) | A-FP | 2019-09-12
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 1 | Protocol-21 (SCR-09) | D | 2019-09-12 | Mutlible Errors
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 1 | Protocol-21 (SCR-09) | D | 2019-09-13 | Inaccurate information
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 1 | Protocol-21 (SCR-09) | A | 2019-09-16
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Traceability | 10 | TMatrixUSPro-01 | D | 2019-09-16 | Inaccurate information
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Traceability | 10 | TMatrixUSPro-01 | A | 2019-09-16
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Software Change Request | 1 | SCR-10 | D | 2019-09-10 | Inaccurate information | Copied of SCR-09 without complete review
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Software Change Request | 1 | SCR-10 | A | 2019-09-12
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | IIVP | 1 | Install-11 (SCR-10) | A-FP | 2019-09-12
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 2 | Protocol-17 | A-FP | 2019-09-12
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol Results | 2 | Protocol-17 Result | D | 2019-09-27 | Inaccurate information
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Software Change Request | 2 | SCR-12 | D | 2019-09-13 | Inadequate Description of Change
Ken | DA-S01449.000 | PRISM OMT Test Fixture | IIVP results | 1 | Install-01 Results | D | 2019-09-17 | Incorrect Objective Evidence
Ken | DA-S01449.000 | PRISM OMT Test Fixture | IIVP results | 1 | Install-01 Results | A | 2019-09-17
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | D | 2019-09-17 | Not compliant with procedure
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol | 1 | Protocol-02 | A | 2019-09-18
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Software Change Request | 2 | SCR-12 | A | 2019-09-17
Ken | DA-S 01194.001 | APLM - QSR Workflow | Other | 1 | Pointer to base validation for common deliverables eRIM, BIA, etc. | A-FP | 2019-09-18
Ken | DA-S 01514.000 | SBM System Level Event Tracking | Other | 1 | Pointer to base validation for eRIM | A-FP | 2019-09-18
Ken | DA-S 01514.000 | SBM System Level Event Tracking | Other | 1 | Pointer to base validation for BIA | A-FP | 2019-09-18
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 3 | SQA-08 | D | 2019-09-27 | Incorrect Approvers
Ken | DA-S01194.000 | APLM - QSR Workflow | Software Change Request | 3 | SQA-08 | A | 2019-09-27
Arun | DA-S01519.000 | CMIA Reader Tester Software | Software Change Request | 1 | SCR-01 | D | 2019-09-25 | Multiple Errors | Email
Arun | DA-S01519.000 | CMIA Reader Tester Software | Software Compliance Assessment | 1 | Assessment-01 | D | 2019-09-24 | Multiple Errors | Email
Arun | DA-S01194.001 | APLM - QSR Workflow | Software Change Request | 1 | SCR-02 | D | 2019-09-19 | Not compliant with procedure | Email
Arun | DA-S01194.001 | APLM - QSR Workflow | Software Change Request | 1 | SCR-02 | D | 2019-09-25 | Not compliant with procedure | Email
Arun | DA-S01194.001 | APLM - QSR Workflow | Software Change Request | 1 | SCR-02 | D | 2019-09-27 | Not compliant with procedure | Email
Arun | DA-S01194.001 | APLM - QSR Workflow | Software Change Request | 1 | SCR-02 | D | 2019-09-30 | Multiple Errors | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 2 | Install-16 | D | 2019-09-19 | Multiple Errors | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 2 | Install-16 | A | 2019-09-25 |  | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 2 | Install-15 | D | 2019-09-19 |  | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 2 | Install-15 | A | 2019-09-25 | Multiple Errors | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 1 | Install -19 | A | 2019-09-23 |  | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | CII | 10 | VDD-01 | A | 2019-09-23 |  | NPV
Arun | DA-S 01194 . 001 | APLM - QSR Workflow | Software Change Request | 3 | SCR-01 - Pointer to the base validation deliverable SCR-08 | A | 2019-09-24 |  | NPV
Arun | DA-S 01194 . 001 | APLM - QSR Workflow | Test Protocol | 2 | Protocol -02 Pointer | A | 2019-09-27
Arun | DA-S 01194 . 001 | APLM - QSR Workflow | ERES | 1 | ERESRisk-01 to the pointer | A | 2019-09-27
Lan | DA-S 00622 . 008 | GPPM DB Server Move | Software Change Request | 1 | SCR-31 | D | 2019-09-02 | Multiple Errors | Email
Lan | DA-S 00622 . 008 | GPPM DB Server Move | Software Change Request | 1 | SCR-31 | A | 2019-09-05 |  | NPV
Lan | DA-S 00622 . 008 | GPPM DB Server Move | IIVP | 15 | Install-1 | D | 2019-09-02 | Multiple Errors | NPV
Lan | DA-S 00622 . 008 | GPPM DB Server Move | IIVP | 15 | Install-1 | A | 2019-09-05 |  | NPV
Lan | DA-S 00622 . 008 | GPPM DB Server Move | Install Result | 1 | Install-15 Result | A-FP | 2019-09-28
Lan | DA-S 00622 . 008 | GPPM DB Server Move | MtP for QA | 1 | MtP-62 | A-FP | 2019-09-21
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Software Change Request | 1 | SCR-35 | D | 2019-09-02 | Multiple Errors | Email
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Software Change Request | 1 | SCR-35 | A | 2019-09-05 |  | NPV
Lan | DA-S 00562.005 | Ticket Code Tool Server move | IIVP | 7 | Install-1 | D | 2019-09-02 | Multiple Errors | NPV
Lan | DA-S 00562.005 | Ticket Code Tool Server move | IIVP | 7 | Install-1 | A | 2019-09-05 |  | NPV
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Install Result | 7 | Install-1 Result | A-FP | 2019-09-28
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Install Result | 1 | Protocol-46 | D | 2019-09-18 | Multiple Errors | Email
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Install Result | 1 | Protocol-46 | D | 2019-09-18 | Multiple Errors | Email
Lan | DA-S 00562.005 | Ticket Code Tool Server move | Install Result | 1 | Protocol-46 | A | 2019-09-21
Lan | DA-S 00562.005 | Ticket Code Tool Server move | MtP for QA | 1 | MtP-81 | A-FP | 2019-09-21
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Software Change Request | 1 | SCR-04 | D | 2019-09-23
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Software Change Request | 1 | SCR-04 | D | 2019-09-25
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Software Change Request | 1 | SCR-04 | A | 2019-09-27
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | User Requirement Specifications (URS) | 2 | URS-01 | D | 2019-09-25 | Multiple Errors | Email
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | User Requirement Specifications (URS) | 2 | URS-01 | A | 2019-09-27
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Functional Requirements Specification (FRS) | 2 | FRS-01 | D | 2019-09-25 | Multiple Errors | Email
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Functional Requirements Specification (FRS) | 2 | FRS-01 | A | 2019-09-27
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 2 | Prortocol-1 | D | 2019-09-23 | Not compliant with procedure | Email
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 2 | Prortocol-1 | A | 2019-09-30
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 1 | Protocol-17 | D | 2019-09-24 | Not compliant with procedure | Email
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 1 | Protocol-17 | A | 2019-09-30
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 1 | Protocol-18 | A-FP | 2019-09-30
Lan | DA-S 1332.003 | ICQDeviceSim v1.3.4 | Protocol | 1 | Protocol-19 | A-FP | 2019-09-30
Lan | DA-S 1254.000 | IDA (Instrument Data Analytics) | Software Change Request | 1 | SCR-08 | D | 2019-09-27 | Not compliant with procedure | NPV
Lan | DA-S 1254.000 | IDA (Instrument Data Analytics) | Software Change Request | 1 | SCR-08 | D | 2019-09-30 | Not compliant with procedure | NPV
Lan | DA-S 1254.000 | IDA (Instrument Data Analytics) | Software Change Request | 1 | SCR-08 | A | 2019-09-30
Lan | DA-S 1497.000 | Abbott Collaborative Environment (ACE) | Software Change Request | 2 | SCR-02 | D | 2019-09-18 | Multiple Errors | Email
Lan | DA-S 1497.000 | Abbott Collaborative Environment (ACE) | Software Change Request | 2 | SCR-02 | A | 2019-09-19
Lan | DA-S 1475.001 | LOG-ICAL | Project Plan | 1 | SPP-01 | D | 2019-08-19 | Multiple Errors | Email
Lan | DA-S 1475.001 | LOG-ICAL | Project Plan | 1 | SPP-01 | D | 2019-09-24 | Multiple Errors | Email
Lan | DA-S 1475.001 | LOG-ICAL | Project Plan | 1 | SPP-01 | A | 2019-09-30
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | USTest-03 | A | 2019-09-21
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | USTest-03 Result | D | 2019-09-21 | Incorrect Objective Evidence | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 2 | USTest-03 | D | 2019-09-21 | Mutlible Errors | Email
Lan | DA-S 01069.004 | QIST : Quality Impact Score Tool 3.3 | Test Protocol | 2 | USTest-03 | A | 2019-09-30
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD-03 | D | 2019-09-27 | Mutlible Errors
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD-03 | D | 2019-09-29 | Mutlible Errors
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD-03 | A | 2019-09-30 |  | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-56 | D | 2019-09-12 | Incorrect Objective Evidence | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-56 | D | 2019-09-21 | Incorrect Objective Evidence | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-56 | D | 2019-09-25 | Mutlible Errors
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-56 | A | 2019-09-25
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-59 | D | 2019-09-12 | Incorrect Objective Evidence | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-59 | D | 2019-09-25 | Mutlible Errors | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-59 | D | 2019-09-25 | Mutlible Errors | NPV
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-59 | A | 2019-09-25
Lan | DA-S 01520.000 | GSS Reliability Database | Test Protocol Results | 1 | SCA-01 | D | 2019-09-25 | Mutlible Errors | NPV
Lan | DA-S 01520.000 | GSS Reliability Database | Test Protocol Results | 1 | SCA-01 | A | 2019-09-25
Carole | DA-S00931.001 | ADMS Order Management | Software Change Request | 1 | SCR-20 | D | 2019-09-04 | Multiple Errors | Email
Carole | DA-S00931.001 | ADMS Order Management | Software Change Request | 1 | SCR-20 | A | 2019-09-10 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-20-Results | D | 2019-09-04 | Incorrect Objective Evidence | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-20-Results | D | 2019-09-09 | Incorrect Objective Evidence | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-20-Results | A | 2019-09-17 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 2 | Protocol-19-Results | D | 2019-09-04 | Incorrect Objective Evidence | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 2 | Protocol-19-Results | D | 2019-09-09 | Incorrect Objective Evidence | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 2 | Protocol-19-Results | A | 2019-09-17 | N/A | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-08-Results | D | 2019-09-04 | Incorrect Objective Evidence | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 1 | Protocol-08-Results | A | 2019-09-16 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 2 | Protocol-02-Results | D | 2019-09-04 | Multiple Errors | Email
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol | 3 | Protocol-02 | A | 2019-09-12 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Test Protocol Results | 3 | Protocol-02 | A | 2019-09-16 | N/A
Carole | DA-S00931.001 | ADMS Order Management | Software Change Request | 1 | SCR-21 | D | 2019-09-11 | Multiple Errors | Email
Carole | DA-S00931.001 | ADMS Order Management | Software Change Request | 1 | SCR-21 | D | 2019-09-12 | Inadequate Description of Change | Email
Carole | DA-S00931.001 | ADMS Order Management | Software Change Request | 1 | SCR-21 | A | 2019-09-30 | N/A
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-02 | D | 2019-09-19 | Inaccurate information | Email
Carole | DA-S00931.001 | ADMS Order Management | IIVP results | 1 | Install-02 | A | 2019-09-26 | N/A
Carole | DA-S01509.000 | ESD | Software Change Request | 1 | SCR-02 | D | 2019-09-09 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | Software Change Request | 1 | SCR-02 | D | 2019-09-11 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | Software Change Request | 1 | SCR-02 | A | 2019-09-12 | N/A
Carole | DA-S01509.000 | ESD | URS | 3 | URS-01 | D | 2019-09-11 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | URS | 3 | URS-01 | A | 2019-09-13 | N/A
Carole | DA-S01509.000 | ESD | Traceability | 2 | TMatrixUSPro-01 | D | 2019-09-12 | Other | Email
Carole | DA-S01509.000 | ESD | Traceability | 2 | TMatrixUSPro-01 | A | 2019-09-13 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol | 1 | Protocol-04 | D | 2019-09-11 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol | 1 | Protocol-04 | D | 2019-09-12 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol | 1 | Protocol-04 | D | 2019-09-12 | Multiple Errors | Email
Carole | DA-S01509.000 | ESD | Test Protocol | 1 | Protocol-04 | A | 2019-09-13 | N/A
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-04 Results | D | 2019-09-13 | Inaccurate information | Email
Carole | DA-S01509.000 | ESD | Test Protocol Results | 1 | Protocol-04 Results | A | 2019-09-13
Carole | DA-S01509.000 | ESD | IIVP results | 2 | Installation instructions and Verification Protocol Results-01 | A | 2019-09-16
Carole | DA-S01510.000 | Camstar | Software Change Request | 1 | SCR-03 | D | 2019-09-05 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | Software Change Request | 1 | SCR-03 | D | 2019-09-06 | Inadequate Description of Change | Email
Carole | DA-S01510.000 | Camstar | Software Change Request | 1 | SCR-03 | D | 2019-09-12 | Inadequate Description of Change | Email
Carole | DA-S01510.000 | Camstar | Software Change Request | 1 | SCR-03 | A | 2019-09-16 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-82 | D | 2019-09-06 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-82 | D | 2019-09-10 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-82 | A | 2019-09-18 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-80 | D | 2019-09-09 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-80 | A | 2019-09-25 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol | 2 | Protocol-80 | A-FP | 2019-09-25 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-81 | D | 2019-09-09 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | Test Protocol | 1 | Protocol-81 | A | 2019-09-18 | N/A
Carole | DA-S01510.000 | Camstar | Traceability | 2 | TMatrixUSPro-01 | D | 2019-09-18 | Other | Email
Carole | DA-S01510.000 | Camstar | Traceability | 2 | TMatrixUSPro-01 | A | 2019-09-18 | N/A
Carole | DA-S01510.000 | Camstar | CII | 2 | VDD-01 | D | 2019-09-17 | Incorrect Approvers | Email
Carole | DA-S01510.000 | Camstar | IIVP | 1 | Install-06 | D | 2019-09-17 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | IIVP | 1 | Install-06 | D | 2019-09-18 | Multiple Errors | Email
Carole | DA-S01510.000 | Camstar | IIVP | 1 | Install-06 | A | 2019-09-18 | N/A
Carole | DA-S01510.000 | Camstar | IIVP results | 1 | Install-06-Results | A | 2019-09-19 | N/A
Carole | DA-S01510.000 | Camstar | IIVP results | 1 | Install-06-Results | A | 2019-09-27 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol Results | 1 | Protocol-82-Results | A-FP | 2019-09-26 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol Results | 1 | Protocol-81-Results | A | 2019-09-20 | N/A
Carole | DA-S01510.000 | Camstar | Test Protocol Results | 1 | Protocol-80-Results | D | 2019-09-23 | Incorrect Objective Evidence | Email
Carole | DA-S01510.000 | Camstar | Test Protocol Results | 2 | Protocol-80-Results | A | 2019-09-26 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-04-Results | A | 2019-09-11 | N/A
Carole | DA-S00921.001 | ADMS Inventory | Software Change Request | 1 | SCR-11 | D | 2019-09-27 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS Inventory | URS | 1 | URS-06 | D | 2019-09-30 | Incorrect Approvers | Email
Carole | DA-S00921.001 | ADMS Inventory | FRS | 1 | SRS-07 | D | 2019-09-30 | N/A
Carole | DA-S00922.001 | ADMS Purchasing | Software Change Request | 1 | SCR-41 | D | 2019-09-30 | Inadequate Description of Change | Email
Carole | DA-S00923.001 | ADMS Work in Progress | Software Change Request | 1 | SCR-05 | D | 2019-09-27 | Multiple Errors | Email
Carole | DA-S00923.001 | ADMS Work in Progress | URS | 1 | URS-03 | D | 2019-09-30 | Incorrect Approvers | Email
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol Results | 1 | Protocol-17 Result | A | 2019-09-27
Ken | DA-S 01194.001 | APLM - QSR Workflow | Software Compliance Assessment | 1 | Assessment-01 | D | 2019-09-18 | Incorrect Approvers
Ken | DA-S 01194.001 | APLM - QSR Workflow | Software Compliance Assessment | 1 | Assessment-01 | A | 2019-09-27
Ken | DA-S 01194.001 | APLM - QSR Workflow | CII | 1 | VDD-01 | D | 2019-09-30 | Inaccurate information | Email
Ken | DA-S 01194.001 | APLM - QSR Workflow | CII | 1 | VDD-01 | A | 2019-09-30
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 2 | Protocol-21 (SCR-09) | D | 2019-09-30 | Insufficient testing | Update to incorporate corrections found during execution
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | Test Protocol | 2 | Protocol-21 | A | 2019-09-30
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | System Certification Summary | 1 | VVSR-10v01 | D | 2019-09-30 | Inaccurate information | Email
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | System Certification Summary | 1 | VVSR-10v01 | A | 2019-09-30
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-06 | D | 2019-10-01 | Incorrect Approvers | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 2 | Install-06 | D | 2019-10-07 | Inadequate Description of Change | Email
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 1 | Install-06 | A | 2019-10-01 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP | 2 | Install-06 | A | 2019-10-07 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 1 | Install-06 | A-FP | 2019-10-01 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 2 | Install-06 | A-FP | 2019-10-07 | N/A
Carole | DA-S00919.004 | ADMS Global Module | IIVP results | 2 | Install-06 | A-FP | 2019-10-07 | N/A
Carole | DA-S00919.004 | ADMS Global Module | CII | 9 | VDD-02 | D | 2019-10-15 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol | 1 | Protocol-24 | D | 2019-10-07 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol | 1 | Protocol-24 | A | 2019-10-10 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Test Protocol | 2 | Protocol-24 | A-FP | 2019-10-14 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-03 | D | 2019-10-15 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP | 1 | Install-03 | A | 2019-10-16 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP results | 1 | Install-03 | D | 2019-10-17 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | IIVP results | 1 | Install-03 | A | 2019-10-18 | N/A
Carole | DA-S00921.001 | ADMS R12 - Inventory | Software Change Request | 1 | SCR-12 | D | 2019-10-24 | Multiple Errors | Email
Carole | DA-S00921.001 | ADMS R12 - Inventory | Software Change Request | 1 | SCR-12 | A | 2019-10-30 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol | 1 | Protocol-11 | A-FP | 2019-10-10 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol | 2 | Protocol-11 | D | 2019-10-14 | Other | Email
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol | 2 | Protocol-11 | A | 2019-10-15 | N/A | Email
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP | 1 | Install-02 | D | 2019-10-15 | Multiple Errors
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP | 1 | Install-02 | A | 2019-10-16 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-02 | D | 2019-10-17 | Multiple Errors | Email
Carole | DA-S00923.001 | ADMS Work in Progress | IIVP results | 1 | Install-02 | A | 2019-10-17 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Software Change Request | 1 | SCR-06 | D | 2019-10-24 | Multiple Errors | Email
Carole | DA-S00923.001 | ADMS Work in Progress | Software Change Request | 1 | SCR-06 | A | 2019-10-31 | N/A
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol Results | 2 | Protocol-11 Results | D | 2019-10-29 | Incorrect Objective Evidence | Email
Carole | DA-S00923.001 | ADMS Work in Progress | Test Protocol Results | 2 | Protocol-11 Results | A | 2019-10-31 | N/A
Carole | DA-S00926.002 | ADMS Quality | Test Protocol | 1 | Protocol-20 | D | 2019-10-11 | Multiple Errors | Email
Carole | DA-S00926.002 | ADMS Quality | Test Protocol | 2 | Protocol-19 | D | 2019-10-14 | Multiple Errors | Email
Carole | DA-S00926.002 | ADMS Quality | Test Protocol | 2 | Protocol-19 | A | 2019-10-16 | N/A
Carole | DA-S00926.002 | ADMS Quality | Test Protocol Results | 2 | Protocol-19 | D | 2019-10-17 | Multiple Errors | Email
Carole | DA-S00926.002 | ADMS Quality | Test Protocol Results | 2 | Protocol-19 | A | 2019-10-17 | N/A
Carole | DA-S01510.001 | Camstar | Software Change Request | 1 | SCR-01 | D | 2019-10-10 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | Software Change Request | 1 | SCR-01 | D | 2019-10-15 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | Software Change Request | 1 | SCR-01 | D | 2019-10-15 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | Software Change Request | 1 | SCR-01 | A | 2019-10-15 | N/A
Carole | DA-S01510.001 | Camstar | Validation Plan | 1 | Project/Validation Plan-01 | D | 2019-10-11 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | Validation Plan | 1 | Project/Validation Plan-01 | D | 2019-10-11 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | Validation Plan | 1 | Project/Validation Plan-01 | A | 2019-10-24 | N/A | Email
Carole | DA-S01510.001 | Camstar | URS | 1 | URS-01 | D | 2019-10-10 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | URS | 1 | URS-01 | A | 2019-10-24 | N/A
Carole | DA-S01510.001 | Camstar | FRS | 1 | FRS-01 | D | 2019-10-10 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | FRS | 1 | FRS-01 | D | 2019-10-28 | Multiple Errors | Email
Carole | DA-S01510.001 | Camstar | FRS | 1 | FRS-01 | D | 2019-10-29 | Multiple Errors | Email
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | CII | 1 | VDD-02 | D | 2019-10-21 | Inaccurate information | email
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | CII | 1 | VDD-02 | D | 2019-10-25 | Inaccurate information | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | CII | 1 | VDD-02 | A | 2019-10-28 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-13 | A | 2019-10-28 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-14 | A | 2019-10-22 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-15 | A | 2019-10-22 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | IIVP results | 1 | Install 1-Resulst | A | 2019-10-29 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-05 | A | 2019-10-28 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-06 | A | 2019-10-08 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-07 | A | 2019-10-08 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-08 | A | 2019-10-08 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-09 | A | 2019-10-08 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-10 | A | 2019-10-08 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-11 | A | 2019-10-09 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-12 | A | 2019-10-09 |  | NPV
Arun | DA-S01194.001 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 1 | Protocol-13 | A | 2019-10-09 |  | NPV
Arun | DA-S01519.000 | CMIA Reader Tester Software | FRS | 2 | FRS-01 | D | 2019-10-16 | Multiple Errors | Email
Arun | DA-S01519.000 | CMIA Reader Tester Software | FRS | 2 | FRS-01 | D | 2019-10-25 | Multiple Errors | Email
Arun | DA-S01519.000 | CMIA Reader Tester Software | Risk Assessment | 1 | Other-1 | D | 2019-10-15 | Inaccurate information | NPV
Arun | DA-S01519.000 | CMIA Reader Tester Software | Test Protocol | 1 | Test protocol -1 | D | 2019-10-23 | Inaccurate information | email
Arun | DA-S01519.000 | CMIA Reader Tester Software | IIVP | 1 | IIVP-1 | D | 2019-10-24 | Inaccurate information | email
Arun | DA-S01519.000 | CMIA Reader Tester Software | Project Plan | 1 | SPP-01 | D | 2019-10-16 | Multiple Errors | email
Arun | DA-S01519.000 | CMIA Reader Tester Software | Project Plan | 1 |  | A | 2019-10-22 |  | NPV
Arun | DA-S01204.000 | HL7 Simulator for ARCHITECT | Software Change Request | 3 | SCR-03 | D | 2019-10-18 | Inaccurate information | email
Arun | DA-S01204.000 | HL7 Simulator for ARCHITECT | Software Change Request | 3 | SCR-03 | A | 2019-10-24 |  | NPV
Arun | DA-S01287.000 | Compliance Test System (CTS) - Harmonics & Flicker Test Software | IIVP results | 1 | Install 1-Results | A | 2019-10-17 |  | NPV
Arun | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP | 1 | Install-15 | A | 2019-10-21 |  | NPV
Ken | DA-S01449.000 | PRISM OMT Test Fixture | Test Protocol Results | 1 | Protocol-02 Result | D | 2019-10-01 | Inaccurate information | Steps call for color observation but OE in B&W
Ken | DA-S01190.003 | Abbott Product Lifecycle Management (APLM) | Design Verification | 1 | TechRevSDDCode01v01 | A-FP | 2019-10-07
Ken | DA-S00893.006 | Mashup - Product Defect Tracking | IIVP results | N/A | Install-10 Result | A-FP | 2019-10-07
Ken | DA-S 01194.001 | APLM - QSR Workflow | FRS | 1 | SRS-01v01 | D | 2019-10-07 | Incorrect Approvers
Ken | DA-S 01194.001 | APLM - QSR Workflow | FRS | 1 | SRS-01v01 | D | 2019-10-07 | Inaccurate information
Ken | DA-S 01194.001 | APLM - QSR Workflow | URS/FRS | 1 | URS-01v01 | D | 2019-10-07 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 4 | Protocol-15v04 | D | 2019-10-07 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 4 | Protocol-15v04 | A | 2019-10-07
Ken | DA-S 01194.001 | APLM - QSR Workflow | FRS | 1 | SRS-01v01 | D | 2019-10-08 | Mutlible Errors
Ken | DA-S 01194.001 | APLM - QSR Workflow | Test Protocol | 1 | Protocol-12v01 | D | 2019-10-08 | Inaccurate information
Ken | DA-S 01194.001 | APLM - QSR Workflow | Test Protocol | 1 | Protocol-13v01 | D | 2019-10-08 | Inaccurate information
Ken | DA-S 01194.001 | APLM - QSR Workflow | Test Protocol | 1 | Protocol-13v01 | A | 2019-10-08
Ken | DA-S 01194.001 | APLM - QSR Workflow | Traceability | 1 | TMatrixUSPro-01 | D | 2019-10-08 | Inaccurate information
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol | 2 | Protocol-01v02 | A-FP | 2019-10-08
Ken | DA-S 01449.000 | PRISM OMT Test Fixture | System Certification Summary | 1 | DA-S01449.000_VVSR-01 | D | 2019-10-21 | Inaccurate information
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 2 | Install-09v02 | D | 2019-10-21 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 2 | Install-16v02 | D | 2019-10-21 | Incorrect Approvers
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 1 | Install-19v01 | D | 2019-10-21 | Incorrect Approvers
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Other | 1 | APLM -TcEDA checklist for windows 10 | A-FP | 2019-10-21
Ken | DA-S 01435.000 | SBM - Affiliate CAPA | Software Change Request | 1 | SCR-01v01 | D | 2019-10-21 | Mutlible Errors | Email
Ken | DA-S 01449.000 | PRISM OMT Test Fixture | System Certification Summary | 1 | VVSR-01v01 | D | 2019-10-21 | Mutlible Errors | Email
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 1 | Install-19v01 Results | A | 2019-10-24
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 2 | Install-09v01 Results | D | 2019-10-30 | Incorrect Approvers
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | IIVP results | 2 | Install-09v01 Results | A | 2019-10-31
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol Results | 2 | Protocol-01v02 Results | D | 2019-10-30 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol Results | 2 | Protocol-01v02 Results | D | 2019-10-31 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol Results | 2 | Protocol-02v02 Results | A-FP | 2019-10-30
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol Results | 1 | Protocol-04v01 Results | D | 2019-10-31 | Mutlible Errors
Ken | DA-S 01190.003 | Abbott Product Lifecycle Management (APLM) | Test Protocol Results | 2 | Protocol-01v02 Results | D | 2019-10-31 | Mutlible Errors
Lan | DA-S 01520.000 | Jenkins | Software Compliance Assessment | 2 | Assessment01 | A | 2019-10-17 | Multiple Errors | Email
Lan | DA-S 01520.000 | Jenkins | Software Change Request | 1 | SCR-01 | A | 2019-10-28 | Multiple Errors | Email
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-56 Result | A-FP | 2019-10-16
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol-59 Result | A-FP | 2019-10-16
Lan | DA-S 00536.004 | GSS Reliability Database | Other | 1 | MtP63 | A-FP | 2019-10-08
Lan | DA-S 00536.004 | GSS Reliability Database | Other | 1 | MtP64 | A-FP | 2019-10-11
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol | 1 | Protocol61 v01 | A | 2019-10-07 | Multiple Errors | Email
Lan | DA-S 00536.004 | GSS Reliability Database | Test Protocol Results | 1 | Protocol61 v01 result | A-FP | 2019-10-11
Lan | DA-S 00536.004 | GSS Reliability Database | Software Change Request | 1 | SCR49 | A-FP | 2019-10-01
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | DepPlan01 | 1 | DepPlan01 | D | 2019-10-25 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | DepPlan01 | 1 | DepPlan01 | D | 2019-10-25 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | DepPlan01 | 1 | DepPlan01 | A | 2019-10-25
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Other | 1 | Other06 | A-FP | 2019-10-29
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | ISSD | 1 | Other09 | A | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | ISSD | 1 | Other09 | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | ISSD | 1 | Other09 | A | 2019-10-25
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol14 | D | 2019-10-01 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol14 | A | 2019-10-03
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol14 Result | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol14 Result | A | 2019-10-22
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol15 | D | 2019-10-01 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol15 | A | 2019-10-03
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol15 Result. | A-FP | 2019-10-25
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol16 | A-FP | 2019-10-28
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol16 Result | D | 2019-10-30 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Test Protocol | 1 | Protocol16 Result | A | 2019-10-30
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | FRS | 1 | SRS01 | A-FP | 2019-10-28
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Traceability | 1 | TMatrixUSPro01 | D | 2019-10-30 | Multiple Errors | NPV
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | Traceability | 1 | TMatrixUSPro01 | A | 2019-10-28
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD03 | D | 2019-10-28 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD03 | D | 2019-10-28 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 1 | VDD03 | A | 2019-10-28
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | CII | 2 | VDD03 | A-FP | 2019-10-28
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | IIVP | 1 | Install03 QA | D | 2019-10-03 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | IIVP | 1 | Install03 QA | D | 2019-10-05 | Multiple Errors | Email
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | IIVP | 1 | Install03 QA | A | 2019-10-08
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | IIVP results | 1 | Install03 QA result | A | 2019-10-10
Lan | DA-S 01069.003 | QIST : Quality Impact Score Tool 3.2 | IIVP | 1 | Install04 prod | A-FP | 2019-10-28
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | IIVP | 1 | Install01 | D | 2019-10-14 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | IIVP | 1 | Install01 | A | 2019-10-14
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol01 | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol01 | A | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol01 result | A-FP | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol15 | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol15 | A | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol15 Result. | A-FP | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol17 | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol17 | A | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol17 Result | A-FP | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol19 | D | 2019-10-21 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol19 | A | 2019-10-21
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Test Protocol | 1 | Protocol19 Result | A-FP | 2019-10-22
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | Other | 1 | UDoc01 | A-FP | 2019-10-11
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | CII | 1 | VDD01 | D | 2019-10-10 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | CII | 1 | VDD01 | A | 2019-10-10
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | System Certification Summary | 1 | VVSR05 | D | 2019-10-28 | Multiple Errors | Email
Lan | DA-S 01332 . 003 | ICQDeviceSim v1.3.4 | System Certification Summary | 1 | VVSR05 | A | 2019-10-28
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | IIVP | 1 | Install04 | D | 2019-10-20 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | IIVP | 1 | Install04 | D | 2019-10-20 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | IIVP | 1 | Install04 | A | 2019-10-29
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Software Change Request | 1 | SCR08 | D | 2019-10-01
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Software Change Request | 1 | SCR08 | D | 2019-10-02 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Software Change Request | 1 | SCR08 | A | 2019-10-07
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Design Documentation | 1 | SDD01 | D | 2019-10-18 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Design Documentation | 1 | SDD01 | A | 2019-10-28
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Design Verification | 1 | TechRevSDDCode02 | D | 2019-10-18 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | Design Verification | 1 | TechRevSDDCode02 | A | 2019-10-28
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | CII | 1 | VDD03 | D | 2019-10-09 | Multiple Errors | Email
Lan | DA-S 01254.000 | IDA Data Mart (Maintenance) | CII | 1 | VDD03 | A | 2019-10-28
Lan | DA-S 01466 . 000 | IDA-Q | IIVP | 1 | Install11 | D | 2019-10-28 | Multiple Errors | Email
Lan | DA-S 01466 . 000 | IDA-Q | IIVP | 1 | Install11 | A | 2019-10-29
Lan | DA-S 01466 . 000 | IDA-Q | Design Documentation | 1 | Other17 | D | 2019-10-23 | Multiple Errors | Email
Lan | DA-S 01466 . 000 | IDA-Q | Design Documentation | 1 | Other17 | A | 2019-10-25
Lan | DA-S 01466 . 000 | IDA-Q | Test Protocol | 1 | Protocol24 | D | 2019-10-29 | Multiple Errors | NPV
Lan | DA-S 01466 . 000 | IDA-Q | Test Protocol | 1 | Protocol24 | A | 2019-10-29
Lan | DA-S 01466 . 000 | IDA-Q | Software Change Request | 1 | SCR13 | D | 2019-10-17 | Multiple Errors | Email
Lan | DA-S 01466 . 000 | IDA-Q | Software Change Request | 1 | SCR13 | A | 2019-10-17
Lan | DA-S 01466 . 000 | IDA-Q | Software Change Request | 1 | SCR14 v01 | D | 2019-10-25 | Multiple Errors | Email
Lan | DA-S 01466 . 000 | IDA-Q | Software Change Request | 1 | SCR14 v01 | A | 2019-10-25
Lan | DA-S 01466 . 000 | IDA-Q | Design Verification | 1 | TechRevSDDCode07 | D | 2019-10-29 | Multiple Errors | NPV
Lan | DA-S 01466 . 000 | IDA-Q | Design Verification | 1 | TechRevSDDCode07 | A | 2019-10-29
Lan | DA-S 01466 . 000 | IDA-Q | CII | 1 | VDD07 | D | 2019-10-31 | Multiple Errors | NPV
Lan | DA-S 01466 . 000 | IDA-Q | CII | 1 | VDD07 | A | 2019-10-31

## SQA
Arun
Carole
Ken
Lan
Liz

## Application
Application | Application Owner or BRM
Abbott Collaborative Environment (ACE)
Abbott Product Lifecycle Management (APLM)
AbbottLink Q Simulator
ADMS Account payable
ADMS Advance Supply Chain
ADMS Bills of Material
ADMS Cost/GL management
ADMS Demantra
ADMS Engineering
ADMS Global Module
ADMS Inventory
ADMS iSupplier
ADMS MPS/MRP
ADMS Order Management
ADMS Purchasing
ADMS Quality
ADMS ShipConsole
ADMS Warehouse Management
ADMS Work in Progress
Alinity S Result QC
ALISS (Alinity LIS Simulator)
Amplifier Research (AR) emcware - Radiated Immunity (Susceptibility) Test Software
APLM - Design Planning (DP) Workflow
APLM - QSR Workflow
Architect Instrument Test Station Configuration Software
Assay Checker Update for Architect Software version 8.1
Automated Refrigeration Monitoring System (ARMS)
Bamboo for Unit Test Result Reporting
BSQ Device Simulator - EP
Calibrator PDF to XML Converter
Camstar
CMIA Reader Tester Software
Compliance Test System (CTS) - Harmonics & Flicker Test Software
Desco / Edge ESD Tester
ESD
File Verification Suite
Global Product Part Master (GPPM)
Gravimetric Vol. Cal Spreadsheet v1.10
GSS Reliability Database
HL7 Simulator for BSQ (HL7SIM-BSQ)
HP Quality Center Version 11.0 Validation
IBM Rational ClearCase
ICQ Device Simulator 1.3
IDA (Instrument Data Analytics)
IDA Data Mart (Maintenance)
IDA Data Mart 2.0 Assay Early Warning
IDA Data Mart 3.0 - Westgard Automation
IDA ETL A3600
IDA-Q
Induction Heating Serial/USB GUI
Ixiasoft DITA Content Management System
LIS Simulator
Load Runner
Loftware Software Suite
LOG-ICAL
Mashup - Design Plan
Mashup - Product Defect Tracking
MobileONe
Proactive Operations Monitoring 2.10
Q ASTM Simulator
QIA Server Interface Simulator
QIST : Quality Impact Score Tool 3.2
Reference Standard Inspection Spreadsheet Template
SBM Affiliate CAPA
SBM DCR
SBM Distributor Control
SBM Machine Shop (SBM MS)
SBM Meetings Application
SBM Pre-Market Issue Tracking
SBM System Level Event Tracking
Serena Business Manager (SBM) - Base (Core) Application Upgrade
Software Tool Access Request System (STARS)
SolidWorks Enterprise Product Data Management (SWEPDM)
Stats CC Data Process
SyncMyGSS - APLM to GSS Web Publish
Team Track - Non-Product Software Problem Reporting
Ticket Code Tool Database and ASP Interface
Ticket Code Tool DB Server move
GPPM DB Server Move
Jenkins
ICQDeviceSim v1.3.4

## Deliverable Types
Cancellation
CII
Data Migration Plan
Data Privacy Plan
Decommissioning Plan
Decommissioning Report
Design Documentation
Design Verification
ERES
FRS
IDP
IIVP
IIVP results
ISSD
Maintenance Plan
Move to Production
Other
Project Plan
Release Notes
Risk Assessment
Software Change Request
Software Compliance Assessment
System Certification Summary
Test Protocol
Test Protocol Results
Traceability
URS
URS/FRS
User Acceptance Protocol
User Acceptance Protocol results
Validation Plan

## Reasons for Disapproval
Inaccurate information
Inadequate Description of Change
Incorrect Approvers
Incorrect Objective Evidence
Incorrect scope
Insufficient testing
Insufficient traceability
Multiple Errors
N/A
Not compliant with procedure
Not following configuration management
Not following document version control
Not using template
Other
Requirement deficiency

## A or D
A
D
A-FP